## Sheet1
Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING
Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L) | Selected Group :- A-Chemical Waterproofing Work (L)
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
466526 | A-2nd Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.001.001. | 0.0000 | Labour | 0 | 0.0000
466526 | A-2nd Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.001.001. | 2.0000 | Labour | 0 | 0.0000
466526 | A-2nd Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.001.001. | 2.0000 | Labour | 0 | 0.0000
466528 | A-3rd Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.002.001. | 0.0000 | Labour | 0 | 0.0000
466528 | A-3rd Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.002.001. | 2.0000 | Labour | 0 | 0.0000
466528 | A-3rd Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.002.001. | 2.0000 | Labour | 0 | 0.0000
466530 | A-4th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.003.001. | 0.0000 | Labour | 0 | 0.0000
466530 | A-4th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.003.001. | 2.0000 | Labour | 0 | 0.0000
466530 | A-4th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.003.001. | 2.0000 | Labour | 0 | 0.0000
466532 | A-5th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.004.001. | 0.0000 | Labour | 0 | 0.0000
466532 | A-5th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.004.001. | 2.0000 | Labour | 0 | 0.0000
466532 | A-5th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.004.001. | 2.0000 | Labour | 0 | 0.0000
466534 | A-6th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.005.001. | 0.0000 | Labour | 0 | 0.0000
466534 | A-6th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.005.001. | 2.0000 | Labour | 0 | 0.0000
466534 | A-6th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.005.001. | 2.0000 | Labour | 0 | 0.0000
466536 | A-7th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.006.001. | 0.0000 | Labour | 0 | 0.0000
466536 | A-7th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.006.001. | 2.0000 | Labour | 0 | 0.0000
466536 | A-7th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.006.001. | 2.0000 | Labour | 0 | 0.0000
466538 | A-8th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.007.001. | 0.0000 | Labour | 0 | 0.0000
466538 | A-8th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.007.001. | 2.0000 | Labour | 0 | 0.0000
466538 | A-8th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.007.001. | 2.0000 | Labour | 0 | 0.0000
466540 | A-9th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.008.001. | 0.0000 | Labour | 0 | 0.0000
466540 | A-9th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.008.001. | 2.0000 | Labour | 0 | 0.0000
466540 | A-9th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.008.001. | 2.0000 | Labour | 0 | 0.0000
466542 | A-10th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.009.001. | 0.0000 | Labour | 0 | 0.0000
466542 | A-10th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.009.001. | 2.0000 | Labour | 0 | 0.0000
466542 | A-10th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.009.001. | 2.0000 | Labour | 0 | 0.0000
466544 | A-11th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.010.001. | 0.0000 | Labour | 0 | 0.0000
466544 | A-11th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.010.001. | 2.0000 | Labour | 0 | 0.0000
466544 | A-11th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.010.001. | 2.0000 | Labour | 0 | 0.0000
466546 | A-12th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.011.001. | 0.0000 | Labour | 0 | 0.0000
466546 | A-12th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.011.001. | 2.0000 | Labour | 0 | 0.0000
466546 | A-12th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.011.001. | 2.0000 | Labour | 0 | 0.0000
466548 | A-13th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.012.001. | 0.0000 | Labour | 0 | 0.0000
466548 | A-13th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.012.001. | 2.0000 | Labour | 0 | 0.0000
466548 | A-13th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.012.001. | 2.0000 | Labour | 0 | 0.0000
466550 | A-14th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.013.001. | 0.0000 | Labour | 0 | 0.0000
466550 | A-14th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.013.001. | 2.0000 | Labour | 0 | 0.0000
466550 | A-14th Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.013.001. | 2.0000 | Labour | 0 | 0.0000
466552 | A-15th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.014.001. | 0.0000 | Labour | 0 | 0.0000
466552 | A-15th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.014.001. | 2.0000 | Labour | 0 | 0.0000
466552 | A-15th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.014.001. | 2.0000 | Labour | 0 | 0.0000
466554 | A-16th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1069 | 0.0000 | 158.001.001.003.007.001.001.015.001. | 0.0000 | Labour | 0 | 0.0000
466554 | A-16th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.015.001. | 2.0000 | Labour | 0 | 0.0000
466554 | A-16th Floor-Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1069 | 2.0000 | 158.001.001.003.007.001.001.015.001. | 2.0000 | Labour | 0 | 0.0000
466556 | A-Terrace Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 348 | 0.0000 | 158.001.001.003.007.001.001.016.001. | 0.0000 | Labour | 0 | 0.0000
466556 | A-Terrace Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 348 | 2.0000 | 158.001.001.003.007.001.001.016.001. | 2.0000 | Labour | 0 | 0.0000
466556 | A-Terrace Floor -Common Lobby Chemical Grouting Work | Floor | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 348 | 2.0000 | 158.001.001.003.007.001.001.016.001. | 2.0000 | Labour | 0 | 0.0000