## Sheet1
Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS
Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint | Selected Group :- Northside Texture Paint
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376766 | Stilt Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376767 | 1st Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1563.36 | 0.0000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 2.2500 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 3.0000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1563.36 | 1.2000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1563.36 | 5.0000 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376768 | 2nd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376769 | 3rd Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376770 | 4th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376771 | 5th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376772 | 6th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1563.36 | 0.0000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 2.2500 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 3.0000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1563.36 | 1.2000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1563.36 | 5.0000 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376773 | 7th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376774 | 8th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376775 | 9th Floor North side Acrylic Texture Paint | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376776 | 10th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376777 | 11th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1563.36 | 0.0000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 2.2500 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 3.0000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1563.36 | 1.2000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1563.36 | 5.0000 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376778 | 12th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376779 | 13th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376780 | 14th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376781 | 15th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376782 | 16th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.017.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1563.36 | 0.0000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 2.2500 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 3.0000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1563.36 | 1.2000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1563.36 | 5.0000 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376783 | 17th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.018.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376784 | 18th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.019.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376785 | 19th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.020.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376786 | 20th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.021.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376788 | 21st Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.022.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1563.36 | 0.0000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 2.2500 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1563.36 | 1.0000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1563.36 | 3.0000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1563.36 | 1.2000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1563.36 | 5.0000 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376789 | 22nd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1563.36 | 1.6500 | 154.006.002.004.015.004.001.023.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376790 | 23rd Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.024.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000
376791 | 24th Floor North side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.001.025.001. | 0.0000 | Labour | 0 | 0.0000