## Sheet1
Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS
Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint | Selected Group :- Southside Texture Paint
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376794 | Stilt Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
376795 | 1st Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1897.37 | 0.0000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 2.2500 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 3.0000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1897.37 | 1.2000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1897.37 | 5.0000 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
384119 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376797 | 3rd Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376798 | 4th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.005.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376800 | 5th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.006.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
376801 | 6th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.007.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1897.37 | 0.0000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 2.2500 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 3.0000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1897.37 | 1.2000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1897.37 | 5.0000 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
384120 | 7th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.008.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376803 | 8th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.009.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376804 | 9th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.010.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376805 | 10th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.011.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
376806 | 11th Fl South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.012.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1897.37 | 0.0000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 2.2500 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 3.0000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1897.37 | 1.2000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1897.37 | 5.0000 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
384121 | 12th Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.013.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376808 | 13th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.014.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376809 | 14th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.015.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376810 | 15th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.016.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
376811 | 16th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.017.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1897.37 | 0.0000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 2.2500 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 3.0000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1897.37 | 1.2000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1897.37 | 5.0000 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
384122 | 17th Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.018.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376813 | 18th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.019.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376814 | 19th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.020.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376815 | 20th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.021.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
376816 | 21st Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.022.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1897.37 | 0.0000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 2.2500 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1897.37 | 1.0000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1897.37 | 3.0000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1897.37 | 1.2000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1897.37 | 5.0000 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
384123 | 22nd Fl-Refuge Fl-South Acylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1897.37 | 1.6500 | 154.006.002.004.015.004.002.023.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376818 | 23rd Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.024.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1625.15 | 0.0000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 2.2500 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1625.15 | 1.0000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1625.15 | 3.0000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1625.15 | 1.2000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1625.15 | 5.0000 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000
376819 | 24th Fl-South Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1625.15 | 1.6500 | 154.006.002.004.015.004.002.025.001. | 0.0000 | Labour | 0 | 0.0000