## Sheet1
Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS | Project :- GANGA ALTUS
Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint | Selected Group :- Eastside Texture Paint
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376845 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376846 | 1st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1413.58 | 0.0000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 2.2500 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 3.0000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1413.58 | 1.2000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1413.58 | 5.0000 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376847 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376848 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376849 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.005.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376850 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.006.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376851 | 6th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.007.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1413.58 | 0.0000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 2.2500 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 3.0000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1413.58 | 1.2000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1413.58 | 5.0000 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376852 | 7th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.008.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376853 | 8th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.009.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376854 | 9th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.010.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376855 | 10th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.011.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376856 | 11th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.012.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1413.58 | 0.0000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 2.2500 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 3.0000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1413.58 | 1.2000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1413.58 | 5.0000 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376857 | 12th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.013.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376858 | 13th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.014.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376859 | 14th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.015.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376860 | 15th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.016.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376861 | 16th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.017.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1413.58 | 0.0000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 2.2500 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 3.0000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1413.58 | 1.2000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1413.58 | 5.0000 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376862 | 17th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.018.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376863 | 18th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.019.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376864 | 19th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.020.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376865 | 20th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.021.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376866 | 21st Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.022.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1413.58 | 0.0000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 2.2500 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1413.58 | 1.0000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1413.58 | 3.0000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1413.58 | 1.2000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1413.58 | 5.0000 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376867 | 22nd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1413.58 | 1.6500 | 154.006.002.004.015.004.004.023.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 2.2500 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 1.0000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 3.0000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 1.2000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 5.0000 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376868 | 23rd Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 1.6500 | 154.006.002.004.015.004.004.024.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 1704 | Texture Paint (L) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000
376869 | 24th Fl-East side Acrylic Texture Paint - 1 Floor | Floor | 1.0000 | 1.0000 | 7329 | Texture Paint (M) | Sq.Ft | 1449.09 | 0.0000 | 154.006.002.004.015.004.004.025.001. | 0.0000 | Labour | 0 | 0.0000