## Sheet1
Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING
Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work | Selected Group :- A-North Side Texture Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468099 | A-2nd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.001.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468100 | A-3rd Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.002.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468101 | A-4th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.003.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468102 | A-5th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.004.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468103 | A-6th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.005.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468104 | A-7th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.006.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1823.79 | 1.0000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1823.79 | 0.0000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1823.79 | 1.0000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1823.79 | 2.2500 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1823.79 | 1.0000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1823.79 | 3.0000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1823.79 | 1.2000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1823.79 | 5.0000 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 1704 | Texture Paint (L) | Sq.Ft | 1823.79 | 1.6500 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468105 | A-8th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 7329 | Texture Paint (M) | Sq.Ft | 1823.79 | 1.6500 | 158.001.001.003.013.001.007.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468106 | A-9th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.008.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468107 | A-10th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.009.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468108 | A-11th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.010.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468109 | A-12th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.011.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1823.79 | 1.0000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1823.79 | 0.0000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1823.79 | 1.0000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1823.79 | 2.2500 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1823.79 | 1.0000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1823.79 | 3.0000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1823.79 | 1.2000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1823.79 | 5.0000 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 1704 | Texture Paint (L) | Sq.Ft | 1823.79 | 1.6500 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468110 | A-13th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2175.0400 | 7329 | Texture Paint (M) | Sq.Ft | 1823.79 | 1.6500 | 158.001.001.003.013.001.012.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468111 | A-14th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.013.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468112 | A-15th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.014.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1945.55 | 0.0000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 2.2500 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1945.55 | 1.0000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1945.55 | 3.0000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1945.55 | 1.2000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1945.55 | 5.0000 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 1704 | Texture Paint (L) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468113 | A-16th Floor North Side Texture with Acrylic Paint | Floor | 1.0000 | 2202.5800 | 7329 | Texture Paint (M) | Sq.Ft | 1945.55 | 1.6500 | 158.001.001.003.013.001.015.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 1704 | Texture Paint (L) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468114 | A-Terrace Floor- Texture with Acrylic Paint | Floor | 1.0000 | 2997.2600 | 7329 | Texture Paint (M) | Sq.Ft | 660.79 | 0.0000 | 158.001.001.003.013.001.016.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 1704 | Texture Paint (L) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000
468115 | A-Machine Room+OHWT Texture with Acrylic Paint | Floor | 1.0000 | 4230.1700 | 7329 | Texture Paint (M) | Sq.Ft | 0 | 0.0000 | 158.001.001.003.013.001.017.001. | 0.0000 | Labour | 0 | 0.0000