## Sheet1
Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING
Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work | Selected Group :- A-East Side Texture Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468131 | A-2nd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2488.7300 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.001.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468132 | A-3rd Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.002.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468133 | A-4th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.003.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468134 | A-5th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.004.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468135 | A-6th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.005.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468136 | A-7th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.006.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468137 | A-8th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.007.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468138 | A-9th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.008.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468139 | A-10th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.009.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468140 | A-11th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.010.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468141 | A-12th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.011.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468142 | A-13th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.012.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468143 | A-14th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.013.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468144 | A-15th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.014.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1418.5 | 0.0000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 2.2500 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1418.5 | 1.0000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1418.5 | 3.0000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1418.5 | 1.2000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1418.5 | 5.0000 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 1704 | Texture Paint (L) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000
468145 | A-16th Floor East Side Texture with Acrylic Paint | Floor | 1.0000 | 2323.1400 | 7329 | Texture Paint (M) | Sq.Ft | 1418.5 | 1.6500 | 158.001.001.003.013.003.015.001. | 0.0000 | Labour | 0 | 0.0000