## Sheet1
Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING
Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work | Selected Group :- A-West Side Texture Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468146 | A-2nd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1019.6500 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.001.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468147 | A-3rd Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.002.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468148 | A-4th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.003.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468149 | A-5th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.004.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468150 | A-6th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.005.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468151 | A-7th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.006.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468152 | A-8th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.007.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468153 | A-9th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.008.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1002.39 | 0.0000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 2.2500 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1002.39 | 1.0000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1002.39 | 3.0000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1002.39 | 1.2000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1002.39 | 5.0000 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468154 | A-10th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1002.39 | 1.6500 | 158.001.001.003.013.004.009.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1254.35 | 0.0000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 2.2500 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 3.0000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1254.35 | 1.2000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1254.35 | 5.0000 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468155 | A-11th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.010.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1254.35 | 0.0000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 2.2500 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 3.0000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1254.35 | 1.2000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1254.35 | 5.0000 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468156 | A-12th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.011.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1254.35 | 0.0000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 2.2500 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 3.0000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1254.35 | 1.2000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1254.35 | 5.0000 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468157 | A-13th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.012.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1254.35 | 0.0000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 2.2500 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 3.0000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1254.35 | 1.2000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1254.35 | 5.0000 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468158 | A-14th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.013.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1254.35 | 0.0000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 2.2500 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 3.0000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1254.35 | 1.2000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1254.35 | 5.0000 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468159 | A-15th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.014.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1254.35 | 0.0000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 2.2500 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1254.35 | 1.0000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1254.35 | 3.0000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1254.35 | 1.2000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1254.35 | 5.0000 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 1704 | Texture Paint (L) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000
468160 | A-16th Floor West Side Texture with Acrylic Paint | Floor | 1.0000 | 1174.9300 | 7329 | Texture Paint (M) | Sq.Ft | 1254.35 | 1.6500 | 158.001.001.003.013.004.015.001. | 0.0000 | Labour | 0 | 0.0000