## Sheet1
Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING | Project :- GANGA ARCADIA - A BUILDING
Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture | Selected Group :- A-Common Lobby Duct Texture
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 1.0000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 1.0000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 2.2500 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 1.0000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 3.0000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 1.2000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 5.0000 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 1.6500 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620004 | A-2nd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 1.6500 | 158.001.001.003.010.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620006 | A-3rd Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620008 | A-4th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620010 | A-5th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620012 | A-6th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.005.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620014 | A-7th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.006.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620016 | A-8th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.007.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620018 | A-9th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.008.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620020 | A-10th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.009.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620022 | A-11th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.010.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620024 | A-12th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.011.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620026 | A-13th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.012.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620028 | A-14th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.013.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620030 | A-15th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.014.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 1704 | Texture Paint (L) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620032 | A-16th Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 1671.7700 | 1671.7700 | 7329 | Texture Paint (M) | Sq.Ft | 1705.45 | 0.0000 | 158.001.001.003.010.004.001.015.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12505 | 1st Coat Acrylic Paint (L) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12504 | 1st Coat Acrylic Paint (M) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12507 | 2nd Coat Acrylic Paint (L) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12506 | 2nd Coat Acrylic Paint (M) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 12509 | Final Cleaning & Housekeeping work (L) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 5668 | Scaffolding Fixing Work - DER | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 1704 | Texture Paint (L) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000
620034 | A-Terrace Floor Comm. Lobby Duct Texture Paint | Sq.Ft | 767.7000 | 767.7000 | 7329 | Texture Paint (M) | Sq.Ft | 767.7000 | 0.0000 | 158.001.001.003.010.004.001.016.001. | 0.0000 | Labour | 0 | 0.0000