## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 630598 | D - Umra Patti Work | NA | 0.0000 | 0.0000 | 0 | 628785 | 31 | 0 | [6 empty] | 0.0000
2 | 630599 | D - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
3 | 630600 | D - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
4 | 630601 | D -301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 3 | 630600 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
5 | 630602 | D - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
6 | 630603 | D -302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 5 | 630602 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
7 | 630604 | D - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
8 | 630605 | D -303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 7 | 630604 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
9 | 630606 | D - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
10 | 630607 | D -304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 9 | 630606 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
11 | 630608 | D - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
12 | 630609 | D -305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 11 | 630608 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
13 | 630610 | D - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
14 | 630611 | D -306 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 13 | 630610 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
15 | 630612 | D - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
16 | 630613 | D -307 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 15 | 630612 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
17 | 630614 | D - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
18 | 630615 | D -308 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 17 | 630614 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
19 | 630616 | D - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
20 | 630617 | D -309 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 19 | 630616 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
21 | 630618 | D - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
22 | 630619 | D -310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 21 | 630618 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
23 | 630620 | D - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
24 | 630621 | D -311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 23 | 630620 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
25 | 630622 | D - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
26 | 630623 | D -312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 25 | 630622 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
27 | 630624 | D - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
28 | 630625 | D -313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 27 | 630624 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
29 | 630626 | D - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 630599 | 31 | 0 | [6 empty] | 0.0000
30 | 630627 | D -314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 29 | 630626 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
31 | 630628 | D - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
32 | 630629 | D - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
33 | 630630 | D -401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 32 | 630629 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
34 | 630631 | D - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
35 | 630632 | D -402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 34 | 630631 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
36 | 630633 | D - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
37 | 630634 | D -403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 36 | 630633 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
38 | 630635 | D - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
39 | 630636 | D -404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 38 | 630635 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
40 | 630637 | D - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
41 | 630638 | D -405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 40 | 630637 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
42 | 630639 | D - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
43 | 630640 | D -406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 42 | 630639 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
44 | 630641 | D - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
45 | 630642 | D -407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 44 | 630641 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
46 | 630643 | D - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
47 | 630644 | D -408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 46 | 630643 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
48 | 630645 | D - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
49 | 630646 | D -409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 48 | 630645 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
50 | 630647 | D - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
51 | 630648 | D -410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 50 | 630647 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
52 | 630649 | D - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
53 | 630650 | D -411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 52 | 630649 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
54 | 630651 | D - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
55 | 630652 | D -412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 54 | 630651 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
56 | 630653 | D - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
57 | 630654 | D -413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 56 | 630653 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
58 | 630655 | D - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 630628 | 31 | 0 | [6 empty] | 0.0000
59 | 630656 | D -414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 58 | 630655 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
60 | 630657 | D - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
61 | 630658 | D - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
62 | 630659 | D -501 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 61 | 630658 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
63 | 630660 | D - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
64 | 630661 | D -502 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 63 | 630660 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
65 | 630662 | D - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
66 | 630663 | D -503 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 65 | 630662 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
67 | 630664 | D - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
68 | 630665 | D -504 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 67 | 630664 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
69 | 630666 | D - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
70 | 630667 | D -505 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 69 | 630666 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
71 | 630668 | D - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
72 | 630669 | D -506 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 71 | 630668 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
73 | 630670 | D - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
74 | 630671 | D -507 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 73 | 630670 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
75 | 630672 | D - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
76 | 630673 | D -508 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 75 | 630672 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
77 | 630674 | D - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
78 | 630675 | D -509 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 77 | 630674 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
79 | 630676 | D - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
80 | 630677 | D -510 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 79 | 630676 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
81 | 630678 | D - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
82 | 630679 | D -511 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 81 | 630678 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
83 | 630680 | D - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
84 | 630681 | D -512 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 83 | 630680 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
85 | 630682 | D - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
86 | 630683 | D -513 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 85 | 630682 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
87 | 630684 | D - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 630657 | 31 | 0 | [6 empty] | 0.0000
88 | 630685 | D -514 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 87 | 630684 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
89 | 630686 | D - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
90 | 630687 | D - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
91 | 630688 | D -601 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 90 | 630687 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
92 | 630689 | D - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
93 | 630690 | D -602 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 92 | 630689 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
94 | 630691 | D - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
95 | 630692 | D -603 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 94 | 630691 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
96 | 630693 | D - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
97 | 630694 | D -604 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 96 | 630693 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
98 | 630695 | D - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
99 | 630696 | D -605 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 98 | 630695 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
100 | 630697 | D - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
101 | 630698 | D -606 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 100 | 630697 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
102 | 630699 | D - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
103 | 630700 | D -607 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 102 | 630699 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
104 | 630701 | D - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
105 | 630702 | D -608 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 104 | 630701 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
106 | 630703 | D - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
107 | 630704 | D -609 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 106 | 630703 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
108 | 630705 | D - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
109 | 630706 | D -610 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 108 | 630705 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
110 | 630707 | D - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
111 | 630708 | D -611 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 110 | 630707 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
112 | 630709 | D - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
113 | 630710 | D -612 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 112 | 630709 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
114 | 630711 | D - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
115 | 630712 | D -613 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 114 | 630711 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
116 | 630713 | D - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 630686 | 31 | 0 | [6 empty] | 0.0000
117 | 630714 | D -614 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 116 | 630713 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
118 | 630715 | D - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
119 | 630716 | D - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
120 | 630717 | D -701 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 119 | 630716 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
121 | 630718 | D - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
122 | 630719 | D -702 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 121 | 630718 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
123 | 630720 | D - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
124 | 630721 | D -703 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 123 | 630720 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
125 | 630722 | D - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
126 | 630723 | D -704 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 125 | 630722 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
127 | 630724 | D - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
128 | 630725 | D -705 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 127 | 630724 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
129 | 630726 | D - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
130 | 630727 | D -706 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 129 | 630726 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
131 | 630728 | D - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
132 | 630729 | D -707 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 131 | 630728 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
133 | 630730 | D - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
134 | 630731 | D -708 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 133 | 630730 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
135 | 630732 | D - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
136 | 630733 | D -709 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 135 | 630732 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
137 | 630734 | D - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
138 | 630735 | D -710 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 137 | 630734 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
139 | 630736 | D - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
140 | 630737 | D -711 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 139 | 630736 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
141 | 630738 | D - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
142 | 630739 | D -712 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 141 | 630738 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
143 | 630740 | D - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
144 | 630741 | D -713 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 143 | 630740 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
145 | 630742 | D - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 630715 | 31 | 0 | [6 empty] | 0.0000
146 | 630743 | D -714 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 145 | 630742 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
147 | 630744 | D - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
148 | 630745 | D - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
149 | 630746 | D -801 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 148 | 630745 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
150 | 630747 | D - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
151 | 630748 | D -802 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 150 | 630747 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
152 | 630749 | D - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
153 | 630750 | D -803 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 152 | 630749 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
154 | 630751 | D - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
155 | 630752 | D -804 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 154 | 630751 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
156 | 630753 | D - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
157 | 630754 | D -805 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 156 | 630753 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
158 | 630755 | D - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
159 | 630756 | D -806 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 158 | 630755 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
160 | 630757 | D - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
161 | 630758 | D -807 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 160 | 630757 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
162 | 630759 | D - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
163 | 630760 | D -808 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 162 | 630759 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
164 | 630761 | D - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
165 | 630762 | D -809 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 164 | 630761 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
166 | 630763 | D - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
167 | 630764 | D -810 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 166 | 630763 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
168 | 630765 | D - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
169 | 630766 | D -811 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 168 | 630765 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
170 | 630767 | D - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
171 | 630768 | D -812 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 170 | 630767 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
172 | 630769 | D - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
173 | 630770 | D -813 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 172 | 630769 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
174 | 630771 | D - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 630744 | 31 | 0 | [6 empty] | 0.0000
175 | 630772 | D -814 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 174 | 630771 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
176 | 630773 | D - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
177 | 630774 | D - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
178 | 630775 | D -901 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 177 | 630774 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
179 | 630776 | D - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
180 | 630777 | D -902 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 179 | 630776 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
181 | 630778 | D - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
182 | 630779 | D -903 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 181 | 630778 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
183 | 630780 | D - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
184 | 630781 | D -904 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 183 | 630780 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
185 | 630782 | D - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
186 | 630783 | D -905 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 185 | 630782 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
187 | 630784 | D - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
188 | 630785 | D -906 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 187 | 630784 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
189 | 630786 | D - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
190 | 630787 | D -907 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 189 | 630786 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
191 | 630788 | D - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
192 | 630789 | D -908 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 191 | 630788 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
193 | 630790 | D - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
194 | 630791 | D -909 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 193 | 630790 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
195 | 630792 | D - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
196 | 630793 | D -910 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 195 | 630792 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
197 | 630794 | D - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
198 | 630795 | D -911 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 197 | 630794 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
199 | 630796 | D - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
200 | 630797 | D -912 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 199 | 630796 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
201 | 630798 | D - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
202 | 630799 | D -913 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 201 | 630798 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
203 | 630800 | D - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 630773 | 31 | 0 | [6 empty] | 0.0000
204 | 630801 | D -914 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 203 | 630800 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
205 | 630802 | D - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
206 | 630803 | D - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
207 | 630804 | D -1001 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 206 | 630803 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
208 | 630805 | D - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
209 | 630806 | D -1002 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 208 | 630805 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
210 | 630807 | D - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
211 | 630808 | D -1003 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 210 | 630807 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
212 | 630809 | D - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
213 | 630810 | D -1004 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 212 | 630809 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
214 | 630811 | D - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
215 | 630812 | D -1005 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 214 | 630811 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
216 | 630813 | D - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
217 | 630814 | D -1006 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 216 | 630813 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
218 | 630815 | D - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
219 | 630816 | D -1007 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 218 | 630815 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
220 | 630817 | D - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
221 | 630818 | D -1008 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 220 | 630817 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
222 | 630819 | D - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
223 | 630820 | D -1009 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 222 | 630819 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
224 | 630821 | D - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
225 | 630822 | D -1010 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 224 | 630821 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
226 | 630823 | D - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
227 | 630824 | D -1011 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 226 | 630823 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
228 | 630825 | D - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
229 | 630826 | D -1012 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 228 | 630825 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
230 | 630827 | D - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
231 | 630828 | D -1013 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 230 | 630827 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
232 | 630829 | D - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 630802 | 31 | 0 | [6 empty] | 0.0000
233 | 630830 | D -1014 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 232 | 630829 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
234 | 630831 | D - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
235 | 630832 | D - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
236 | 630833 | D -1101 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 235 | 630832 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
237 | 630834 | D - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
238 | 630835 | D -1102 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 237 | 630834 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
239 | 630836 | D - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
240 | 630837 | D -1103 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 239 | 630836 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
241 | 630838 | D - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
242 | 630839 | D -1104 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 241 | 630838 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
243 | 630840 | D - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
244 | 630841 | D -1105 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 243 | 630840 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
245 | 630842 | D - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
246 | 630843 | D -1106 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 245 | 630842 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
247 | 630844 | D - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
248 | 630845 | D -1107 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 247 | 630844 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
249 | 630846 | D - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
250 | 630847 | D -1108 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 249 | 630846 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
251 | 630848 | D - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
252 | 630849 | D -1109 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 251 | 630848 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
253 | 630850 | D - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
254 | 630851 | D -1110 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 253 | 630850 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
255 | 630852 | D - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
256 | 630853 | D -1111 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 255 | 630852 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
257 | 630854 | D - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
258 | 630855 | D -1112 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 257 | 630854 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
259 | 630856 | D - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
260 | 630857 | D -1113 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 259 | 630856 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
261 | 630858 | D - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 630831 | 31 | 0 | [6 empty] | 0.0000
262 | 630859 | D -1114 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 261 | 630858 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
263 | 630860 | D - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
264 | 630861 | D - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
265 | 630862 | D -1201 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 264 | 630861 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
266 | 630863 | D - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
267 | 630864 | D -1202 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 266 | 630863 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
268 | 630865 | D - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
269 | 630866 | D -1203 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 268 | 630865 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
270 | 630867 | D - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
271 | 630868 | D -1204 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 270 | 630867 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
272 | 630869 | D - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
273 | 630870 | D -1205 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 272 | 630869 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
274 | 630871 | D - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
275 | 630872 | D -1206 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 274 | 630871 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
276 | 630873 | D - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
277 | 630874 | D -1207 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 276 | 630873 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
278 | 630875 | D - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
279 | 630876 | D -1208 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 278 | 630875 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
280 | 630877 | D - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
281 | 630878 | D -1209 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 280 | 630877 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
282 | 630879 | D - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
283 | 630880 | D -1210 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 282 | 630879 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
284 | 630881 | D - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
285 | 630882 | D -1211 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 284 | 630881 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
286 | 630883 | D - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
287 | 630884 | D -1212 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 286 | 630883 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
288 | 630885 | D - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
289 | 630886 | D -1213 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 288 | 630885 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
290 | 630887 | D - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 630860 | 31 | 0 | [6 empty] | 0.0000
291 | 630888 | D -1214 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 290 | 630887 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
292 | 630889 | D - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
293 | 630890 | D - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
294 | 630891 | D -1301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 293 | 630890 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
295 | 630892 | D - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
296 | 630893 | D -1302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 295 | 630892 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
297 | 630894 | D - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
298 | 630895 | D -1303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 297 | 630894 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
299 | 630896 | D - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
300 | 630897 | D -1304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 299 | 630896 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
301 | 630898 | D - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
302 | 630899 | D -1305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 301 | 630898 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
303 | 630900 | D - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
304 | 630901 | D -1306 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 303 | 630900 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
305 | 630902 | D - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
306 | 630903 | D -1307 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 305 | 630902 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
307 | 630904 | D - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
308 | 630905 | D -1308 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 307 | 630904 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
309 | 630906 | D - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
310 | 630907 | D -1309 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 309 | 630906 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
311 | 630908 | D - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
312 | 630909 | D -1310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 311 | 630908 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
313 | 630910 | D - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
314 | 630911 | D -1311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 313 | 630910 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
315 | 630912 | D - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
316 | 630913 | D -1312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 315 | 630912 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
317 | 630914 | D - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
318 | 630915 | D -1313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 317 | 630914 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
319 | 630916 | D - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 630889 | 31 | 0 | [6 empty] | 0.0000
320 | 630917 | D -1314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 319 | 630916 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
321 | 630918 | D - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 630598 | 31 | 0 | [6 empty] | 0.0000
322 | 630919 | D - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
323 | 630920 | D -1401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 322 | 630919 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
324 | 630921 | D - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
325 | 630922 | D -1402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 324 | 630921 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
326 | 630923 | D - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
327 | 630924 | D -1403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 326 | 630923 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
328 | 630925 | D - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
329 | 630926 | D -1404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 328 | 630925 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
330 | 630927 | D - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
331 | 630928 | D -1405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 330 | 630927 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
332 | 630929 | D - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
333 | 630930 | D -1406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 332 | 630929 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
334 | 630931 | D - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
335 | 630932 | D -1407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 334 | 630931 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
336 | 630933 | D - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
337 | 630934 | D -1408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 336 | 630933 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
338 | 630935 | D - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
339 | 630936 | D -1409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 338 | 630935 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
340 | 630937 | D - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
341 | 630938 | D -1410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 340 | 630937 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
342 | 630939 | D - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
343 | 630940 | D -1411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 342 | 630939 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
344 | 630941 | D - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
345 | 630942 | D -1412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 344 | 630941 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
346 | 630943 | D - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
347 | 630944 | D -1413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 346 | 630943 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
348 | 630945 | D - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 630918 | 31 | 0 | [6 empty] | 0.0000
349 | 630946 | D -1414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 348 | 630945 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000