## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 631296 | D - Kitchen Otta | NA | 0.0000 | 0.0000 | 0 | 628785 | 31 | 0 | [6 empty] | 0.0000
2 | 631297 | D - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
3 | 631298 | D - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
4 | 631299 | D -301 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 3 | 631298 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
5 | 631300 | D - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
6 | 631301 | D -302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 5 | 631300 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
7 | 631302 | D - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
8 | 631303 | D -303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 7 | 631302 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
9 | 631304 | D - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
10 | 631305 | D -304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 9 | 631304 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
11 | 631306 | D - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
12 | 631307 | D -305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 11 | 631306 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
13 | 631308 | D - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
14 | 631309 | D -306 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 13 | 631308 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
15 | 631310 | D - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
16 | 631311 | D -307 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 15 | 631310 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
17 | 631312 | D - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
18 | 631313 | D -308 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 17 | 631312 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
19 | 631314 | D - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
20 | 631315 | D -309 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 19 | 631314 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
21 | 631316 | D - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
22 | 631317 | D -310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 21 | 631316 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
23 | 631318 | D - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
24 | 631319 | D -311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 23 | 631318 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
25 | 631320 | D - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
26 | 631321 | D -312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 25 | 631320 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
27 | 631322 | D - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
28 | 631323 | D -313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 27 | 631322 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
29 | 631324 | D - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 631297 | 31 | 0 | [6 empty] | 0.0000
30 | 631325 | D -314 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 29 | 631324 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
31 | 631326 | D - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
32 | 631327 | D - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
33 | 631328 | D -401 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 32 | 631327 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
34 | 631329 | D - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
35 | 631330 | D -402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 34 | 631329 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
36 | 631331 | D - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
37 | 631332 | D -403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 36 | 631331 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
38 | 631333 | D - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
39 | 631334 | D -404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 38 | 631333 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
40 | 631335 | D - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
41 | 631336 | D -405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 40 | 631335 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
42 | 631337 | D - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
43 | 631338 | D -406 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 42 | 631337 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
44 | 631339 | D - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
45 | 631340 | D -407 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 44 | 631339 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
46 | 631341 | D - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
47 | 631342 | D -408 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 46 | 631341 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
48 | 631343 | D - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
49 | 631344 | D -409 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 48 | 631343 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
50 | 631345 | D - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
51 | 631346 | D -410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 50 | 631345 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
52 | 631347 | D - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
53 | 631348 | D -411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 52 | 631347 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
54 | 631349 | D - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
55 | 631350 | D -412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 54 | 631349 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
56 | 631351 | D - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
57 | 631352 | D -413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 56 | 631351 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
58 | 631353 | D - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 631326 | 31 | 0 | [6 empty] | 0.0000
59 | 631354 | D -414 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 58 | 631353 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
60 | 631355 | D - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
61 | 631356 | D - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
62 | 631357 | D -501 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 61 | 631356 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
63 | 631358 | D - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
64 | 631359 | D -502 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 63 | 631358 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
65 | 631360 | D - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
66 | 631361 | D -503 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 65 | 631360 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
67 | 631362 | D - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
68 | 631363 | D -504 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 67 | 631362 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
69 | 631364 | D - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
70 | 631365 | D -505 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 69 | 631364 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
71 | 631366 | D - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
72 | 631367 | D -506 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 71 | 631366 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
73 | 631368 | D - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
74 | 631369 | D -507 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 73 | 631368 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
75 | 631370 | D - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
76 | 631371 | D -508 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 75 | 631370 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
77 | 631372 | D - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
78 | 631373 | D -509 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 77 | 631372 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
79 | 631374 | D - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
80 | 631375 | D -510 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 79 | 631374 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
81 | 631376 | D - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
82 | 631377 | D -511 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 81 | 631376 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
83 | 631378 | D - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
84 | 631379 | D -512 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 83 | 631378 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
85 | 631380 | D - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
86 | 631381 | D -513 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 85 | 631380 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
87 | 631382 | D - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 631355 | 31 | 0 | [6 empty] | 0.0000
88 | 631383 | D -514 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 87 | 631382 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
89 | 631384 | D - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
90 | 631385 | D - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
91 | 631386 | D -601 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 90 | 631385 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
92 | 631387 | D - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
93 | 631388 | D -602 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 92 | 631387 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
94 | 631389 | D - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
95 | 631390 | D -603 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 94 | 631389 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
96 | 631391 | D - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
97 | 631392 | D -604 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 96 | 631391 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
98 | 631393 | D - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
99 | 631394 | D -605 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 98 | 631393 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
100 | 631395 | D - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
101 | 631396 | D -606 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 100 | 631395 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
102 | 631397 | D - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
103 | 631398 | D -607 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 102 | 631397 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
104 | 631399 | D - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
105 | 631400 | D -608 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 104 | 631399 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
106 | 631401 | D - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
107 | 631402 | D -609 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 106 | 631401 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
108 | 631403 | D - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
109 | 631404 | D -610 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 108 | 631403 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
110 | 631405 | D - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
111 | 631406 | D -611 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 110 | 631405 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
112 | 631407 | D - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
113 | 631408 | D -612 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 112 | 631407 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
114 | 631409 | D - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
115 | 631410 | D -613 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 114 | 631409 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
116 | 631411 | D - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 631384 | 31 | 0 | [6 empty] | 0.0000
117 | 631412 | D -614 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 116 | 631411 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
118 | 631413 | D - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
119 | 631414 | D - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
120 | 631415 | D -701 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 119 | 631414 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
121 | 631416 | D - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
122 | 631417 | D -702 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 121 | 631416 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
123 | 631418 | D - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
124 | 631419 | D -703 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 123 | 631418 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
125 | 631420 | D - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
126 | 631421 | D -704 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 125 | 631420 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
127 | 631422 | D - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
128 | 631423 | D -705 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 127 | 631422 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
129 | 631424 | D - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
130 | 631425 | D -706 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 129 | 631424 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
131 | 631426 | D - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
132 | 631427 | D -707 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 131 | 631426 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
133 | 631428 | D - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
134 | 631429 | D -708 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 133 | 631428 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
135 | 631430 | D - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
136 | 631431 | D -709 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 135 | 631430 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
137 | 631432 | D - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
138 | 631433 | D -710 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 137 | 631432 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
139 | 631434 | D - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
140 | 631435 | D -711 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 139 | 631434 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
141 | 631436 | D - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
142 | 631437 | D -712 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 141 | 631436 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
143 | 631438 | D - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
144 | 631439 | D -713 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 143 | 631438 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
145 | 631440 | D - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 631413 | 31 | 0 | [6 empty] | 0.0000
146 | 631441 | D -714 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 145 | 631440 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
147 | 631442 | D - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
148 | 631443 | D - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
149 | 631444 | D -801 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 148 | 631443 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
150 | 631445 | D - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
151 | 631446 | D -802 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 150 | 631445 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
152 | 631447 | D - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
153 | 631448 | D -803 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 152 | 631447 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
154 | 631449 | D - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
155 | 631450 | D -804 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 154 | 631449 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
156 | 631451 | D - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
157 | 631452 | D -805 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 156 | 631451 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
158 | 631453 | D - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
159 | 631454 | D -806 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 158 | 631453 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
160 | 631455 | D - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
161 | 631456 | D -807 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 160 | 631455 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
162 | 631457 | D - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
163 | 631458 | D -808 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 162 | 631457 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
164 | 631459 | D - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
165 | 631460 | D -809 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 164 | 631459 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
166 | 631461 | D - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
167 | 631462 | D -810 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 166 | 631461 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
168 | 631463 | D - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
169 | 631464 | D -811 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 168 | 631463 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
170 | 631465 | D - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
171 | 631466 | D -812 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 170 | 631465 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
172 | 631467 | D - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
173 | 631468 | D -813 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 172 | 631467 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
174 | 631469 | D - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 631442 | 31 | 0 | [6 empty] | 0.0000
175 | 631470 | D -814 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 174 | 631469 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
176 | 631471 | D - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
177 | 631472 | D - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
178 | 631473 | D -901 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 177 | 631472 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
179 | 631474 | D - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
180 | 631475 | D -902 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 179 | 631474 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
181 | 631476 | D - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
182 | 631477 | D -903 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 181 | 631476 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
183 | 631478 | D - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
184 | 631479 | D -904 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 183 | 631478 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
185 | 631480 | D - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
186 | 631481 | D -905 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 185 | 631480 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
187 | 631482 | D - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
188 | 631483 | D -906 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 187 | 631482 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
189 | 631484 | D - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
190 | 631485 | D -907 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 189 | 631484 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
191 | 631486 | D - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
192 | 631487 | D -908 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 191 | 631486 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
193 | 631488 | D - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
194 | 631489 | D -909 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 193 | 631488 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
195 | 631490 | D - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
196 | 631491 | D -910 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 195 | 631490 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
197 | 631492 | D - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
198 | 631493 | D -911 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 197 | 631492 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
199 | 631494 | D - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
200 | 631495 | D -912 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 199 | 631494 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
201 | 631496 | D - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
202 | 631497 | D -913 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 201 | 631496 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
203 | 631498 | D - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 631471 | 31 | 0 | [6 empty] | 0.0000
204 | 631499 | D -914 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 203 | 631498 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
205 | 631500 | D - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
206 | 631501 | D - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
207 | 631502 | D -1001 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 206 | 631501 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
208 | 631503 | D - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
209 | 631504 | D -1002 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 208 | 631503 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
210 | 631505 | D - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
211 | 631506 | D -1003 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 210 | 631505 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
212 | 631507 | D - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
213 | 631508 | D -1004 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 212 | 631507 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
214 | 631509 | D - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
215 | 631510 | D -1005 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 214 | 631509 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
216 | 631511 | D - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
217 | 631512 | D -1006 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 216 | 631511 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
218 | 631513 | D - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
219 | 631514 | D -1007 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 218 | 631513 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
220 | 631515 | D - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
221 | 631516 | D -1008 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 220 | 631515 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
222 | 631517 | D - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
223 | 631518 | D -1009 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 222 | 631517 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
224 | 631519 | D - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
225 | 631520 | D -1010 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 224 | 631519 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
226 | 631521 | D - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
227 | 631522 | D -1011 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 226 | 631521 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
228 | 631523 | D - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
229 | 631524 | D -1012 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 228 | 631523 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
230 | 631525 | D - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
231 | 631526 | D -1013 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 230 | 631525 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
232 | 631527 | D - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 631500 | 31 | 0 | [6 empty] | 0.0000
233 | 631528 | D -1014 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 232 | 631527 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
234 | 631529 | D - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
235 | 631530 | D - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
236 | 631531 | D -1101 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 235 | 631530 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
237 | 631532 | D - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
238 | 631533 | D -1102 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 237 | 631532 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
239 | 631534 | D - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
240 | 631535 | D -1103 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 239 | 631534 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
241 | 631536 | D - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
242 | 631537 | D -1104 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 241 | 631536 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
243 | 631538 | D - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
244 | 631539 | D -1105 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 243 | 631538 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
245 | 631540 | D - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
246 | 631541 | D -1106 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 245 | 631540 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
247 | 631542 | D - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
248 | 631543 | D -1107 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 247 | 631542 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
249 | 631544 | D - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
250 | 631545 | D -1108 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 249 | 631544 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
251 | 631546 | D - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
252 | 631547 | D -1109 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 251 | 631546 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
253 | 631548 | D - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
254 | 631549 | D -1110 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 253 | 631548 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
255 | 631550 | D - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
256 | 631551 | D -1111 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 255 | 631550 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
257 | 631552 | D - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
258 | 631553 | D -1112 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 257 | 631552 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
259 | 631554 | D - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
260 | 631555 | D -1113 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 259 | 631554 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
261 | 631556 | D - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 631529 | 31 | 0 | [6 empty] | 0.0000
262 | 631557 | D -1114 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 261 | 631556 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
263 | 631558 | D - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
264 | 631559 | D - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
265 | 631560 | D -1201 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 264 | 631559 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
266 | 631561 | D - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
267 | 631562 | D -1202 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 266 | 631561 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
268 | 631563 | D - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
269 | 631564 | D -1203 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 268 | 631563 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
270 | 631565 | D - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
271 | 631566 | D -1204 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 270 | 631565 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
272 | 631567 | D - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
273 | 631568 | D -1205 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 272 | 631567 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
274 | 631569 | D - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
275 | 631570 | D -1206 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 274 | 631569 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
276 | 631571 | D - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
277 | 631572 | D -1207 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 276 | 631571 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
278 | 631573 | D - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
279 | 631574 | D -1208 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 278 | 631573 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
280 | 631575 | D - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
281 | 631576 | D -1209 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 280 | 631575 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
282 | 631577 | D - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
283 | 631578 | D -1210 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 282 | 631577 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
284 | 631579 | D - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
285 | 631580 | D -1211 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 284 | 631579 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
286 | 631581 | D - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
287 | 631582 | D -1212 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 286 | 631581 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
288 | 631583 | D - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
289 | 631584 | D -1213 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 288 | 631583 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
290 | 631585 | D - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 631558 | 31 | 0 | [6 empty] | 0.0000
291 | 631586 | D -1214 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 290 | 631585 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
292 | 631587 | D - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
293 | 631588 | D - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
294 | 631589 | D -1301 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 293 | 631588 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
295 | 631590 | D - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
296 | 631591 | D -1302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 295 | 631590 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
297 | 631592 | D - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
298 | 631593 | D -1303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 297 | 631592 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
299 | 631594 | D - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
300 | 631595 | D -1304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 299 | 631594 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
301 | 631596 | D - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
302 | 631597 | D -1305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 301 | 631596 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
303 | 631598 | D - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
304 | 631599 | D -1306 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 303 | 631598 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
305 | 631600 | D - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
306 | 631601 | D -1307 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 305 | 631600 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
307 | 631602 | D - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
308 | 631603 | D -1308 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 307 | 631602 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
309 | 631604 | D - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
310 | 631605 | D -1309 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 309 | 631604 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
311 | 631606 | D - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
312 | 631607 | D -1310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 311 | 631606 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
313 | 631608 | D - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
314 | 631609 | D -1311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 313 | 631608 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
315 | 631610 | D - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
316 | 631611 | D -1312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 315 | 631610 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
317 | 631612 | D - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
318 | 631613 | D -1313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 317 | 631612 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
319 | 631614 | D - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 631587 | 31 | 0 | [6 empty] | 0.0000
320 | 631615 | D -1314 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 319 | 631614 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
321 | 631616 | D - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 631296 | 31 | 0 | [6 empty] | 0.0000
322 | 631617 | D - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
323 | 631618 | D -1401 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 322 | 631617 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
324 | 631619 | D - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
325 | 631620 | D -1402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 324 | 631619 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
326 | 631621 | D - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
327 | 631622 | D -1403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 326 | 631621 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
328 | 631623 | D - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
329 | 631624 | D -1404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 328 | 631623 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
330 | 631625 | D - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
331 | 631626 | D -1405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 330 | 631625 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
332 | 631627 | D - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
333 | 631628 | D -1406 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 332 | 631627 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
334 | 631629 | D - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
335 | 631630 | D -1407 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 334 | 631629 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
336 | 631631 | D - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
337 | 631632 | D -1408 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 336 | 631631 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
338 | 631633 | D - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
339 | 631634 | D -1409 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 338 | 631633 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
340 | 631635 | D - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
341 | 631636 | D -1410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 340 | 631635 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
342 | 631637 | D - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
343 | 631638 | D -1411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 342 | 631637 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
344 | 631639 | D - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
345 | 631640 | D -1412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 344 | 631639 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
346 | 631641 | D - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
347 | 631642 | D -1413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 346 | 631641 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
348 | 631643 | D - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 631616 | 31 | 0 | [6 empty] | 0.0000
349 | 631644 | D -1414 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 348 | 631643 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000