## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work | Selected Group :- D - Umra Patti Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 633817 | E - Umra Patti Work | NA | 0.0000 | 0.0000 | 0 | 632004 | 31 | 0 | [6 empty] | 0.0000
2 | 633818 | E - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
3 | 633819 | E - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
4 | 633820 | E -301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 3 | 633819 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
5 | 633821 | E - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
6 | 633822 | E -302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 5 | 633821 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
7 | 633823 | E - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
8 | 633824 | E -303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 7 | 633823 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
9 | 633825 | E - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
10 | 633826 | E -304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 9 | 633825 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
11 | 633827 | E - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
12 | 633828 | E -305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 11 | 633827 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
13 | 633829 | E - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
14 | 633830 | E -306 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 13 | 633829 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
15 | 633831 | E - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
16 | 633832 | E -307 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 15 | 633831 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
17 | 633833 | E - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
18 | 633834 | E -308 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 17 | 633833 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
19 | 633835 | E - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
20 | 633836 | E -309 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 19 | 633835 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
21 | 633837 | E - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
22 | 633838 | E -310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 21 | 633837 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
23 | 633839 | E - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
24 | 633840 | E -311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 23 | 633839 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
25 | 633841 | E - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
26 | 633842 | E -312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 25 | 633841 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
27 | 633843 | E - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
28 | 633844 | E -313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 27 | 633843 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
29 | 633845 | E - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 633818 | 31 | 0 | [6 empty] | 0.0000
30 | 633846 | E -314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 29 | 633845 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
31 | 633847 | E - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
32 | 633848 | E - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
33 | 633849 | E -401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 32 | 633848 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
34 | 633850 | E - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
35 | 633851 | E -402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 34 | 633850 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
36 | 633852 | E - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
37 | 633853 | E -403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 36 | 633852 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
38 | 633854 | E - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
39 | 633855 | E -404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 38 | 633854 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
40 | 633856 | E - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
41 | 633857 | E -405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 40 | 633856 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
42 | 633858 | E - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
43 | 633859 | E -406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 42 | 633858 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
44 | 633860 | E - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
45 | 633861 | E -407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 44 | 633860 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
46 | 633862 | E - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
47 | 633863 | E -408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 46 | 633862 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
48 | 633864 | E - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
49 | 633865 | E -409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 48 | 633864 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
50 | 633866 | E - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
51 | 633867 | E -410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 50 | 633866 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
52 | 633868 | E - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
53 | 633869 | E -411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 52 | 633868 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
54 | 633870 | E - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
55 | 633871 | E -412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 54 | 633870 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
56 | 633872 | E - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
57 | 633873 | E -413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 56 | 633872 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
58 | 633874 | E - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 633847 | 31 | 0 | [6 empty] | 0.0000
59 | 633875 | E -414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 58 | 633874 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
60 | 633876 | E - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
61 | 633877 | E - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
62 | 633878 | E -501 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 61 | 633877 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
63 | 633879 | E - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
64 | 633880 | E -502 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 63 | 633879 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
65 | 633881 | E - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
66 | 633882 | E -503 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 65 | 633881 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
67 | 633883 | E - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
68 | 633884 | E -504 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 67 | 633883 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
69 | 633885 | E - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
70 | 633886 | E -505 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 69 | 633885 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
71 | 633887 | E - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
72 | 633888 | E -506 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 71 | 633887 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
73 | 633889 | E - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
74 | 633890 | E -507 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 73 | 633889 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
75 | 633891 | E - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
76 | 633892 | E -508 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 75 | 633891 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
77 | 633893 | E - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
78 | 633894 | E -509 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 77 | 633893 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
79 | 633895 | E - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
80 | 633896 | E -510 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 79 | 633895 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
81 | 633897 | E - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
82 | 633898 | E -511 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 81 | 633897 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
83 | 633899 | E - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
84 | 633900 | E -512 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 83 | 633899 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
85 | 633901 | E - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
86 | 633902 | E -513 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 85 | 633901 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
87 | 633903 | E - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 633876 | 31 | 0 | [6 empty] | 0.0000
88 | 633904 | E -514 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 87 | 633903 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
89 | 633905 | E - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
90 | 633906 | E - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
91 | 633907 | E -601 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 90 | 633906 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
92 | 633908 | E - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
93 | 633909 | E -602 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 92 | 633908 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
94 | 633910 | E - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
95 | 633911 | E -603 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 94 | 633910 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
96 | 633912 | E - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
97 | 633913 | E -604 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 96 | 633912 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
98 | 633914 | E - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
99 | 633915 | E -605 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 98 | 633914 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
100 | 633916 | E - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
101 | 633917 | E -606 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 100 | 633916 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
102 | 633918 | E - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
103 | 633919 | E -607 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 102 | 633918 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
104 | 633920 | E - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
105 | 633921 | E -608 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 104 | 633920 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
106 | 633922 | E - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
107 | 633923 | E -609 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 106 | 633922 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
108 | 633924 | E - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
109 | 633925 | E -610 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 108 | 633924 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
110 | 633926 | E - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
111 | 633927 | E -611 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 110 | 633926 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
112 | 633928 | E - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
113 | 633929 | E -612 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 112 | 633928 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
114 | 633930 | E - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
115 | 633931 | E -613 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 114 | 633930 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
116 | 633932 | E - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 633905 | 31 | 0 | [6 empty] | 0.0000
117 | 633933 | E -614 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 116 | 633932 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
118 | 633934 | E - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
119 | 633935 | E - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
120 | 633936 | E -701 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 119 | 633935 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
121 | 633937 | E - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
122 | 633938 | E -702 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 121 | 633937 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
123 | 633939 | E - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
124 | 633940 | E -703 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 123 | 633939 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
125 | 633941 | E - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
126 | 633942 | E -704 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 125 | 633941 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
127 | 633943 | E - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
128 | 633944 | E -705 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 127 | 633943 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
129 | 633945 | E - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
130 | 633946 | E -706 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 129 | 633945 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
131 | 633947 | E - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
132 | 633948 | E -707 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 131 | 633947 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
133 | 633949 | E - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
134 | 633950 | E -708 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 133 | 633949 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
135 | 633951 | E - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
136 | 633952 | E -709 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 135 | 633951 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
137 | 633953 | E - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
138 | 633954 | E -710 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 137 | 633953 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
139 | 633955 | E - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
140 | 633956 | E -711 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 139 | 633955 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
141 | 633957 | E - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
142 | 633958 | E -712 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 141 | 633957 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
143 | 633959 | E - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
144 | 633960 | E -713 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 143 | 633959 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
145 | 633961 | E - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 633934 | 31 | 0 | [6 empty] | 0.0000
146 | 633962 | E -714 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 145 | 633961 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
147 | 633963 | E - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
148 | 633964 | E - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
149 | 633965 | E -801 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 148 | 633964 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
150 | 633966 | E - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
151 | 633967 | E -802 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 150 | 633966 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
152 | 633968 | E - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
153 | 633969 | E -803 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 152 | 633968 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
154 | 633970 | E - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
155 | 633971 | E -804 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 154 | 633970 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
156 | 633972 | E - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
157 | 633973 | E -805 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 156 | 633972 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
158 | 633974 | E - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
159 | 633975 | E -806 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 158 | 633974 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
160 | 633976 | E - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
161 | 633977 | E -807 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 160 | 633976 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
162 | 633978 | E - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
163 | 633979 | E -808 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 162 | 633978 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
164 | 633980 | E - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
165 | 633981 | E -809 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 164 | 633980 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
166 | 633982 | E - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
167 | 633983 | E -810 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 166 | 633982 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
168 | 633984 | E - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
169 | 633985 | E -811 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 168 | 633984 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
170 | 633986 | E - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
171 | 633987 | E -812 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 170 | 633986 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
172 | 633988 | E - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
173 | 633989 | E -813 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 172 | 633988 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
174 | 633990 | E - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 633963 | 31 | 0 | [6 empty] | 0.0000
175 | 633991 | E -814 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 174 | 633990 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
176 | 633992 | E - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
177 | 633993 | E - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
178 | 633994 | E -901 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 177 | 633993 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
179 | 633995 | E - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
180 | 633996 | E -902 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 179 | 633995 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
181 | 633997 | E - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
182 | 633998 | E -903 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 181 | 633997 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
183 | 633999 | E - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
184 | 634000 | E -904 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 183 | 633999 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
185 | 634001 | E - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
186 | 634002 | E -905 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 185 | 634001 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
187 | 634003 | E - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
188 | 634004 | E -906 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 187 | 634003 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
189 | 634005 | E - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
190 | 634006 | E -907 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 189 | 634005 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
191 | 634007 | E - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
192 | 634008 | E -908 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 191 | 634007 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
193 | 634009 | E - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
194 | 634010 | E -909 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 193 | 634009 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
195 | 634011 | E - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
196 | 634012 | E -910 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 195 | 634011 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
197 | 634013 | E - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
198 | 634014 | E -911 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 197 | 634013 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
199 | 634015 | E - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
200 | 634016 | E -912 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 199 | 634015 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
201 | 634017 | E - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
202 | 634018 | E -913 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 201 | 634017 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
203 | 634019 | E - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 633992 | 31 | 0 | [6 empty] | 0.0000
204 | 634020 | E -914 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 203 | 634019 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
205 | 634021 | E - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
206 | 634022 | E - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
207 | 634023 | E -1001 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 206 | 634022 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
208 | 634024 | E - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
209 | 634025 | E -1002 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 208 | 634024 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
210 | 634026 | E - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
211 | 634027 | E -1003 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 210 | 634026 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
212 | 634028 | E - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
213 | 634029 | E -1004 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 212 | 634028 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
214 | 634030 | E - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
215 | 634031 | E -1005 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 214 | 634030 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
216 | 634032 | E - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
217 | 634033 | E -1006 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 216 | 634032 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
218 | 634034 | E - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
219 | 634035 | E -1007 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 218 | 634034 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
220 | 634036 | E - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
221 | 634037 | E -1008 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 220 | 634036 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
222 | 634038 | E - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
223 | 634039 | E -1009 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 222 | 634038 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
224 | 634040 | E - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
225 | 634041 | E -1010 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 224 | 634040 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
226 | 634042 | E - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
227 | 634043 | E -1011 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 226 | 634042 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
228 | 634044 | E - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
229 | 634045 | E -1012 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 228 | 634044 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
230 | 634046 | E - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
231 | 634047 | E -1013 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 230 | 634046 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
232 | 634048 | E - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 634021 | 31 | 0 | [6 empty] | 0.0000
233 | 634049 | E -1014 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 232 | 634048 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
234 | 634050 | E - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
235 | 634051 | E - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
236 | 634052 | E -1101 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 235 | 634051 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
237 | 634053 | E - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
238 | 634054 | E -1102 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 237 | 634053 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
239 | 634055 | E - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
240 | 634056 | E -1103 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 239 | 634055 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
241 | 634057 | E - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
242 | 634058 | E -1104 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 241 | 634057 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
243 | 634059 | E - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
244 | 634060 | E -1105 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 243 | 634059 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
245 | 634061 | E - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
246 | 634062 | E -1106 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 245 | 634061 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
247 | 634063 | E - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
248 | 634064 | E -1107 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 247 | 634063 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
249 | 634065 | E - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
250 | 634066 | E -1108 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 249 | 634065 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
251 | 634067 | E - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
252 | 634068 | E -1109 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 251 | 634067 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
253 | 634069 | E - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
254 | 634070 | E -1110 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 253 | 634069 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
255 | 634071 | E - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
256 | 634072 | E -1111 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 255 | 634071 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
257 | 634073 | E - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
258 | 634074 | E -1112 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 257 | 634073 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
259 | 634075 | E - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
260 | 634076 | E -1113 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 259 | 634075 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
261 | 634077 | E - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 634050 | 31 | 0 | [6 empty] | 0.0000
262 | 634078 | E -1114 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 261 | 634077 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
263 | 634079 | E - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
264 | 634080 | E - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
265 | 634081 | E -1201 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 264 | 634080 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
266 | 634082 | E - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
267 | 634083 | E -1202 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 266 | 634082 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
268 | 634084 | E - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
269 | 634085 | E -1203 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 268 | 634084 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
270 | 634086 | E - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
271 | 634087 | E -1204 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 270 | 634086 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
272 | 634088 | E - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
273 | 634089 | E -1205 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 272 | 634088 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
274 | 634090 | E - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
275 | 634091 | E -1206 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 274 | 634090 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
276 | 634092 | E - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
277 | 634093 | E -1207 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 276 | 634092 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
278 | 634094 | E - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
279 | 634095 | E -1208 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 278 | 634094 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
280 | 634096 | E - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
281 | 634097 | E -1209 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 280 | 634096 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
282 | 634098 | E - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
283 | 634099 | E -1210 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 282 | 634098 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
284 | 634100 | E - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
285 | 634101 | E -1211 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 284 | 634100 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
286 | 634102 | E - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
287 | 634103 | E -1212 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 286 | 634102 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
288 | 634104 | E - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
289 | 634105 | E -1213 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 288 | 634104 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
290 | 634106 | E - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 634079 | 31 | 0 | [6 empty] | 0.0000
291 | 634107 | E -1214 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 290 | 634106 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
292 | 634108 | E - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
293 | 634109 | E - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
294 | 634110 | E -1301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 293 | 634109 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
295 | 634111 | E - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
296 | 634112 | E -1302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 295 | 634111 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
297 | 634113 | E - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
298 | 634114 | E -1303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 297 | 634113 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
299 | 634115 | E - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
300 | 634116 | E -1304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 299 | 634115 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
301 | 634117 | E - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
302 | 634118 | E -1305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 301 | 634117 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
303 | 634119 | E - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
304 | 634120 | E -1306 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 303 | 634119 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
305 | 634121 | E - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
306 | 634122 | E -1307 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 305 | 634121 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
307 | 634123 | E - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
308 | 634124 | E -1308 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 307 | 634123 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
309 | 634125 | E - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
310 | 634126 | E -1309 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 309 | 634125 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
311 | 634127 | E - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
312 | 634128 | E -1310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 311 | 634127 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
313 | 634129 | E - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
314 | 634130 | E -1311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 313 | 634129 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
315 | 634131 | E - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
316 | 634132 | E -1312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 315 | 634131 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
317 | 634133 | E - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
318 | 634134 | E -1313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 317 | 634133 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
319 | 634135 | E - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 634108 | 31 | 0 | [6 empty] | 0.0000
320 | 634136 | E -1314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 319 | 634135 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
321 | 634137 | E - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 633817 | 31 | 0 | [6 empty] | 0.0000
322 | 634138 | E - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
323 | 634139 | E -1401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 322 | 634138 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
324 | 634140 | E - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
325 | 634141 | E -1402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 324 | 634140 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
326 | 634142 | E - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
327 | 634143 | E -1403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 326 | 634142 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
328 | 634144 | E - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
329 | 634145 | E -1404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 328 | 634144 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
330 | 634146 | E - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
331 | 634147 | E -1405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 330 | 634146 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
332 | 634148 | E - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
333 | 634149 | E -1406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 332 | 634148 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
334 | 634150 | E - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
335 | 634151 | E -1407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 334 | 634150 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
336 | 634152 | E - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
337 | 634153 | E -1408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 336 | 634152 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
338 | 634154 | E - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
339 | 634155 | E -1409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 338 | 634154 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
340 | 634156 | E - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
341 | 634157 | E -1410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 340 | 634156 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
342 | 634158 | E - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
343 | 634159 | E -1411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 342 | 634158 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
344 | 634160 | E - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
345 | 634161 | E -1412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 344 | 634160 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
346 | 634162 | E - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
347 | 634163 | E -1413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 346 | 634162 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
348 | 634164 | E - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 634137 | 31 | 0 | [6 empty] | 0.0000
349 | 634165 | E -1414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 348 | 634164 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000