## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work | Selected Group :- D Internal Finishing Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 664836 | D Internal Finishing Work | NA | 0.0000 | 0.0000 | 0 | 556887 | 31 | 0 | [6 empty] | 0.0000
2 | 664837 | Waterproofing | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
3 | 664849 | D-Bldg Internal Flat Waterproofing Work | No. | 1.0000 | 1.0000 | 2 | 664837 | 4 | 34541 | A-Bldg Internal Flat Waterproofing Work | [5 empty] | 0.0000
4 | 664838 | Plumbing Work | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
5 | 664850 | D-Bldg Internal Flat Plumbing Work | No. | 1.0000 | 1.0000 | 4 | 664838 | 4 | 34542 | A-Bldg Internal Flat Plumbing Work | [5 empty] | 0.0000
6 | 664839 | Door & Windows | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
7 | 664851 | D-Bldg Internal Flat Door & Windows Work | No. | 1.0000 | 1.0000 | 6 | 664839 | 4 | 34543 | A-Bldg Internal Flat Door & Windows Work | [5 empty] | 0.0000
8 | 664840 | Folding Door | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
9 | 664852 | D-Bldg Internal Flat Folding Door Work | No. | 1.0000 | 1.0000 | 8 | 664840 | 4 | 34544 | A-Bldg Internal Flat Folding Door Work | [5 empty] | 0.0000
10 | 664841 | Window Grill | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
11 | 664853 | D-Bldg Internal Flat Window Grill Work | No. | 1.0000 | 1.0000 | 10 | 664841 | 4 | 34545 | A-Bldg Internal Flat Window Grill Work | [5 empty] | 0.0000
12 | 664842 | Aluminium Window | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
13 | 664854 | D-Bldg Internal Flat Aluminium Window Work | No. | 1.0000 | 1.0000 | 12 | 664842 | 4 | 34546 | A-Bldg Internal Flat Aluminium Window Work | [5 empty] | 0.0000
14 | 664843 | Painting | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
15 | 664855 | D-Bldg Internal Flat Painting Work | No. | 1.0000 | 1.0000 | 14 | 664843 | 4 | 34547 | A-Bldg Internal Flat Painting Work | [5 empty] | 0.0000
16 | 664844 | Flooring & Tiling | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
17 | 664856 | D-Bldg Internal Flat Tiling Work | No. | 1.0000 | 1.0000 | 16 | 664844 | 4 | 34548 | A-Bldg Internal Flat Tiling Work | [5 empty] | 0.0000
18 | 664845 | Electrical Work | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
19 | 664857 | D-Bldg Internal Flat Electrical Work | No. | 1.0000 | 1.0000 | 18 | 664845 | 4 | 34549 | A-Bldg Internal Flat Electrical Work | [5 empty] | 0.0000
20 | 664846 | Fire Fighting | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
21 | 664858 | D-Bldg Internal Flat Fire Fighting Work | No. | 1.0000 | 1.0000 | 20 | 664846 | 4 | 34550 | A-Bldg Internal Flat Fire Fighting Work | [5 empty] | 0.0000
22 | 664847 | Railing Work | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
23 | 664859 | D-Bldg Internal Flat Railing Work | No. | 1.0000 | 1.0000 | 22 | 664847 | 4 | 34551 | A-Bldg Internal Flat Railing Work | [5 empty] | 0.0000
24 | 664848 | Misc. Work | NA | 0.0000 | 0.0000 | 1 | 664836 | 31 | 0 | [6 empty] | 0.0000
25 | 664860 | D-Bldg Internal Flat Misc. Work | No. | 1.0000 | 1.0000 | 24 | 664848 | 4 | 34552 | A-Bldg Internal Flat Misc. Work | [5 empty] | 0.0000