## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work | Selected Group :- Wing-2 Refuge Area Waterproofing Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 610614 | Wing-2 Refuge Area Waterproofing Work | NA | 0.0000 | 0.0000 | 0 | 604370 | 31 | 0 | [6 empty] | 0.0000
2 | 610615 | Wing-2 103 Refuge Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 610614 | 31 | 0 | [6 empty] | 0.0000
3 | 610616 | Wing-2 103 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.6600 | 506.6600 | 2 | 610615 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
4 | 610617 | Wing-2 103 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.5200 | 30.5200 | 2 | 610615 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
5 | 610618 | Wing-2 103 Flat C. Toilet IPS W/P | Sq.Ft | 30.5200 | 30.5200 | 2 | 610615 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
6 | 610619 | Wing-2 103 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 2 | 610615 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
7 | 610620 | Wing-2 103 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 2 | 610615 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
8 | 610621 | Wing-2 103 Flat Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 2 | 610615 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
9 | 610622 | Wing-2 103 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 2 | 610615 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
10 | 610623 | Wing-2 103 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 2 | 610615 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
11 | 610624 | Wing-2 103 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 2 | 610615 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
12 | 610625 | Wing-2 103 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 2 | 610615 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
13 | 610626 | Wing-2 103 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 2 | 610615 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
14 | 610627 | Wing-2 603 Refuge Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 610614 | 31 | 0 | [6 empty] | 0.0000
15 | 610628 | Wing-2 603 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.6600 | 506.6600 | 14 | 610627 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
16 | 610629 | Wing-2 603 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.5200 | 30.5200 | 14 | 610627 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
17 | 610630 | Wing-2 603 Flat C. Toilet IPS W/P | Sq.Ft | 30.5200 | 30.5200 | 14 | 610627 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
18 | 610631 | Wing-2 603 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 14 | 610627 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
19 | 610632 | Wing-2 603 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 14 | 610627 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
20 | 610633 | Wing-2 603 Flat Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 14 | 610627 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
21 | 610634 | Wing-2 603 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 14 | 610627 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
22 | 610635 | Wing-2 603 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 14 | 610627 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
23 | 610636 | Wing-2 603 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 14 | 610627 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
24 | 610637 | Wing-2 603 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 14 | 610627 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
25 | 610638 | Wing-2 603 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 14 | 610627 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
26 | 610639 | Wing-2 1103 Refuge Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 610614 | 31 | 0 | [6 empty] | 0.0000
27 | 610640 | Wing-2 1103 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.6600 | 506.6600 | 26 | 610639 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
28 | 610641 | Wing-2 1103 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.5200 | 30.5200 | 26 | 610639 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
29 | 610642 | Wing-2 1103 Flat C. Toilet IPS W/P | Sq.Ft | 30.5200 | 30.5200 | 26 | 610639 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
30 | 610643 | Wing-2 1103 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 26 | 610639 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
31 | 610644 | Wing-2 1103 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 26 | 610639 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
32 | 610645 | Wing-2 1103 Flat Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 26 | 610639 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
33 | 610646 | Wing-2 1103 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 26 | 610639 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
34 | 610647 | Wing-2 1103 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 26 | 610639 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
35 | 610648 | Wing-2 1103 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 26 | 610639 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
36 | 610649 | Wing-2 1103 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 26 | 610639 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
37 | 610650 | Wing-2 1103 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 26 | 610639 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
38 | 610651 | Wing-2 1603 Refuge Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 610614 | 31 | 0 | [6 empty] | 0.0000
39 | 610652 | Wing-2 1603 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.6600 | 506.6600 | 38 | 610651 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
40 | 610653 | Wing-2 1603 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.5200 | 30.5200 | 38 | 610651 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
41 | 610654 | Wing-2 1603 Flat C. Toilet IPS W/P | Sq.Ft | 30.5200 | 30.5200 | 38 | 610651 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
42 | 610655 | Wing-2 1603 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 38 | 610651 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
43 | 610656 | Wing-2 1603 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 38 | 610651 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
44 | 610657 | Wing-2 1603 Flat Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 38 | 610651 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
45 | 610658 | Wing-2 1603 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 38 | 610651 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
46 | 610659 | Wing-2 1603 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 38 | 610651 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
47 | 610660 | Wing-2 1603 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 38 | 610651 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
48 | 610661 | Wing-2 1603 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 38 | 610651 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
49 | 610662 | Wing-2 1603 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 38 | 610651 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
50 | 610663 | Wing-2 2103 Refuge Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 610614 | 31 | 0 | [6 empty] | 0.0000
51 | 610664 | Wing-2 2103 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.6600 | 506.6600 | 50 | 610663 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
52 | 610665 | Wing-2 2103 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.5200 | 30.5200 | 50 | 610663 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
53 | 610666 | Wing-2 2103 Flat C. Toilet IPS W/P | Sq.Ft | 30.5200 | 30.5200 | 50 | 610663 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
54 | 610667 | Wing-2 2103 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 50 | 610663 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
55 | 610668 | Wing-2 2103 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 50 | 610663 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
56 | 610669 | Wing-2 2103 Flat Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 50 | 610663 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
57 | 610670 | Wing-2 2103 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 50 | 610663 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
58 | 610671 | Wing-2 2103 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 50 | 610663 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
59 | 610672 | Wing-2 2103 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 50 | 610663 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
60 | 610673 | Wing-2 2103 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 50 | 610663 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
61 | 610674 | Wing-2 2103 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 50 | 610663 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
62 | 610675 | Wing-2 2603 Refuge Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 610614 | 31 | 0 | [6 empty] | 0.0000
63 | 610676 | Wing-2 2603 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.6600 | 506.6600 | 62 | 610675 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
64 | 610677 | Wing-2 2603 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.5200 | 30.5200 | 62 | 610675 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
65 | 610678 | Wing-2 2603 Flat C. Toilet IPS W/P | Sq.Ft | 30.5200 | 30.5200 | 62 | 610675 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
66 | 610679 | Wing-2 2603 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 62 | 610675 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
67 | 610680 | Wing-2 2603 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 62 | 610675 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
68 | 610681 | Wing-2 2603 Flat Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 62 | 610675 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
69 | 610682 | Wing-2 2603 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 62 | 610675 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
70 | 610683 | Wing-2 2603 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 62 | 610675 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
71 | 610684 | Wing-2 2603 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 62 | 610675 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
72 | 610685 | Wing-2 2603 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 62 | 610675 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
73 | 610686 | Wing-2 2603 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 62 | 610675 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000