## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M) | Selected Group :- E - Super Structure RCC Work (M)
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 623251 | E - Super Structure RCC Work (M) | NA | 0.0000 | 0.0000 | 0 | 623155 | 31 | 0 | [6 empty] | 0.0000
2 | 623252 | E - 1st Slab RCC Work (M) | Sq.Ft | 9471.1000 | 14134.9000 | 1 | 623251 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
3 | 623253 | E - 2nd Slab RCC Work (M) | Sq.Ft | 9471.1000 | 14134.9000 | 1 | 623251 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
4 | 623254 | E - 3rd Slab RCC Work (M) | Sq.Ft | 9471.1000 | 14134.9000 | 1 | 623251 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
5 | 623255 | E - 4th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
6 | 623256 | E - 5th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
7 | 623257 | E - 6th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
8 | 623258 | E - 7th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
9 | 623259 | E - 8th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
10 | 623260 | E - 9th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
11 | 623261 | E - 10th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
12 | 623262 | E - 11th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
13 | 623263 | E - 12th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
14 | 623264 | E - 13th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
15 | 623265 | E - 14th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
16 | 623266 | E - 15th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
17 | 623267 | E - 16th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
18 | 623268 | E - 17th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
19 | 623269 | E - 18th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34388 | A - 18th Slab RCC Work (M) | [5 empty] | 0.0000
20 | 623270 | E - 19th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34389 | A - 19th Slab RCC Work (M) | [5 empty] | 0.0000
21 | 623271 | E - 20th Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
22 | 623272 | E - 21st Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
23 | 623273 | E - 22nd Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
24 | 623274 | E - 23rd Slab RCC Work (M) | Sq.Ft | 6272.5000 | 9892.0200 | 1 | 623251 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
25 | 623275 | E - 24th (Terrace) Slab RCC Work (M) | Sq.Ft | 6077.6000 | 9578.7950 | 1 | 623251 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
26 | 623276 | E - LMR & OHWT RCC Work (M) | Sq.Ft | 2330.4000 | 2330.4000 | 1 | 623251 | 4 | 34391 | A - LMR & OHWT RCC Work (M) | [5 empty] | 0.0000
27 | 623277 | E - Super Structure Aluform (M) | Sq.Ft | 35695.2650 | 197631.0000 | 1 | 623251 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000