## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure | Selected Group :- C Super Structure
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 623730 | C Super Structure | NA | 0.0000 | 0.0000 | 0 | 556883 | 31 | 0 | [6 empty] | 0.0000
2 | 623731 | C - Super structure RCC Work (L) | NA | 0.0000 | 0.0000 | 1 | 623730 | 31 | 0 | [6 empty] | 0.0000
3 | 623732 | C - 1st Slab RCC Work (L) | Sq.Ft | 11635.2000 | 11635.2000 | 2 | 623731 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
4 | 623733 | C - 2nd Slab RCC Work (L) | Sq.Ft | 11635.2000 | 11635.2000 | 2 | 623731 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
5 | 623734 | C - 3rd Slab RCC Work (L) | Sq.Ft | 11635.2000 | 11635.2000 | 2 | 623731 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
6 | 623735 | C - 4th Slab RCC Work (L) | Sq.Ft | 8286.2000 | 8286.2000 | 2 | 623731 | 4 | 34378 | A - 4th Slab RCC Work (L) | [5 empty] | 0.0000
7 | 623736 | C - 5th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
8 | 623737 | C - 6th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
9 | 623738 | C - 7th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
10 | 623739 | C - 8th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
11 | 623740 | C - 9th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
12 | 623741 | C - 10th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
13 | 623742 | C - 11th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
14 | 623743 | C - 12th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
15 | 623744 | C - 13th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
16 | 623745 | C - 14th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
17 | 623746 | C - 15th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
18 | 623747 | C - 16th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
19 | 623748 | C - 17th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
20 | 623749 | C - 18th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
21 | 623750 | C - 19th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
22 | 623751 | C - 20th Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
23 | 623752 | C - 21st Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
24 | 623753 | C - 22nd Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
25 | 623754 | C - 23rd Slab RCC Work (L) | Sq.Ft | 8285.7000 | 8285.7000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
26 | 623755 | C - 24th Slab RCC Work (L) | Sq.Ft | 7990.8000 | 7990.8000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
27 | 623756 | C - LMR & OHWT RCC Work (L) | Sq.Ft | 2330.4000 | 2330.4000 | 2 | 623731 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
28 | 623757 | C - Super Structure Aluform Work | Sq.Ft | 46813.7100 | 46813.7100 | 2 | 623731 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000
29 | 623758 | C - Super Structure RCC Work (M) | NA | 0.0000 | 0.0000 | 1 | 623730 | 31 | 0 | [6 empty] | 0.0000
30 | 623759 | C - 1st Slab RCC Work (M) | Sq.Ft | 11635.2000 | 11635.2000 | 29 | 623758 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
31 | 623760 | C - 2nd Slab RCC Work (M) | Sq.Ft | 11635.2000 | 11635.2000 | 29 | 623758 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
32 | 623761 | C - 3rd Slab RCC Work (M) | Sq.Ft | 11635.2000 | 11635.2000 | 29 | 623758 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
33 | 623762 | C - 4th Slab RCC Work (M) | Sq.Ft | 8286.2000 | 8286.2000 | 29 | 623758 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
34 | 623763 | C - 5th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
35 | 623764 | C - 6th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
36 | 623765 | C - 7th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
37 | 623766 | C - 8th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
38 | 623767 | C - 9th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
39 | 623768 | C - 10th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
40 | 623769 | C - 11th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
41 | 623770 | C - 12th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
42 | 623771 | C - 13th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
43 | 623772 | C - 14th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
44 | 623773 | C - 15th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
45 | 623774 | C - 16th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
46 | 623775 | C - 17th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
47 | 623776 | C - 18th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34388 | A - 18th Slab RCC Work (M) | [5 empty] | 0.0000
48 | 623777 | C - 19th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34389 | A - 19th Slab RCC Work (M) | [5 empty] | 0.0000
49 | 623778 | C - 20th Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
50 | 623779 | C - 21st Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
51 | 623780 | C - 22nd Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
52 | 623781 | C - 23rd Slab RCC Work (M) | Sq.Ft | 8285.7000 | 8285.7000 | 29 | 623758 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
53 | 623782 | C - 24th (Terrace) Slab RCC Work (M) | Sq.Ft | 7990.8000 | 7990.8000 | 29 | 623758 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
54 | 623783 | C - LMR & OHWT RCC Work (M) | Sq.Ft | 2330.4000 | 2330.4000 | 29 | 623758 | 4 | 34391 | A - LMR & OHWT RCC Work (M) | [5 empty] | 0.0000
55 | 623784 | C - Super Structure Aluform (M) | Sq.Ft | 46813.7100 | 46813.7100 | 29 | 623758 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000