## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work | Selected Group :- Wing-2 MS Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 398370 | Wing-2 MS Work | NA | 0.0000 | 0.0000 | 0 | 398354 | 31 | 0 | [6 empty] | 0.0000
2 | 651966 | Wing-2 Podium Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
3 | 651967 | Wing-2 Flat No P1 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
4 | 651968 | Wing-2 Flat No P2 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
5 | 651969 | Wing-2 Flat No P3 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
6 | 651970 | Wing-2 Flat No P4 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
7 | 651971 | Wing-2 Flat No P5 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
8 | 651982 | Wing-2 Flat No P6 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
9 | 651983 | Wing-2 Flat No P7 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
10 | 651984 | Wing-2 Flat No P8 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
11 | 651985 | Wing-2 Flat No P9 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 2 | 651966 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
12 | 651986 | Wing-2 1st Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
13 | 651987 | Wing-2 Flat No 101 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
14 | 651988 | Wing-2 Flat No 102 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
15 | 651990 | Wing-2 Flat No 104 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
16 | 651991 | Wing-2 Flat No 105 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
17 | 651992 | Wing-2 Flat No 106 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
18 | 651993 | Wing-2 Flat No 107 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
19 | 651994 | Wing-2 Flat No 108 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
20 | 651995 | Wing-2 Flat No 109 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
21 | 651989 | Wing-2 Flat No 110 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 12 | 651986 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
22 | 652135 | Wing-2 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
23 | 652136 | Wing-2 Flat No 201 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
24 | 652137 | Wing-2 Flat No 202 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
25 | 652145 | Wing.2 Flat No 203 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
26 | 652139 | Wing-2 Flat No 204 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
27 | 652140 | Wing-2 Flat No 205 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
28 | 652141 | Wing-2 Flat No 206 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
29 | 652142 | Wing-2 Flat No 207 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
30 | 652143 | Wing-2 Flat No 208 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
31 | 652144 | Wing-2 Flat No 209 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
32 | 652138 | Wing-2 Flat No 210 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 22 | 652135 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
33 | 652146 | Wing-2 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
34 | 652147 | Wing-2 Flat No 301 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
35 | 652148 | Wing-2 Flat No 302 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
36 | 652156 | Wing.2 Flat No 303 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
37 | 652150 | Wing-2 Flat No 304 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
38 | 652151 | Wing-2 Flat No 305 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
39 | 652152 | Wing-2 Flat No 306 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
40 | 652153 | Wing-2 Flat No 307 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
41 | 652154 | Wing-2 Flat No 308 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
42 | 652155 | Wing-2 Flat No 309 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
43 | 652149 | Wing-2 Flat No 310 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 33 | 652146 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
44 | 652157 | Wing-2 4th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
45 | 652158 | Wing-2 Flat No 401 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
46 | 652159 | Wing-2 Flat No 402 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
47 | 652167 | Wing.2 Flat No 403 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
48 | 652161 | Wing-2 Flat No 404 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
49 | 652162 | Wing-2 Flat No 405 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
50 | 652163 | Wing-2 Flat No 406 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
51 | 652164 | Wing-2 Flat No 407 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
52 | 652165 | Wing-2 Flat No 408 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
53 | 652166 | Wing-2 Flat No 409 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
54 | 652160 | Wing-2 Flat No 410 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 44 | 652157 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
55 | 652168 | Wing-2 5th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
56 | 652169 | Wing-2 Flat No 501 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
57 | 652170 | Wing-2 Flat No 502 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
58 | 652178 | Wing.2 Flat No 503 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
59 | 652172 | Wing-2 Flat No 504 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
60 | 652173 | Wing-2 Flat No 505 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
61 | 652174 | Wing-2 Flat No 506 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
62 | 652175 | Wing-2 Flat No 507 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
63 | 652176 | Wing-2 Flat No 508 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
64 | 652177 | Wing-2 Flat No 509 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
65 | 652171 | Wing-2 Flat No 510 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 55 | 652168 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
66 | 652179 | Wing-2 6th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
67 | 652180 | Wing-2 Flat No 601 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
68 | 652181 | Wing-2 Flat No 602 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
69 | 652183 | Wing-2 Flat No 604 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
70 | 652184 | Wing-2 Flat No 605 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
71 | 652185 | Wing-2 Flat No 606 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
72 | 652186 | Wing-2 Flat No 607 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
73 | 652187 | Wing-2 Flat No 608 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
74 | 652188 | Wing-2 Flat No 609 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
75 | 652182 | Wing-2 Flat No 610 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 66 | 652179 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
76 | 652189 | Wing-2 7th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
77 | 652190 | Wing-2 Flat No 701 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
78 | 652191 | Wing-2 Flat No 702 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
79 | 652199 | Wing.2 Flat No 703 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
80 | 652193 | Wing-2 Flat No 704 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
81 | 652194 | Wing-2 Flat No 705 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
82 | 652195 | Wing-2 Flat No 706 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
83 | 652196 | Wing-2 Flat No 707 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
84 | 652197 | Wing-2 Flat No 708 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
85 | 652198 | Wing-2 Flat No 709 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
86 | 652192 | Wing-2 Flat No 2=710 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 76 | 652189 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
87 | 652200 | Wing-2 8th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
88 | 652201 | Wing-2 Flat No 801 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
89 | 652202 | Wing-2 Flat No 802 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
90 | 652210 | Wing.2 Flat No 803 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
91 | 652204 | Wing-2 Flat No 804 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
92 | 652205 | Wing-2 Flat No 805 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
93 | 652206 | Wing-2 Flat No 806 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
94 | 652207 | Wing-2 Flat No 807 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
95 | 652208 | Wing-2 Flat No 808 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
96 | 652209 | Wing-2 Flat No 809 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
97 | 652203 | Wing-2 Flat No 810 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 87 | 652200 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
98 | 652211 | Wing-2 9th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
99 | 652212 | Wing-2 Flat No 901 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
100 | 652213 | Wing-2 Flat No 902 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
101 | 652221 | Wing.2 Flat No 903 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
102 | 652215 | Wing-2 Flat No 904 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
103 | 652216 | Wing-2 Flat No 905 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
104 | 652217 | Wing-2 Flat No 906 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
105 | 652218 | Wing-2 Flat No 907 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
106 | 652219 | Wing-2 Flat No 908 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
107 | 652220 | Wing-2 Flat No 909 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
108 | 652214 | Wing-2 Flat No 910 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 98 | 652211 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
109 | 652222 | Wing-2 10th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
110 | 652223 | Wing-2 Flat No 1001 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
111 | 652224 | Wing-2 Flat No 1002 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
112 | 652232 | Wing.2 Flat No 1003 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
113 | 652226 | Wing-2 Flat No 1004 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
114 | 652227 | Wing-2 Flat No 1005 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
115 | 652228 | Wing-2 Flat No 1006 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
116 | 652229 | Wing-2 Flat No 1007 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
117 | 652230 | Wing-2 Flat No 1008 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
118 | 652231 | Wing-2 Flat No 1009 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
119 | 652225 | Wing-2 Flat No 1010 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 109 | 652222 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
120 | 652233 | Wing-2 11th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
121 | 652234 | Wing-2 Flat No 1101 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
122 | 652235 | Wing-2 Flat No 1102 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
123 | 652237 | Wing-2 Flat No 1104 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
124 | 652238 | Wing-2 Flat No 1105 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
125 | 652239 | Wing-2 Flat No 1106 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
126 | 652240 | Wing-2 Flat No 1107 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
127 | 652241 | Wing-2 Flat No 1108 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
128 | 652242 | Wing-2 Flat No 1109 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
129 | 652236 | Wing-2 Flat No 1110 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 120 | 652233 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
130 | 652243 | Wing-2 12th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
131 | 652244 | Wing-2 Flat No 1201 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
132 | 652245 | Wing-2 Flat No 1202 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
133 | 652253 | Wing.2 Flat No 1203 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
134 | 652247 | Wing-2 Flat No 1204 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
135 | 652248 | Wing-2 Flat No 1205 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
136 | 652249 | Wing-2 Flat No 1206 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
137 | 652250 | Wing-2 Flat No 1207 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
138 | 652251 | Wing-2 Flat No 1208 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
139 | 652252 | Wing-2 Flat No 1209 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
140 | 652246 | Wing-2 Flat No 1210 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 130 | 652243 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
141 | 652254 | Wing-2 13th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
142 | 652255 | Wing-2 Flat No 1301 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
143 | 652256 | Wing-2 Flat No 1302 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
144 | 652264 | Wing.2 Flat No 1303 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
145 | 652258 | Wing-2 Flat No 1304 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
146 | 652259 | Wing-2 Flat No 1305 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
147 | 652260 | Wing-2 Flat No 1306 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
148 | 652261 | Wing-2 Flat No 1307 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
149 | 652262 | Wing-2 Flat No 1308 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
150 | 652263 | Wing-2 Flat No 1309 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
151 | 652257 | Wing-2 Flat No 1310 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 141 | 652254 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
152 | 652265 | Wing-2 14th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
153 | 652266 | Wing-2 Flat No 1401 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
154 | 652267 | Wing-2 Flat No 1402 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
155 | 652275 | Wing.2 Flat No 1403 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
156 | 652269 | Wing-2 Flat No 1404 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
157 | 652270 | Wing-2 Flat No 1405 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
158 | 652271 | Wing-2 Flat No 1406 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
159 | 652272 | Wing-2 Flat No 1407 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
160 | 652273 | Wing-2 Flat No 1408 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
161 | 652274 | Wing-2 Flat No 1409 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
162 | 652268 | Wing-2 Flat No 1410 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 152 | 652265 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
163 | 652276 | Wing-2 15th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
164 | 652277 | Wing-2 Flat No 1501 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
165 | 652278 | Wing-2 Flat No 1502 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
166 | 652286 | Wing.2 Flat No 1503 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
167 | 652280 | Wing-2 Flat No 1504 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
168 | 652281 | Wing-2 Flat No 1505 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
169 | 652282 | Wing-2 Flat No 1506 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
170 | 652283 | Wing-2 Flat No 1507 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
171 | 652284 | Wing-2 Flat No 1508 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
172 | 652285 | Wing-2 Flat No 1509 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
173 | 652279 | Wing-2 Flat No 1510 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 163 | 652276 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
174 | 652287 | Wing-2 16th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
175 | 652288 | Wing-2 Flat No 1601 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
176 | 652289 | Wing-2 Flat No 1602 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
177 | 652291 | Wing-2 Flat No 1604 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
178 | 652292 | Wing-2 Flat No 1605 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
179 | 652293 | Wing-2 Flat No 1606 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
180 | 652294 | Wing-2 Flat No 1607 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
181 | 652295 | Wing-2 Flat No 1608 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
182 | 652296 | Wing-2 Flat No 1609 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
183 | 652290 | Wing-2 Flat No 1610 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 174 | 652287 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
184 | 652297 | Wing-2 17th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
185 | 652298 | Wing-2 Flat No 1701 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
186 | 652299 | Wing-2 Flat No 1702 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
187 | 652307 | Wing.2 Flat No 1703 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
188 | 652301 | Wing-2 Flat No 1704 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
189 | 652302 | Wing-2 Flat No 1705 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
190 | 652303 | Wing-2 Flat No 1706 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
191 | 652304 | Wing-2 Flat No 1707 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
192 | 652305 | Wing-2 Flat No 1708 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
193 | 652306 | Wing-2 Flat No 1709 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
194 | 652300 | Wing-2 Flat No 1710 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 184 | 652297 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
195 | 652308 | Wing-2 18th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
196 | 652309 | Wing-2 Flat No 1801 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
197 | 652310 | Wing-2 Flat No 1802 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
198 | 652318 | Wing.2 Flat No 1803 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
199 | 652312 | Wing-2 Flat No 1804 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
200 | 652313 | Wing-2 Flat No 1805 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
201 | 652314 | Wing-2 Flat No 1806 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
202 | 652315 | Wing-2 Flat No 1807 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
203 | 652316 | Wing-2 Flat No 1808 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
204 | 652317 | Wing-2 Flat No 1809 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
205 | 652311 | Wing-2 Flat No 1810 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 195 | 652308 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
206 | 652319 | Wing-2 19th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
207 | 652320 | Wing-2 Flat No 1901 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
208 | 652321 | Wing-2 Flat No 1902 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
209 | 652329 | Wing.2 Flat No 1903 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
210 | 652323 | Wing-2 Flat No 1904 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
211 | 652324 | Wing-2 Flat No 1905 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
212 | 652325 | Wing-2 Flat No 1906 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
213 | 652326 | Wing-2 Flat No 1907 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
214 | 652327 | Wing-2 Flat No 1908 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
215 | 652328 | Wing-2 Flat No 1909 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
216 | 652322 | Wing-2 Flat No 1910 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 206 | 652319 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
217 | 652330 | Wing-2 20th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
218 | 652331 | Wing-2 Flat No 2001 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
219 | 652332 | Wing-2 Flat No 2002 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
220 | 652340 | Wing.2 Flat No 2003 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
221 | 652334 | Wing-2 Flat No 2004 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
222 | 652335 | Wing-2 Flat No 2005 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
223 | 652336 | Wing-2 Flat No 2006 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
224 | 652337 | Wing-2 Flat No 2007 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
225 | 652338 | Wing-2 Flat No 2008 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
226 | 652339 | Wing-2 Flat No 2009 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
227 | 652333 | Wing-2 Flat No 2010 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 217 | 652330 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
228 | 652341 | Wing-2 21th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
229 | 652342 | Wing-2 Flat No 2101 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
230 | 652343 | Wing-2 Flat No 2102 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
231 | 652345 | Wing-2 Flat No 2104 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
232 | 652346 | Wing-2 Flat No 2105 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
233 | 652347 | Wing-2 Flat No 2106 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
234 | 652348 | Wing-2 Flat No 2107 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
235 | 652349 | Wing-2 Flat No 2108 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
236 | 652350 | Wing-2 Flat No 2109 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
237 | 652344 | Wing-2 Flat No 2110 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 228 | 652341 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
238 | 652408 | Wing-2 22nd Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
239 | 652409 | Wing-2 Flat No 2201 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
240 | 652410 | Wing-2 Flat No 2202 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
241 | 652418 | Wing.2 Flat No 2203 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
242 | 652412 | Wing-2 Flat No 2204 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
243 | 652413 | Wing-2 Flat No 2205 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
244 | 652414 | Wing-2 Flat No 2206 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
245 | 652415 | Wing-2 Flat No 2207 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
246 | 652416 | Wing-2 Flat No 2208 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
247 | 652417 | Wing-2 Flat No 2209 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
248 | 652411 | Wing-2 Flat No 2210 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 238 | 652408 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
249 | 652476 | Wing-2 23rd Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
250 | 652477 | Wing-2 Flat No 2301 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
251 | 652478 | Wing-2 Flat No 2302 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
252 | 652486 | Wing.2 Flat No 2303 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
253 | 652480 | Wing-2 Flat No 2304 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
254 | 652481 | Wing-2 Flat No 2305 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
255 | 652482 | Wing-2 Flat No 2306 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
256 | 652483 | Wing-2 Flat No 2307 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
257 | 652484 | Wing-2 Flat No 2308 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
258 | 652485 | Wing-2 Flat No 2309 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
259 | 652479 | Wing-2 Flat No 2310 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 249 | 652476 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
260 | 652544 | Wing-2 24th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
261 | 652545 | Wing-2 Flat No 2401 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
262 | 652546 | Wing-2 Flat No 2402 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
263 | 652554 | Wing.2 Flat No 2403 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
264 | 652548 | Wing-2 Flat No 2404 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
265 | 652549 | Wing-2 Flat No 2405 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
266 | 652550 | Wing-2 Flat No 2406 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
267 | 652551 | Wing-2 Flat No 2407 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
268 | 652552 | Wing-2 Flat No 2408 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
269 | 652553 | Wing-2 Flat No 2409 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
270 | 652547 | Wing-2 Flat No 2410 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 260 | 652544 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
271 | 652555 | Wing-2 25th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
272 | 652556 | Wing-2 Flat No 2501 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
273 | 652557 | Wing-2 Flat No 2502 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
274 | 652565 | Wing.2 Flat No 2503 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
275 | 652559 | Wing-2 Flat No 2504 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
276 | 652560 | Wing-2 Flat No 2505 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
277 | 652561 | Wing-2 Flat No 2506 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
278 | 652562 | Wing-2 Flat No 2507 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
279 | 652563 | Wing-2 Flat No 2508 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
280 | 652564 | Wing-2 Flat No 2509 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
281 | 652558 | Wing-2 Flat No 2510 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 271 | 652555 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
282 | 652623 | Wing-2 26th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
283 | 652624 | Wing-2 Flat No 2601 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
284 | 652625 | Wing-2 Flat No 2602 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
285 | 652627 | Wing-2 Flat No 2604 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
286 | 652628 | Wing-2 Flat No 2605 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
287 | 652629 | Wing-2 Flat No 2606 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
288 | 652630 | Wing-2 Flat No 2607 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
289 | 652631 | Wing-2 Flat No 2608 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
290 | 652632 | Wing-2 Flat No 2609 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
291 | 652626 | Wing-2 Flat No 2610 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 282 | 652623 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
292 | 652633 | Wing-2 27th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
293 | 652634 | Wing-2 Flat No 2701 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
294 | 652635 | Wing-2 Flat No 2702 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
295 | 652643 | Wing.2 Flat No 2703 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
296 | 652637 | Wing-2 Flat No 2704 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
297 | 652638 | Wing-2 Flat No 2705 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
298 | 652639 | Wing-2 Flat No 2706 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
299 | 652640 | Wing-2 Flat No 2707 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
300 | 652641 | Wing-2 Flat No 2708 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
301 | 652642 | Wing-2 Flat No 2709 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
302 | 652636 | Wing-2 Flat No 2710 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 292 | 652633 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
303 | 652644 | Wing-2 28th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
304 | 652645 | Wing-2 Flat No 2801 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
305 | 652646 | Wing-2 Flat No 2802 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
306 | 652654 | Wing.2 Flat No 2803 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
307 | 652648 | Wing-2 Flat No 2804 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
308 | 652649 | Wing-2 Flat No 2805 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
309 | 652650 | Wing-2 Flat No 2806 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
310 | 652651 | Wing-2 Flat No 2807 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
311 | 652652 | Wing-2 Flat No 2808 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
312 | 652653 | Wing-2 Flat No 2809 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
313 | 652647 | Wing-2 Flat No 2810 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 303 | 652644 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
314 | 652655 | Wing-2 29th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
315 | 652656 | Wing-2 Flat No 2901 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
316 | 652657 | Wing-2 Flat No 2902 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
317 | 652665 | Wing.2 Flat No 2903 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
318 | 652659 | Wing-2 Flat No 2904 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
319 | 652660 | Wing-2 Flat No 2905 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
320 | 652661 | Wing-2 Flat No 2906 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
321 | 652662 | Wing-2 Flat No 2907 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
322 | 652663 | Wing-2 Flat No 2908 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
323 | 652664 | Wing-2 Flat No 2909 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
324 | 652658 | Wing-2 Flat No 2910 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 314 | 652655 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
325 | 652666 | Wing-2 30th Floor | NA | 0.0000 | 0.0000 | 1 | 398370 | 31 | 0 | [6 empty] | 0.0000
326 | 652667 | Wing-2 Flat No 3001 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
327 | 652668 | Wing-2 Flat No 3002 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
328 | 652676 | Wing.2 Flat No 3003 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
329 | 652670 | Wing-2 Flat No 3004 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
330 | 652671 | Wing-2 Flat No 3005 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
331 | 652672 | Wing-2 Flat No 3006 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
332 | 652673 | Wing-2 Flat No 3007 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
333 | 652674 | Wing-2 Flat No 3008 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
334 | 652675 | Wing-2 Flat No 3009 MS Window Grill | Sq.Ft | 83.3130 | 83.3130 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000
335 | 652669 | Wing-2 Flat No 3010 MS Window Grill | Sq.Ft | 118.1900 | 118.1900 | 325 | 652666 | 4 | 28839 | MS Window Grill 1 | [5 empty] | 0.0000