## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L) | Selected Group :- Wing-3 Superstructure (L)
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 399847 | Wing-3 Superstructure (L) | NA | 0.0000 | 0.0000 | 0 | 382072 | 31 | 0 | [6 empty] | 0.0000
2 | 399861 | Wing-3 - 1st Slab (P2 Lvl) | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
3 | 399867 | Wing-3 - 1st Slab (P2 Lvl) Building RCC Work | Sq.Ft | 11284.1000 | 11284.1000 | 2 | 399861 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
4 | 399868 | Wing-3 - 1st Slab (P2 Lvl) Flower Bed Chajja RCC Work | Sq.Ft | 434.0100 | 434.0100 | 2 | 399861 | 4 | 28434 | Flower Bed Chajja RCC Labour Work | [5 empty] | 0.0000
5 | 399869 | Wing-3 - 1st Slab (P2 Lvl) Podium RCC Work | Sq.Ft | 3959.4300 | 3959.4300 | 2 | 399861 | 4 | 28433 | Podium RCC Labour Work | [5 empty] | 0.0000
6 | 399862 | Wing-3 - 2nd Slab (P3 Lvl) | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
7 | 399870 | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Work | Sq.Ft | 12228.6200 | 12228.6200 | 6 | 399862 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
8 | 399871 | Wing-3 - 2nd Slab (P3 Lvl) Flower Bed Chajja RCC Work | Sq.Ft | 434.0100 | 434.0100 | 6 | 399862 | 4 | 28434 | Flower Bed Chajja RCC Labour Work | [5 empty] | 0.0000
9 | 399872 | Wing-3 - 2nd Slab (P3 Lvl) Podium RCC Work | Sq.Ft | 3959.4300 | 3959.4300 | 6 | 399862 | 4 | 28433 | Podium RCC Labour Work | [5 empty] | 0.0000
10 | 399863 | Wing-3 - 3rd Slab (P4 Lvl) | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
11 | 399873 | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Work | Sq.Ft | 12228.6200 | 12228.6200 | 10 | 399863 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
12 | 399874 | Wing-3 - 3rd Slab (P4 Lvl) Flower Bed Chajja RCC Work | Sq.Ft | 434.0100 | 434.0100 | 10 | 399863 | 4 | 28434 | Flower Bed Chajja RCC Labour Work | [5 empty] | 0.0000
13 | 399875 | Wing-3 - 3rd Slab (P4 Lvl) Podium RCC Work | Sq.Ft | 3959.4300 | 3959.4300 | 10 | 399863 | 4 | 28433 | Podium RCC Labour Work | [5 empty] | 0.0000
14 | 399864 | Wing-3 - 4th Slab (P5 Lvl) | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
15 | 399876 | Wing-3 - 4th Slab (P5 Lvl) Building RCC Work | Sq.Ft | 12228.6200 | 12228.6200 | 14 | 399864 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
16 | 399881 | Wing-3 - 4th Slab (P5 Lvl) Flower Bed Chajja RCC Work | Sq.Ft | 434.0100 | 434.0100 | 14 | 399864 | 4 | 28434 | Flower Bed Chajja RCC Labour Work | [5 empty] | 0.0000
17 | 399882 | Wing-3 - 4th Slab (P5 Lvl) Podium RCC Work | Sq.Ft | 3959.4300 | 3959.4300 | 14 | 399864 | 4 | 28433 | Podium RCC Labour Work | [5 empty] | 0.0000
18 | 399865 | Wing-3 - 5th Slab (P6 Lvl) | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
19 | 399877 | Wing-3 - 5th Slab (P6 Lvl) Building RCC Work | Sq.Ft | 12228.6200 | 12228.6200 | 18 | 399865 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
20 | 399880 | Wing-3 - 5th Slab (P6 Lvl) Flower Bed Chajja RCC Work | Sq.Ft | 434.0100 | 434.0100 | 18 | 399865 | 4 | 28434 | Flower Bed Chajja RCC Labour Work | [5 empty] | 0.0000
21 | 399883 | Wing-3 - 5th Slab (P6 Lvl) Podium RCC Work | Sq.Ft | 3959.4300 | 3959.4300 | 18 | 399865 | 4 | 28433 | Podium RCC Labour Work | [5 empty] | 0.0000
22 | 399866 | Wing-3 - 6th Slab (Podium Floor Lvl) | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
23 | 399878 | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Wor | Sq.Ft | 12274.3700 | 12274.3700 | 22 | 399866 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
24 | 399879 | Wing-3 - 6th Slab (Podium Floor Lvl) Flower Bed Chajja RCC L | Sq.Ft | 258.3400 | 258.3400 | 22 | 399866 | 4 | 28434 | Flower Bed Chajja RCC Labour Work | [5 empty] | 0.0000
25 | 399884 | Wing-3 - 6th Slab (Podium Floor Lvl) Podium RCC Work | Sq.Ft | 3935.3200 | 3935.3200 | 22 | 399866 | 4 | 28433 | Podium RCC Labour Work | [5 empty] | 0.0000
26 | 620793 | Wing-3 7th Slab (1st Floor) to terrace Slab | NA | 0.0000 | 0.0000 | 1 | 399847 | 31 | 0 | [6 empty] | 0.0000
27 | 620794 | Wing-3 1st Floor (7th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
28 | 620795 | Wing.3 2nd Floor (8th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
29 | 620796 | Wing.3 3rd Floor (9th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
30 | 620797 | Wing.3 4th Floor (10th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
31 | 620798 | Wing.3 5th Floor (11th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
32 | 620799 | Wing.3 6th Floor (12th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
33 | 620800 | Wing.3 7th Floor (13th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
34 | 620801 | Wing.3 8th Floor (14th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
35 | 620802 | Wing.3 9th Floor (15th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
36 | 620803 | Wing.3 10th Floor (16th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
37 | 620804 | Wing.3 11th Floor (17th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
38 | 620805 | Wing.3 12th Floor (18th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
39 | 620806 | Wing.3 13th Floor (19th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
40 | 620807 | Wing.3 14th Floor (20th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
41 | 620808 | Wing.3 15th Floor (21st Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
42 | 620809 | Wing.3 16th Floor (22nd Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
43 | 620810 | Wing.3 17th Floor (23rd Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
44 | 620811 | Wing.3 18th Floor (24th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
45 | 620812 | Wing.3 19th Floor (25th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
46 | 620813 | Wing.3 20th Floor (26th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
47 | 620814 | Wing.3 21st Floor (27th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
48 | 620815 | Wing.3 22nd Floor (28th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
49 | 620816 | Wing.3 23rd Floor (29th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
50 | 620817 | Wing.3 24th Floor (30th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
51 | 620818 | Wing.3 25th Floor (31st Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
52 | 620819 | Wing.3 26th Floor (32nd Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
53 | 620820 | Wing.3 27th Floor (33rd Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
54 | 620821 | Wing.3 28th Floor (34th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
55 | 620822 | Wing.3 29th Floor (35th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
56 | 620823 | Wing.3 30th Floor (36th Slab) RCC Work(L) | Sq.Ft | 10989.0900 | 10989.0900 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000
57 | 620824 | Wing.3 Terrace Floor (37th Slab) RCC Work(L) | Sq.Ft | 11194.1400 | 11194.1400 | 26 | 620793 | 4 | 28432 | Building RCC Labour Work | [5 empty] | 0.0000