## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work | Selected Group :- Wing-2 Common Lobby Painting Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 658604 | Wing-2 Common Lobby Painting Work | NA | 0.0000 | 0.0000 | 0 | 658598 | 31 | 0 | [6 empty] | 0.0000
2 | 658605 | Wing-2 Podium Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
3 | 658616 | Wing-2 Podium Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 2 | 658605 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
4 | 658627 | Wing-2 Podium Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 2 | 658605 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
5 | 658633 | Wing-2 1st Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
6 | 658634 | Wing-2 1st Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 5 | 658633 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
7 | 658635 | Wing-2 1st Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 5 | 658633 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
8 | 658646 | Wing-2 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
9 | 658647 | Wing-2 2nd Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 8 | 658646 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
10 | 658648 | Wing-2 2nd Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 8 | 658646 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
11 | 658654 | Wing-2 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
12 | 658655 | Wing-2 3rd Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 11 | 658654 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
13 | 658656 | Wing-2 3rd Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 11 | 658654 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
14 | 658662 | Wing-2 4th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
15 | 658663 | Wing-2 4th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 14 | 658662 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
16 | 658664 | Wing-2 4th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 14 | 658662 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
17 | 658665 | Wing-2 5th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
18 | 658666 | Wing-2 5th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 17 | 658665 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
19 | 658667 | Wing-2 5th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 17 | 658665 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
20 | 658673 | Wing-2 6th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
21 | 658674 | Wing-2 6th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 20 | 658673 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
22 | 658675 | Wing-2 6th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 20 | 658673 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
23 | 658676 | Wing-2 7th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
24 | 658677 | Wing-2 7th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 23 | 658676 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
25 | 658678 | Wing-2 7th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 23 | 658676 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
26 | 658684 | Wing-2 8th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
27 | 658685 | Wing-2 8th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 26 | 658684 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
28 | 658686 | Wing-2 8th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 26 | 658684 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
29 | 658708 | Wing-2 9th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
30 | 658709 | Wing-2 9th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 29 | 658708 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
31 | 658710 | Wing-2 9th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 29 | 658708 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
32 | 658717 | Wing-2 10th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
33 | 658718 | Wing-2 10th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 32 | 658717 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
34 | 658719 | Wing-2 10th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 32 | 658717 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
35 | 658720 | Wing-2 11th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
36 | 658721 | Wing-2 11th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 35 | 658720 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
37 | 658722 | Wing-2 11th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 35 | 658720 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
38 | 658724 | Wing-2 12th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
39 | 658725 | Wing-2 12th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 38 | 658724 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
40 | 658726 | Wing-2 12th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 38 | 658724 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
41 | 658728 | Wing-2 13th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
42 | 658729 | Wing-2 13th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 41 | 658728 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
43 | 658730 | Wing-2 13th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 41 | 658728 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
44 | 658732 | Wing-2 14th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
45 | 658733 | Wing-2 14th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 44 | 658732 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
46 | 658734 | Wing-2 14th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 44 | 658732 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
47 | 658735 | Wing-2 15th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
48 | 658736 | Wing-2 15th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 47 | 658735 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
49 | 658737 | Wing-2 15th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 47 | 658735 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
50 | 658739 | Wing-2 16th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
51 | 658740 | Wing-2 16th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 50 | 658739 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
52 | 658741 | Wing-2 16th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 50 | 658739 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
53 | 658742 | Wing-2 17th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
54 | 658743 | Wing-2 17th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 53 | 658742 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
55 | 658744 | Wing-2 17th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 53 | 658742 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
56 | 658746 | Wing-2 18th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
57 | 658747 | Wing-2 18th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 56 | 658746 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
58 | 658748 | Wing-2 18th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 56 | 658746 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
59 | 658750 | Wing-2 19th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
60 | 658751 | Wing-2 19th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 59 | 658750 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
61 | 658752 | Wing-2 19th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 59 | 658750 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
62 | 658754 | Wing-2 20th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
63 | 658755 | Wing-2 20th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 62 | 658754 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
64 | 658756 | Wing-2 20th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 62 | 658754 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
65 | 658758 | Wing-2 21st Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
66 | 658759 | Wing-2 21st Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 65 | 658758 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
67 | 658760 | Wing-2 21st Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 65 | 658758 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
68 | 658762 | Wing-2 22nd Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
69 | 658763 | Wing-2 22nd Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 68 | 658762 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
70 | 658764 | Wing-2 22nd Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 68 | 658762 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
71 | 658766 | Wing-2 23rd Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
72 | 658767 | Wing-2 23rd Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 71 | 658766 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
73 | 658768 | Wing-2 23rd Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 71 | 658766 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
74 | 658769 | Wing-2 24th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
75 | 658770 | Wing-2 24th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 74 | 658769 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
76 | 658771 | Wing-2 24th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 74 | 658769 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
77 | 658777 | Wing-2 25th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
78 | 658778 | Wing-2 25th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 77 | 658777 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
79 | 658779 | Wing-2 25th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 77 | 658777 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
80 | 658785 | Wing-2 26th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
81 | 658786 | Wing-2 26th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 80 | 658785 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
82 | 658787 | Wing-2 26th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 80 | 658785 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
83 | 658793 | Wing-2 27th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
84 | 658794 | Wing-2 27th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 83 | 658793 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
85 | 658795 | Wing-2 27th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 83 | 658793 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
86 | 658796 | Wing-2 28th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
87 | 658797 | Wing-2 28th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 86 | 658796 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
88 | 658798 | Wing-2 28th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 86 | 658796 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
89 | 658799 | Wing-2 29th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
90 | 658800 | Wing-2 29th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 89 | 658799 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
91 | 658801 | Wing-2 29th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 89 | 658799 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000
92 | 658802 | Wing-2 30th Floor | NA | 0.0000 | 0.0000 | 1 | 658604 | 31 | 0 | [6 empty] | 0.0000
93 | 658803 | Wing-2 30th Floor C. Lobby Wall & Beam Painting Work | Sq.Ft | 2763.4740 | 2763.4740 | 92 | 658802 | 4 | 34536 | Wing-2 C. Lobby Wall & Beam Painting Work | [5 empty] | 0.0000
94 | 658804 | Wing-2 30th Floor C. Lobby Ceiling Painting Work | Sq.Ft | 1274.1890 | 1274.1890 | 92 | 658802 | 4 | 34537 | Wing-2 C. Lobby Ceiling Painting Work | [5 empty] | 0.0000