## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work | Selected Group :- Wing-2 Staircase Painting Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 660068 | Wing-2 Staircase Painting Work | NA | 0.0000 | 0.0000 | 0 | 658598 | 31 | 0 | [6 empty] | 0.0000
2 | 660069 | Wing-2 Fire Staircase-1 Painting Work | NA | 0.0000 | 0.0000 | 1 | 660068 | 31 | 0 | [6 empty] | 0.0000
3 | 660070 | Wing-2 Podium Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
4 | 660071 | Wing-2 Podium Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 3 | 660070 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
5 | 660072 | Wing-2 Podium Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 3 | 660070 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
6 | 660138 | Wing-2 1st Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
7 | 660139 | Wing-2 1st Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 6 | 660138 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
8 | 660140 | Wing-2 1st Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 6 | 660138 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
9 | 660141 | Wing-2 2nd Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
10 | 660142 | Wing-2 2nd Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 9 | 660141 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
11 | 660143 | Wing-2 2nd Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 9 | 660141 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
12 | 660144 | Wing-2 3rd Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
13 | 660145 | Wing-2 3rd Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 12 | 660144 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
14 | 660146 | Wing-2 3rd Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 12 | 660144 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
15 | 660147 | Wing-2 4th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
16 | 660148 | Wing-2 4th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 15 | 660147 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
17 | 660149 | Wing-2 4th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 15 | 660147 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
18 | 660150 | Wing-2 5th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
19 | 660151 | Wing-2 5th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 18 | 660150 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
20 | 660152 | Wing-2 5th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 18 | 660150 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
21 | 660153 | Wing-2 6th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
22 | 660154 | Wing-2 6th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 21 | 660153 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
23 | 660155 | Wing-2 6th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 21 | 660153 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
24 | 660156 | Wing-2 7th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
25 | 660157 | Wing-2 7th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 24 | 660156 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
26 | 660158 | Wing-2 7th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 24 | 660156 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
27 | 660159 | Wing-2 8th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
28 | 660160 | Wing-2 8th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 27 | 660159 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
29 | 660161 | Wing-2 8th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 27 | 660159 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
30 | 660162 | Wing-2 9th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
31 | 660163 | Wing-2 9th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 30 | 660162 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
32 | 660164 | Wing-2 9th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 30 | 660162 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
33 | 660165 | Wing-2 10th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
34 | 660166 | Wing-2 10th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 33 | 660165 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
35 | 660167 | Wing-2 10th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 33 | 660165 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
36 | 660168 | Wing-2 11th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
37 | 660169 | Wing-2 11th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 36 | 660168 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
38 | 660170 | Wing-2 11th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 36 | 660168 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
39 | 660171 | Wing-2 12th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
40 | 660172 | Wing-2 12th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 39 | 660171 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
41 | 660173 | Wing-2 12th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 39 | 660171 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
42 | 660174 | Wing-2 13th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
43 | 660175 | Wing-2 13th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 42 | 660174 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
44 | 660176 | Wing-2 13th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 42 | 660174 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
45 | 660177 | Wing-2 14th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
46 | 660178 | Wing-2 14th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 45 | 660177 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
47 | 660179 | Wing-2 14th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 45 | 660177 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
48 | 660180 | Wing-2 15th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
49 | 660181 | Wing-2 15th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 48 | 660180 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
50 | 660182 | Wing-2 15th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 48 | 660180 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
51 | 660183 | Wing-2 16th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
52 | 660184 | Wing-2 16th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 51 | 660183 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
53 | 660185 | Wing-2 16th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 51 | 660183 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
54 | 660186 | Wing-2 17th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
55 | 660187 | Wing-2 17th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 54 | 660186 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
56 | 660188 | Wing-2 17th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 54 | 660186 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
57 | 660189 | Wing-2 18th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
58 | 660190 | Wing-2 18th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 57 | 660189 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
59 | 660191 | Wing-2 18th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 57 | 660189 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
60 | 660192 | Wing-2 19th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
61 | 660193 | Wing-2 19th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 60 | 660192 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
62 | 660194 | Wing-2 19th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 60 | 660192 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
63 | 660195 | Wing-2 20th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
64 | 660196 | Wing-2 20th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 63 | 660195 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
65 | 660197 | Wing-2 20th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 63 | 660195 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
66 | 660198 | Wing-2 21st Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
67 | 660199 | Wing-2 21st Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 66 | 660198 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
68 | 660200 | Wing-2 21st Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 66 | 660198 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
69 | 660201 | Wing-2 22nd Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
70 | 660202 | Wing-2 22nd Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 69 | 660201 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
71 | 660203 | Wing-2 22nd Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 69 | 660201 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
72 | 660204 | Wing-2 23rd Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
73 | 660205 | Wing-2 23rd Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 72 | 660204 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
74 | 660206 | Wing-2 23rd Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 72 | 660204 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
75 | 660207 | Wing-2 24th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
76 | 660208 | Wing-2 24th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 75 | 660207 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
77 | 660209 | Wing-2 24th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 75 | 660207 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
78 | 660210 | Wing-2 25th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
79 | 660211 | Wing-2 25th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 78 | 660210 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
80 | 660212 | Wing-2 25th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 78 | 660210 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
81 | 660213 | Wing-2 26th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
82 | 660214 | Wing-2 26th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 81 | 660213 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
83 | 660215 | Wing-2 26th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 81 | 660213 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
84 | 660216 | Wing-2 27th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
85 | 660217 | Wing-2 27th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 84 | 660216 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
86 | 660218 | Wing-2 27th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 84 | 660216 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
87 | 660219 | Wing-2 28th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
88 | 660220 | Wing-2 28th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 87 | 660219 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
89 | 660221 | Wing-2 28th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 87 | 660219 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
90 | 660222 | Wing-2 29th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
91 | 660223 | Wing-2 29th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 90 | 660222 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
92 | 660224 | Wing-2 29th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 90 | 660222 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
93 | 660225 | Wing-2 30th Floor | NA | 0.0000 | 0.0000 | 2 | 660069 | 31 | 0 | [6 empty] | 0.0000
94 | 660226 | Wing-2 30th Floor Staircase-1 Wall & Beam Painting Work | Sq.Ft | 613.9430 | 613.9430 | 93 | 660225 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
95 | 660227 | Wing-2 30th Floor Staircase-1 Ceiling Painting Work | Sq.Ft | 167.4878 | 167.4878 | 93 | 660225 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
96 | 660073 | Wing-2 Fire Staircase-2 Painting Work | NA | 0.0000 | 0.0000 | 1 | 660068 | 31 | 0 | [6 empty] | 0.0000
97 | 660074 | Wing-2 Podium Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
98 | 660075 | Wing-2 Podium Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 97 | 660074 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
99 | 660076 | Wing-2 Podium Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 97 | 660074 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
100 | 660228 | Wing-2 1st Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
101 | 660229 | Wing-2 1st Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 100 | 660228 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
102 | 660230 | Wing-2 1st Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 100 | 660228 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
103 | 660231 | Wing-2 2nd Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
104 | 660232 | Wing-2 2nd Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 103 | 660231 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
105 | 660233 | Wing-2 2nd Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 103 | 660231 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
106 | 660234 | Wing-2 3rd Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
107 | 660235 | Wing-2 3rd Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 106 | 660234 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
108 | 660236 | Wing-2 3rd Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 106 | 660234 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
109 | 660237 | Wing-2 4th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
110 | 660238 | Wing-2 4th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 109 | 660237 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
111 | 660239 | Wing-2 4th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 109 | 660237 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
112 | 660240 | Wing-2 5th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
113 | 660241 | Wing-2 5th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 112 | 660240 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
114 | 660242 | Wing-2 5th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 112 | 660240 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
115 | 660243 | Wing-2 6th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
116 | 660244 | Wing-2 6th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 115 | 660243 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
117 | 660245 | Wing-2 6th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 115 | 660243 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
118 | 660246 | Wing-2 7th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
119 | 660247 | Wing-2 7th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 118 | 660246 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
120 | 660248 | Wing-2 7th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 118 | 660246 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
121 | 660249 | Wing-2 8th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
122 | 660250 | Wing-2 8th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 121 | 660249 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
123 | 660251 | Wing-2 8th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 121 | 660249 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
124 | 660252 | Wing-2 9th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
125 | 660253 | Wing-2 9th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 124 | 660252 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
126 | 660254 | Wing-2 9th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 124 | 660252 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
127 | 660255 | Wing-2 10th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
128 | 660256 | Wing-2 10th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 127 | 660255 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
129 | 660257 | Wing-2 10th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 127 | 660255 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
130 | 660258 | Wing-2 11th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
131 | 660259 | Wing-2 11th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 130 | 660258 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
132 | 660260 | Wing-2 11th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 130 | 660258 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
133 | 660261 | Wing-2 12th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
134 | 660262 | Wing-2 12th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 133 | 660261 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
135 | 660263 | Wing-2 12th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 133 | 660261 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
136 | 660264 | Wing-2 13th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
137 | 660265 | Wing-2 13th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 136 | 660264 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
138 | 660266 | Wing-2 13th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 136 | 660264 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
139 | 660267 | Wing-2 14th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
140 | 660268 | Wing-2 14th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 139 | 660267 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
141 | 660269 | Wing-2 14th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 139 | 660267 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
142 | 660271 | Wing-2 15th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
143 | 660272 | Wing-2 15th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 142 | 660271 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
144 | 660273 | Wing-2 15th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 142 | 660271 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
145 | 660275 | Wing-2 16th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
146 | 660276 | Wing-2 16th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 145 | 660275 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
147 | 660277 | Wing-2 16th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 145 | 660275 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
148 | 660278 | Wing-2 17th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
149 | 660279 | Wing-2 17th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 148 | 660278 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
150 | 660280 | Wing-2 17th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 148 | 660278 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
151 | 660281 | Wing-2 18th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
152 | 660282 | Wing-2 18th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 151 | 660281 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
153 | 660283 | Wing-2 18th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 151 | 660281 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
154 | 660284 | Wing-2 19th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
155 | 660285 | Wing-2 19th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 154 | 660284 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
156 | 660286 | Wing-2 19th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 154 | 660284 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
157 | 660287 | Wing-2 20th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
158 | 660288 | Wing-2 20th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 157 | 660287 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
159 | 660289 | Wing-2 20th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 157 | 660287 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
160 | 660290 | Wing-2 21st Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
161 | 660291 | Wing-2 21st Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 160 | 660290 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
162 | 660292 | Wing-2 21st Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 160 | 660290 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
163 | 660293 | Wing-2 22nd Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
164 | 660294 | Wing-2 22nd Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 163 | 660293 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
165 | 660295 | Wing-2 22nd Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 163 | 660293 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
166 | 660296 | Wing-2 23rd Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
167 | 660297 | Wing-2 23rd Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 166 | 660296 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
168 | 660298 | Wing-2 23rd Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 166 | 660296 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
169 | 660299 | Wing-2 24th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
170 | 660300 | Wing-2 24th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 169 | 660299 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
171 | 660301 | Wing-2 24th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 169 | 660299 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
172 | 660302 | Wing-2 25th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
173 | 660303 | Wing-2 25th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 172 | 660302 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
174 | 660304 | Wing-2 25th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 172 | 660302 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
175 | 660305 | Wing-2 26th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
176 | 660306 | Wing-2 26th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 175 | 660305 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
177 | 660307 | Wing-2 26th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 175 | 660305 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
178 | 660308 | Wing-2 27th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
179 | 660309 | Wing-2 27th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 178 | 660308 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
180 | 660310 | Wing-2 27th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 178 | 660308 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
181 | 660311 | Wing-2 28th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
182 | 660312 | Wing-2 28th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 181 | 660311 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
183 | 660313 | Wing-2 28th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 181 | 660311 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
184 | 660314 | Wing-2 29th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
185 | 660315 | Wing-2 29th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 184 | 660314 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
186 | 660316 | Wing-2 29th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 184 | 660314 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000
187 | 660317 | Wing-2 30th Floor | NA | 0.0000 | 0.0000 | 96 | 660073 | 31 | 0 | [6 empty] | 0.0000
188 | 660318 | Wing-2 30th Floor Staircase-2 Wall & Beam Painting Work | Sq.Ft | 601.1870 | 601.1870 | 187 | 660317 | 4 | 34556 | Wing-2 Staircase Wall & Beam Painting Work | [5 empty] | 0.0000
189 | 660319 | Wing-2 30th Floor Staircase Ceiling Painting Work | Sq.Ft | 150.6960 | 150.6960 | 187 | 660317 | 4 | 34557 | Wing-2 Staircase Waist Slab & Landing Painting Work | [5 empty] | 0.0000