## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P | Selected Group :- Wing-1 W/P 16th floor Above W/P
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 674188 | Wing-1 W/P 16th floor Above W/P | NA | 0.0000 | 0.0000 | 0 | 384180 | 31 | 0 | [6 empty] | 0.0000
2 | 388401 | Wing-1 16thFloor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
3 | 388402 | Wing-1 Flat No 1601 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
4 | 388403 | Wing-1 Flat No 1601 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 3 | 388402 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
5 | 388404 | Wing-1 Flat No 1601 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 3 | 388402 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
6 | 388405 | Wing-1 Flat No 1601 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 3 | 388402 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
7 | 388406 | Wing-1 Flat No 1601 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 3 | 388402 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
8 | 388407 | Wing-1 Flat No 1601 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 3 | 388402 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
9 | 388408 | Wing-1 Flat No 1601 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 3 | 388402 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
10 | 388409 | Wing-1 Flat No 1601 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 3 | 388402 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
11 | 388410 | Wing-1 Flat No 1601 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 3 | 388402 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
12 | 388483 | Wing-1 Flat No 1601 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 3 | 388402 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
13 | 388492 | Wing-1 Flat No 1601 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 3 | 388402 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
14 | 451197 | Wing-1 Flat No 1601 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 3 | 388402 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
15 | 388411 | Wing-1 Flat No 1602 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
16 | 388412 | Wing-1 Flat No 1602 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 15 | 388411 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
17 | 388413 | Wing-1 Flat No 1602 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 15 | 388411 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
18 | 388414 | Wing-1 Flat No 1602 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 15 | 388411 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
19 | 388415 | Wing-1 Flat No 1602 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 15 | 388411 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
20 | 388416 | Wing-1 Flat No 1602 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 15 | 388411 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
21 | 388417 | Wing-1 Flat No 1602 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 15 | 388411 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
22 | 388418 | Wing-1 Flat No 1602 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 15 | 388411 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
23 | 388419 | Wing-1 Flat No 1602 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 15 | 388411 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
24 | 388484 | Wing-1 Flat No 1602 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 15 | 388411 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
25 | 388493 | Wing-1 Flat No 1602 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 15 | 388411 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
26 | 451198 | Wing-1 Flat No 1602 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 15 | 388411 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
27 | 388420 | Wing-1 Flat No 1603 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
28 | 388421 | Wing-1 Flat No 1603 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 27 | 388420 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
29 | 388422 | Wing-1 Flat No 1603 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 27 | 388420 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
30 | 388423 | Wing-1 Flat No 1603 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 27 | 388420 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
31 | 388424 | Wing-1 Flat No 1603 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 27 | 388420 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
32 | 388425 | Wing-1 Flat No 1603 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 27 | 388420 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
33 | 388426 | Wing-1 Flat No 1603 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 27 | 388420 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
34 | 388427 | Wing-1 Flat No 1603 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 27 | 388420 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
35 | 388428 | Wing-1 Flat No 1603 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 27 | 388420 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
36 | 388485 | Wing-1 Flat No 1603 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 27 | 388420 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
37 | 388494 | Wing-1 Flat No 1603 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 27 | 388420 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
38 | 451199 | Wing-1 Flat No 1603 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 27 | 388420 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
39 | 388429 | Wing-1 Flat No 1604 (Refuge Area) | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
40 | 388430 | Wing-1 Flat No 1604 Int Flat Chemical Grouting Work | Sq.Ft | 552.9600 | 552.9600 | 39 | 388429 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
41 | 388431 | Wing-1 Flat No 1604 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 39 | 388429 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
42 | 388432 | Wing-1 Flat No 1604 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 39 | 388429 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
43 | 388433 | Wing-1 Flat No 1604 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 39 | 388429 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
44 | 388434 | Wing-1 Flat No 1604 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 39 | 388429 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
45 | 388435 | Wing-1 Flat No 1604 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 39 | 388429 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
46 | 388436 | Wing-1 Flat No 1604 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 39 | 388429 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
47 | 388437 | Wing-1 Flat No 1604 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 39 | 388429 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
48 | 388486 | Wing-1 Flat No 1604 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 39 | 388429 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
49 | 388495 | Wing-1 Flat No 1604 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 39 | 388429 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
50 | 451200 | Wing-1 Flat No 1604 (Refuge Area) Bore Packing + Perma Eazee | Flat | 1.0000 | 1.0000 | 39 | 388429 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
51 | 388438 | Wing-1 Flat No 1605 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
52 | 388439 | Wing-1 Flat No 1605 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 51 | 388438 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
53 | 388440 | Wing-1 Flat No 1605 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 51 | 388438 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
54 | 388441 | Wing-1 Flat No 1605 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 51 | 388438 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
55 | 388442 | Wing-1 Flat No 1605 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 51 | 388438 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
56 | 388443 | Wing-1 Flat No 1605 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 51 | 388438 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
57 | 388444 | Wing-1 Flat No 1605 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 51 | 388438 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
58 | 388445 | Wing-1 Flat No 1605 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 51 | 388438 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
59 | 388446 | Wing-1 Flat No 1605 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 51 | 388438 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
60 | 388487 | Wing-1 Flat No 1605 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 51 | 388438 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
61 | 388496 | Wing-1 Flat No 1605 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 51 | 388438 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
62 | 451201 | Wing-1 Flat No 1605 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 51 | 388438 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
63 | 388447 | Wing-1 Flat No 1606 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
64 | 388448 | Wing-1 Flat No 1606 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 63 | 388447 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
65 | 388449 | Wing-1 Flat No 1606 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 63 | 388447 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
66 | 388450 | Wing-1 Flat No 1606 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 63 | 388447 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
67 | 388451 | Wing-1 Flat No 1606 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 63 | 388447 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
68 | 388452 | Wing-1 Flat No 1606 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 63 | 388447 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
69 | 388453 | Wing-1 Flat No 1606 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 63 | 388447 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
70 | 388454 | Wing-1 Flat No 1606 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 63 | 388447 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
71 | 388455 | Wing-1 Flat No 1606 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 63 | 388447 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
72 | 388488 | Wing-1 Flat No 1606 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 63 | 388447 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
73 | 388497 | Wing-1 Flat No 1606 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 63 | 388447 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
74 | 451202 | Wing-1 Flat No 1606 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 63 | 388447 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
75 | 388456 | Wing-1 Flat No 1607 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
76 | 388457 | Wing-1 Flat No 1607 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 75 | 388456 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
77 | 388458 | Wing-1 Flat No 1607 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 75 | 388456 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
78 | 388459 | Wing-1 Flat No 1607 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 75 | 388456 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
79 | 388460 | Wing-1 Flat No 1607 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 75 | 388456 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
80 | 388461 | Wing-1 Flat No 1607 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 75 | 388456 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
81 | 388462 | Wing-1 Flat No 1607 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 75 | 388456 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
82 | 388463 | Wing-1 Flat No 1607 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 75 | 388456 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
83 | 388464 | Wing-1 Flat No 1607 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 75 | 388456 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
84 | 388489 | Wing-1 Flat No 1607 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 75 | 388456 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
85 | 388498 | Wing-1 Flat No 1607 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 75 | 388456 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
86 | 451203 | Wing-1 Flat No 1607 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 75 | 388456 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
87 | 388465 | Wing-1 Flat No 1608 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
88 | 388466 | Wing-1 Flat No 1608 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 87 | 388465 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
89 | 388467 | Wing-1 Flat No 1608 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 87 | 388465 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
90 | 388468 | Wing-1 Flat No 1608 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 87 | 388465 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
91 | 388469 | Wing-1 Flat No 1608 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 87 | 388465 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
92 | 388470 | Wing-1 Flat No 1608 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 87 | 388465 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
93 | 388471 | Wing-1 Flat No 1608 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 87 | 388465 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
94 | 388472 | Wing-1 Flat No 1608 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 87 | 388465 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
95 | 388473 | Wing-1 Flat No 1608 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 87 | 388465 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
96 | 388490 | Wing-1 Flat No 1608 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 87 | 388465 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
97 | 388499 | Wing-1 Flat No 1608 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 87 | 388465 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
98 | 451204 | Wing-1 Flat No 1608 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 87 | 388465 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
99 | 388474 | Wing-1 Flat No 1609 | NA | 0.0000 | 0.0000 | 2 | 388401 | 31 | 0 | [6 empty] | 0.0000
100 | 388475 | Wing.1 Flat No 1609 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 99 | 388474 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
101 | 388476 | Wing-1 Flat No 1609 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 99 | 388474 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
102 | 388477 | Wing-1 Flat No 1609 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 99 | 388474 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
103 | 388478 | Wing-1 Flat No 1609 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 99 | 388474 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
104 | 388479 | Wing-1 Flat No 1609 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 99 | 388474 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
105 | 388480 | Wing-1 Flat No 1609 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 99 | 388474 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
106 | 388481 | Wing-1 Flat No 1609 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 99 | 388474 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
107 | 388482 | Wing-1 Flat No 1609 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 99 | 388474 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
108 | 388491 | Wing-1 Flat No 1609 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 99 | 388474 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
109 | 388500 | Wing-1 Flat No 1609 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 99 | 388474 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
110 | 451205 | Wing-1 Flat No 1609 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 99 | 388474 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
111 | 387401 | Wing-1 17th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
112 | 387402 | Wing-1 Flat No 1701 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
113 | 387403 | Wing-1 Flat No 1701 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 112 | 387402 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
114 | 387404 | Wing-1 Flat No 1701 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 112 | 387402 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
115 | 387405 | Wing-1 Flat No 1701 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 112 | 387402 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
116 | 387406 | Wing-1 Flat No 1701 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 112 | 387402 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
117 | 387407 | Wing-1 Flat No 1701 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 112 | 387402 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
118 | 387408 | Wing-1 Flat No 1701 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 112 | 387402 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
119 | 387409 | Wing-1 Flat No 1701 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 112 | 387402 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
120 | 387410 | Wing-1 Flat No 1701 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 112 | 387402 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
121 | 387483 | Wing-1 Flat No 1701 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 112 | 387402 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
122 | 387492 | Wing-1 Flat No 1701 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 112 | 387402 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
123 | 451206 | Wing-1 Flat No 1701 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 112 | 387402 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
124 | 387411 | Wing-1 Flat No 1702 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
125 | 387412 | Wing-1 Flat No 1702 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 124 | 387411 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
126 | 387413 | Wing-1 Flat No 1702 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 124 | 387411 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
127 | 387414 | Wing-1 Flat No 1702 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 124 | 387411 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
128 | 387415 | Wing-1 Flat No 1702 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 124 | 387411 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
129 | 387416 | Wing-1 Flat No 1702 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 124 | 387411 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
130 | 387417 | Wing-1 Flat No 1702 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 124 | 387411 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
131 | 387418 | Wing-1 Flat No 1702 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 124 | 387411 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
132 | 387419 | Wing-1 Flat No 1702 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 124 | 387411 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
133 | 387484 | Wing-1 Flat No 1702 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 124 | 387411 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
134 | 387493 | Wing-1 Flat No 1702 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 124 | 387411 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
135 | 451207 | Wing-1 Flat No 1702 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 124 | 387411 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
136 | 387420 | Wing-1 Flat No 1703 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
137 | 387421 | Wing-1 Flat No 1703 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 136 | 387420 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
138 | 387422 | Wing-1 Flat No 1703 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 136 | 387420 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
139 | 387423 | Wing-1 Flat No 1703 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 136 | 387420 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
140 | 387424 | Wing-1 Flat No 1703 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 136 | 387420 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
141 | 387425 | Wing-1 Flat No 1703 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 136 | 387420 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
142 | 387426 | Wing-1 Flat No 1703 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 136 | 387420 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
143 | 387427 | Wing-1 Flat No 1703 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 136 | 387420 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
144 | 387428 | Wing-1 Flat No 1703 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 136 | 387420 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
145 | 387485 | Wing-1 Flat No 1703 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 136 | 387420 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
146 | 387494 | Wing-1 Flat No 1703 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 136 | 387420 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
147 | 451208 | Wing-1 Flat No 1703 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 136 | 387420 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
148 | 387429 | Wing-1 Flat No 1704 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
149 | 387430 | Wing-1 Flat No 1704 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 148 | 387429 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
150 | 387431 | Wing-1 Flat No 1704 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 148 | 387429 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
151 | 387432 | Wing-1 Flat No 1704 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 148 | 387429 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
152 | 387433 | Wing-1 Flat No 1704 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 148 | 387429 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
153 | 387434 | Wing-1 Flat No 1704 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 148 | 387429 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
154 | 387435 | Wing-1 Flat No 1704 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 148 | 387429 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
155 | 387436 | Wing-1 Flat No 1704 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 148 | 387429 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
156 | 387437 | Wing-1 Flat No 1704 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 148 | 387429 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
157 | 387486 | Wing-1 Flat No 1704 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 148 | 387429 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
158 | 387495 | Wing-1 Flat No 1704 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 148 | 387429 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
159 | 451209 | Wing-1 Flat No 1704 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 148 | 387429 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
160 | 387438 | Wing-1 Flat No 1705 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
161 | 387439 | Wing-1 Flat No 1705 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 160 | 387438 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
162 | 387440 | Wing-1 Flat No 1705 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 160 | 387438 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
163 | 387441 | Wing-1 Flat No 1705 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 160 | 387438 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
164 | 387442 | Wing-1 Flat No 1705 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 160 | 387438 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
165 | 387443 | Wing-1 Flat No 1705 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 160 | 387438 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
166 | 387444 | Wing-1 Flat No 1705 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 160 | 387438 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
167 | 387445 | Wing-1 Flat No 1705 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 160 | 387438 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
168 | 387446 | Wing-1 Flat No 1705 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 160 | 387438 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
169 | 387487 | Wing-1 Flat No 1705 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 160 | 387438 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
170 | 387496 | Wing-1 Flat No 1705 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 160 | 387438 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
171 | 451210 | Wing-1 Flat No 1705 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 160 | 387438 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
172 | 387447 | Wing-1 Flat No 1706 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
173 | 387448 | Wing-1 Flat No 1706 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 172 | 387447 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
174 | 387449 | Wing-1 Flat No 1706 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 172 | 387447 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
175 | 387450 | Wing-1 Flat No 1706 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 172 | 387447 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
176 | 387451 | Wing-1 Flat No 1706 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 172 | 387447 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
177 | 387452 | Wing-1 Flat No 1706 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 172 | 387447 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
178 | 387453 | Wing-1 Flat No 1706 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 172 | 387447 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
179 | 387454 | Wing-1 Flat No 1706 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 172 | 387447 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
180 | 387455 | Wing-1 Flat No 1706 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 172 | 387447 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
181 | 387488 | Wing-1 Flat No 1706 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 172 | 387447 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
182 | 387497 | Wing-1 Flat No 1706 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 172 | 387447 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
183 | 451211 | Wing-1 Flat No 1706 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 172 | 387447 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
184 | 387456 | Wing-1 Flat No 1707 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
185 | 387457 | Wing-1 Flat No 1707 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 184 | 387456 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
186 | 387458 | Wing-1 Flat No 1707 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 184 | 387456 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
187 | 387459 | Wing-1 Flat No 1707 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 184 | 387456 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
188 | 387460 | Wing-1 Flat No 1707 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 184 | 387456 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
189 | 387461 | Wing-1 Flat No 1707 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 184 | 387456 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
190 | 387462 | Wing-1 Flat No 1707 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 184 | 387456 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
191 | 387463 | Wing-1 Flat No 1707 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 184 | 387456 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
192 | 387464 | Wing-1 Flat No 1707 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 184 | 387456 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
193 | 387489 | Wing-1 Flat No 1707 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 184 | 387456 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
194 | 387498 | Wing-1 Flat No 1707 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 184 | 387456 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
195 | 451212 | Wing-1 Flat No 1707 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 184 | 387456 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
196 | 387465 | Wing-1 Flat No 1708 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
197 | 387466 | Wing-1 Flat No 1708 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 196 | 387465 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
198 | 387467 | Wing-1 Flat No 1708 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 196 | 387465 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
199 | 387468 | Wing-1 Flat No 1708 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 196 | 387465 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
200 | 387469 | Wing-1 Flat No 1708 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 196 | 387465 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
201 | 387470 | Wing-1 Flat No 1708 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 196 | 387465 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
202 | 387471 | Wing-1 Flat No 1708 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 196 | 387465 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
203 | 387472 | Wing-1 Flat No 1708 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 196 | 387465 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
204 | 387473 | Wing-1 Flat No 1708 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 196 | 387465 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
205 | 387490 | Wing-1 Flat No 1708 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 196 | 387465 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
206 | 387499 | Wing-1 Flat No 1708 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 196 | 387465 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
207 | 451213 | Wing-1 Flat No 1708 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 196 | 387465 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
208 | 387474 | Wing-1 Flat No 1709 | NA | 0.0000 | 0.0000 | 111 | 387401 | 31 | 0 | [6 empty] | 0.0000
209 | 387475 | Wing.1 Flat No 1709 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 208 | 387474 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
210 | 387476 | Wing-1 Flat No 1709 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 208 | 387474 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
211 | 387477 | Wing-1 Flat No 1709 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 208 | 387474 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
212 | 387478 | Wing-1 Flat No 1709 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 208 | 387474 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
213 | 387479 | Wing-1 Flat No 1709 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 208 | 387474 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
214 | 387480 | Wing-1 Flat No 1709 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 208 | 387474 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
215 | 387481 | Wing-1 Flat No 1709 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 208 | 387474 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
216 | 387482 | Wing-1 Flat No 1709 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 208 | 387474 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
217 | 387491 | Wing-1 Flat No 1709 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 208 | 387474 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
218 | 387500 | Wing-1 Flat No 1709 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 208 | 387474 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
219 | 451214 | Wing-1 Flat No 1709 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 208 | 387474 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
220 | 387501 | Wing-1 18th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
221 | 387502 | Wing-1 Flat No 1801 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
222 | 387503 | Wing-1 Flat No 1801 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 221 | 387502 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
223 | 387504 | Wing-1 Flat No 1801 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 221 | 387502 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
224 | 387505 | Wing-1 Flat No 1801 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 221 | 387502 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
225 | 387506 | Wing-1 Flat No 1801 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 221 | 387502 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
226 | 387507 | Wing-1 Flat No 1801 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 221 | 387502 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
227 | 387508 | Wing-1 Flat No 1801 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 221 | 387502 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
228 | 387509 | Wing-1 Flat No 1801 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 221 | 387502 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
229 | 387510 | Wing-1 Flat No 1801 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 221 | 387502 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
230 | 387583 | Wing-1 Flat No 1801 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 221 | 387502 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
231 | 387592 | Wing-1 Flat No 1801 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 221 | 387502 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
232 | 451215 | Wing-1 Flat No 1801 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 221 | 387502 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
233 | 387511 | Wing-1 Flat No 1802 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
234 | 387512 | Wing-1 Flat No 1802 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 233 | 387511 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
235 | 387513 | Wing-1 Flat No 1802 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 233 | 387511 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
236 | 387514 | Wing-1 Flat No 1802 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 233 | 387511 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
237 | 387515 | Wing-1 Flat No 1802 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 233 | 387511 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
238 | 387516 | Wing-1 Flat No 1802 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 233 | 387511 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
239 | 387517 | Wing-1 Flat No 1802 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 233 | 387511 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
240 | 387518 | Wing-1 Flat No 1802 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 233 | 387511 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
241 | 387519 | Wing-1 Flat No 1802 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 233 | 387511 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
242 | 387584 | Wing-1 Flat No 1802 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 233 | 387511 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
243 | 387593 | Wing-1 Flat No 1802 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 233 | 387511 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
244 | 451216 | Wing-1 Flat No 1802 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 233 | 387511 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
245 | 387520 | Wing-1 Flat No 1803 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
246 | 387521 | Wing-1 Flat No 1803 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 245 | 387520 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
247 | 387522 | Wing-1 Flat No 1803 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 245 | 387520 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
248 | 387523 | Wing-1 Flat No 1803 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 245 | 387520 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
249 | 387524 | Wing-1 Flat No 1803 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 245 | 387520 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
250 | 387525 | Wing-1 Flat No 1803 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 245 | 387520 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
251 | 387526 | Wing-1 Flat No 1803 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 245 | 387520 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
252 | 387527 | Wing-1 Flat No 1803 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 245 | 387520 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
253 | 387528 | Wing-1 Flat No 1803 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 245 | 387520 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
254 | 387585 | Wing-1 Flat No 1803 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 245 | 387520 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
255 | 387594 | Wing-1 Flat No 1803 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 245 | 387520 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
256 | 451217 | Wing-1 Flat No 1803 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 245 | 387520 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
257 | 387529 | Wing-1 Flat No 1804 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
258 | 387530 | Wing-1 Flat No 1804 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 257 | 387529 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
259 | 387531 | Wing-1 Flat No 1804 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 257 | 387529 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
260 | 387532 | Wing-1 Flat No 1804 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 257 | 387529 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
261 | 387533 | Wing-1 Flat No 1804 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 257 | 387529 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
262 | 387534 | Wing-1 Flat No 1804 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 257 | 387529 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
263 | 387535 | Wing-1 Flat No 1804 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 257 | 387529 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
264 | 387536 | Wing-1 Flat No 1804 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 257 | 387529 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
265 | 387537 | Wing-1 Flat No 1804 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 257 | 387529 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
266 | 387586 | Wing-1 Flat No 1804 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 257 | 387529 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
267 | 387595 | Wing-1 Flat No 1804 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 257 | 387529 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
268 | 451218 | Wing-1 Flat No 1804 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 257 | 387529 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
269 | 387538 | Wing-1 Flat No 1805 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
270 | 387539 | Wing-1 Flat No 1805 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 269 | 387538 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
271 | 387540 | Wing-1 Flat No 1805 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 269 | 387538 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
272 | 387541 | Wing-1 Flat No 1805 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 269 | 387538 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
273 | 387542 | Wing-1 Flat No 1805 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 269 | 387538 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
274 | 387543 | Wing-1 Flat No 1805 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 269 | 387538 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
275 | 387544 | Wing-1 Flat No 1805 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 269 | 387538 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
276 | 387545 | Wing-1 Flat No 1805 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 269 | 387538 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
277 | 387546 | Wing-1 Flat No 1805 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 269 | 387538 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
278 | 387587 | Wing-1 Flat No 1805 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 269 | 387538 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
279 | 387596 | Wing-1 Flat No 1805 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 269 | 387538 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
280 | 451220 | Wing-1 Flat No 1805 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 269 | 387538 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
281 | 387547 | Wing-1 Flat No1806 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
282 | 387548 | Wing-1 Flat No 1806 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 281 | 387547 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
283 | 387549 | Wing-1 Flat No 1806 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 281 | 387547 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
284 | 387550 | Wing-1 Flat No 1806 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 281 | 387547 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
285 | 387551 | Wing-1 Flat No 1806 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 281 | 387547 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
286 | 387552 | Wing-1 Flat No 1806 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 281 | 387547 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
287 | 387553 | Wing-1 Flat No 1806 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 281 | 387547 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
288 | 387554 | Wing-1 Flat No 1806 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 281 | 387547 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
289 | 387555 | Wing-1 Flat No 1806 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 281 | 387547 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
290 | 387588 | Wing-1 Flat No 1806 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 281 | 387547 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
291 | 387597 | Wing-1 Flat No 1806 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 281 | 387547 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
292 | 451221 | Wing-1 Flat No1806 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 281 | 387547 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
293 | 387556 | Wing-1 Flat No 1807 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
294 | 387557 | Wing-1 Flat No 1807 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 293 | 387556 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
295 | 387558 | Wing-1 Flat No 1807 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 293 | 387556 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
296 | 387559 | Wing-1 Flat No 1807 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 293 | 387556 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
297 | 387560 | Wing-1 Flat No 1807 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 293 | 387556 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
298 | 387561 | Wing-1 Flat No 1807 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 293 | 387556 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
299 | 387562 | Wing-1 Flat No 1807 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 293 | 387556 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
300 | 387563 | Wing-1 Flat No 1807 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 293 | 387556 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
301 | 387564 | Wing-1 Flat No 1807 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 293 | 387556 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
302 | 387589 | Wing-1 Flat No 1807 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 293 | 387556 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
303 | 387598 | Wing-1 Flat No 1807 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 293 | 387556 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
304 | 451222 | Wing-1 Flat No 1807 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 293 | 387556 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
305 | 387565 | Wing-1 Flat No 1808 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
306 | 387566 | Wing-1 Flat No 1808 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 305 | 387565 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
307 | 387567 | Wing-1 Flat No 1808 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 305 | 387565 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
308 | 387568 | Wing-1 Flat No 1808 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 305 | 387565 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
309 | 387569 | Wing-1 Flat No 1808 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 305 | 387565 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
310 | 387570 | Wing-1 Flat No 1808 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 305 | 387565 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
311 | 387571 | Wing-1 Flat No 1808 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 305 | 387565 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
312 | 387572 | Wing-1 Flat No 1808 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 305 | 387565 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
313 | 387573 | Wing-1 Flat No 1808 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 305 | 387565 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
314 | 387590 | Wing-1 Flat No 1808 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 305 | 387565 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
315 | 387599 | Wing-1 Flat No 1808 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 305 | 387565 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
316 | 451223 | Wing-1 Flat No 1808 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 305 | 387565 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
317 | 387574 | Wing-1 Flat No 1809 | NA | 0.0000 | 0.0000 | 220 | 387501 | 31 | 0 | [6 empty] | 0.0000
318 | 387575 | Wing.1 Flat No 1809 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 317 | 387574 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
319 | 387576 | Wing-1 Flat No 1809 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 317 | 387574 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
320 | 387577 | Wing-1 Flat No 1809 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 317 | 387574 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
321 | 387578 | Wing-1 Flat No 1809 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 317 | 387574 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
322 | 387579 | Wing-1 Flat No 1809 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 317 | 387574 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
323 | 387580 | Wing-1 Flat No 1809 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 317 | 387574 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
324 | 387581 | Wing-1 Flat No 1809 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 317 | 387574 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
325 | 387582 | Wing-1 Flat No 1809 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 317 | 387574 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
326 | 387591 | Wing-1 Flat No 1809 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 317 | 387574 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
327 | 387600 | Wing-1 Flat No 1809 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 317 | 387574 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
328 | 451224 | Wing-1 Flat No 1809 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 317 | 387574 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
329 | 387601 | Wing-1 19th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
330 | 387602 | Wing-1 Flat No 1901 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
331 | 387603 | Wing-1 Flat No 1901 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 330 | 387602 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
332 | 387604 | Wing-1 Flat No 1901 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 330 | 387602 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
333 | 387605 | Wing-1 Flat No 1901 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 330 | 387602 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
334 | 387606 | Wing-1 Flat No 1901 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 330 | 387602 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
335 | 387607 | Wing-1 Flat No 1901 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 330 | 387602 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
336 | 387608 | Wing-1 Flat No 1901 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 330 | 387602 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
337 | 387609 | Wing-1 Flat No 1901 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 330 | 387602 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
338 | 387610 | Wing-1 Flat No 1901 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 330 | 387602 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
339 | 387683 | Wing-1 Flat No 1901 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 330 | 387602 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
340 | 387692 | Wing-1 Flat No 1901 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 330 | 387602 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
341 | 451225 | Wing-1 Flat No 1901 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 330 | 387602 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
342 | 387611 | Wing-1 Flat No 1902 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
343 | 387612 | Wing-1 Flat No 1902 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 342 | 387611 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
344 | 387613 | Wing-1 Flat No 1902 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 342 | 387611 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
345 | 387614 | Wing-1 Flat No 1902 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 342 | 387611 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
346 | 387615 | Wing-1 Flat No 1902 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 342 | 387611 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
347 | 387616 | Wing-1 Flat No 1902 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 342 | 387611 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
348 | 387617 | Wing-1 Flat No 1902 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 342 | 387611 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
349 | 387618 | Wing-1 Flat No 1902 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 342 | 387611 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
350 | 387619 | Wing-1 Flat No 1902 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 342 | 387611 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
351 | 387684 | Wing-1 Flat No 1902 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 342 | 387611 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
352 | 387693 | Wing-1 Flat No 1902 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 342 | 387611 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
353 | 451226 | Wing-1 Flat No 1902 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 342 | 387611 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
354 | 387620 | Wing-1 Flat No 1903 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
355 | 387621 | Wing-1 Flat No 1903 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 354 | 387620 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
356 | 387622 | Wing-1 Flat No 1903 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 354 | 387620 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
357 | 387623 | Wing-1 Flat No 1903 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 354 | 387620 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
358 | 387624 | Wing-1 Flat No 1903 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 354 | 387620 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
359 | 387625 | Wing-1 Flat No 1903 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 354 | 387620 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
360 | 387626 | Wing-1 Flat No 1903 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 354 | 387620 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
361 | 387627 | Wing-1 Flat No 1903 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 354 | 387620 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
362 | 387628 | Wing-1 Flat No 1903 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 354 | 387620 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
363 | 387685 | Wing-1 Flat No 1903 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 354 | 387620 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
364 | 387694 | Wing-1 Flat No 1903 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 354 | 387620 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
365 | 451227 | Wing-1 Flat No 1903 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 354 | 387620 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
366 | 387629 | Wing-1 Flat No 1904 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
367 | 387630 | Wing-1 Flat No 1904 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 366 | 387629 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
368 | 387631 | Wing-1 Flat No 1904 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 366 | 387629 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
369 | 387632 | Wing-1 Flat No 1904 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 366 | 387629 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
370 | 387633 | Wing-1 Flat No 1904 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 366 | 387629 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
371 | 387634 | Wing-1 Flat No 1904 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 366 | 387629 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
372 | 387635 | Wing-1 Flat No 1904 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 366 | 387629 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
373 | 387636 | Wing-1 Flat No 1904 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 366 | 387629 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
374 | 387637 | Wing-1 Flat No 1904 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 366 | 387629 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
375 | 387686 | Wing-1 Flat No 1904 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 366 | 387629 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
376 | 387695 | Wing-1 Flat No 1904 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 366 | 387629 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
377 | 451228 | Wing-1 Flat No 1904 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 366 | 387629 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
378 | 387638 | Wing-1 Flat No 1905 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
379 | 387639 | Wing-1 Flat No 1905 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 378 | 387638 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
380 | 387640 | Wing-1 Flat No 1905 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 378 | 387638 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
381 | 387641 | Wing-1 Flat No 1905 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 378 | 387638 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
382 | 387642 | Wing-1 Flat No 1905 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 378 | 387638 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
383 | 387643 | Wing-1 Flat No 1905 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 378 | 387638 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
384 | 387644 | Wing-1 Flat No 1905 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 378 | 387638 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
385 | 387645 | Wing-1 Flat No 1905 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 378 | 387638 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
386 | 387646 | Wing-1 Flat No 1905 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 378 | 387638 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
387 | 387687 | Wing-1 Flat No 1905 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 378 | 387638 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
388 | 387696 | Wing-1 Flat No 1905 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 378 | 387638 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
389 | 451229 | Wing-1 Flat No 1905 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 378 | 387638 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
390 | 387647 | Wing-1 Flat No 1906 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
391 | 387648 | Wing-1 Flat No 1906 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 390 | 387647 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
392 | 387649 | Wing-1 Flat No 1906 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 390 | 387647 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
393 | 387650 | Wing-1 Flat No 1906 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 390 | 387647 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
394 | 387651 | Wing-1 Flat No 1906 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 390 | 387647 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
395 | 387652 | Wing-1 Flat No 1906 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 390 | 387647 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
396 | 387653 | Wing-1 Flat No 1906 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 390 | 387647 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
397 | 387654 | Wing-1 Flat No 1906 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 390 | 387647 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
398 | 387655 | Wing-1 Flat No 1906 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 390 | 387647 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
399 | 387688 | Wing-1 Flat No 1906 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 390 | 387647 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
400 | 387697 | Wing-1 Flat No 1906 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 390 | 387647 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
401 | 451230 | Wing-1 Flat No 1906 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 390 | 387647 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
402 | 387656 | Wing-1 Flat No 1907 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
403 | 387657 | Wing-1 Flat No 1907 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 402 | 387656 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
404 | 387658 | Wing-1 Flat No 1907 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 402 | 387656 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
405 | 387659 | Wing-1 Flat No 1907 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 402 | 387656 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
406 | 387660 | Wing-1 Flat No 1907 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 402 | 387656 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
407 | 387661 | Wing-1 Flat No 1907 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 402 | 387656 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
408 | 387662 | Wing-1 Flat No 1907 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 402 | 387656 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
409 | 387663 | Wing-1 Flat No 1907 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 402 | 387656 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
410 | 387664 | Wing-1 Flat No 1907 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 402 | 387656 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
411 | 387689 | Wing-1 Flat No 1907 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 402 | 387656 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
412 | 387698 | Wing-1 Flat No 1907 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 402 | 387656 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
413 | 451231 | Wing-1 Flat No 1907 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 402 | 387656 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
414 | 387665 | Wing-1 Flat No 1908 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
415 | 387666 | Wing-1 Flat No 1908 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 414 | 387665 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
416 | 387667 | Wing-1 Flat No 1908 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 414 | 387665 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
417 | 387668 | Wing-1 Flat No 1908 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 414 | 387665 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
418 | 387669 | Wing-1 Flat No 1908 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 414 | 387665 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
419 | 387670 | Wing-1 Flat No 1908 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 414 | 387665 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
420 | 387671 | Wing-1 Flat No 1908 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 414 | 387665 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
421 | 387672 | Wing-1 Flat No 1908 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 414 | 387665 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
422 | 387673 | Wing-1 Flat No 1908 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 414 | 387665 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
423 | 387690 | Wing-1 Flat No 1908 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 414 | 387665 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
424 | 387699 | Wing-1 Flat No 1908 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 414 | 387665 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
425 | 451232 | Wing-1 Flat No 1908 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 414 | 387665 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
426 | 387674 | Wing-1 Flat No 1909 | NA | 0.0000 | 0.0000 | 329 | 387601 | 31 | 0 | [6 empty] | 0.0000
427 | 387675 | Wing.1 Flat No 1909 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 426 | 387674 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
428 | 387676 | Wing-1 Flat No 1909 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 426 | 387674 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
429 | 387677 | Wing-1 Flat No 1909 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 426 | 387674 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
430 | 387678 | Wing-1 Flat No 1909 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 426 | 387674 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
431 | 387679 | Wing-1 Flat No 1909 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 426 | 387674 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
432 | 387680 | Wing-1 Flat No 1909 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 426 | 387674 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
433 | 387681 | Wing-1 Flat No 1909 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 426 | 387674 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
434 | 387682 | Wing-1 Flat No 1909 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 426 | 387674 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
435 | 387691 | Wing-1 Flat No 1909 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 426 | 387674 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
436 | 387700 | Wing-1 Flat No 1909 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 426 | 387674 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
437 | 451233 | Wing-1 Flat No 1909 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 426 | 387674 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
438 | 387701 | Wing-1 20th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
439 | 387702 | Wing-1 Flat No 2001 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
440 | 387703 | Wing-1 Flat No 2001 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 439 | 387702 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
441 | 387704 | Wing-1 Flat No 2001 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 439 | 387702 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
442 | 387705 | Wing-1 Flat No 2001 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 439 | 387702 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
443 | 387706 | Wing-1 Flat No 2001 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 439 | 387702 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
444 | 387707 | Wing-1 Flat No 2001 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 439 | 387702 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
445 | 387708 | Wing-1 Flat No 2001 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 439 | 387702 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
446 | 387709 | Wing-1 Flat No 2001 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 439 | 387702 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
447 | 387710 | Wing-1 Flat No 2001 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 439 | 387702 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
448 | 387783 | Wing-1 Flat No 2001 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 439 | 387702 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
449 | 387792 | Wing-1 Flat No 2001 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 439 | 387702 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
450 | 451234 | Wing-1 Flat No 2001 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 439 | 387702 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
451 | 387711 | Wing-1 Flat No 2002 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
452 | 387712 | Wing-1 Flat No 2002 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 451 | 387711 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
453 | 387713 | Wing-1 Flat No 2002 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 451 | 387711 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
454 | 387714 | Wing-1 Flat No 2002 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 451 | 387711 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
455 | 387715 | Wing-1 Flat No 2002 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 451 | 387711 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
456 | 387716 | Wing-1 Flat No 2002 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 451 | 387711 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
457 | 387717 | Wing-1 Flat No 2002 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 451 | 387711 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
458 | 387718 | Wing-1 Flat No 2002 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 451 | 387711 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
459 | 387719 | Wing-1 Flat No 2002 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 451 | 387711 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
460 | 387784 | Wing-1 Flat No 2002 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 451 | 387711 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
461 | 387793 | Wing-1 Flat No 2002 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 451 | 387711 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
462 | 451235 | Wing-1 Flat No 2002 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 451 | 387711 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
463 | 387720 | Wing-1 Flat No 2003 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
464 | 387721 | Wing-1 Flat No 2003 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 463 | 387720 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
465 | 387722 | Wing-1 Flat No 2003 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 463 | 387720 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
466 | 387723 | Wing-1 Flat No 2003 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 463 | 387720 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
467 | 387724 | Wing-1 Flat No 2003 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 463 | 387720 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
468 | 387725 | Wing-1 Flat No 2003 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 463 | 387720 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
469 | 387726 | Wing-1 Flat No 2003 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 463 | 387720 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
470 | 387727 | Wing-1 Flat No 2003 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 463 | 387720 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
471 | 387728 | Wing-1 Flat No 2003 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 463 | 387720 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
472 | 387785 | Wing-1 Flat No 2003 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 463 | 387720 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
473 | 387794 | Wing-1 Flat No 2003 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 463 | 387720 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
474 | 451236 | Wing-1 Flat No 2003 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 463 | 387720 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
475 | 387729 | Wing-1 Flat No 2004 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
476 | 387730 | Wing-1 Flat No 2004 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 475 | 387729 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
477 | 387731 | Wing-1 Flat No 2004 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 475 | 387729 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
478 | 387732 | Wing-1 Flat No 2004 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 475 | 387729 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
479 | 387733 | Wing-1 Flat No 2004 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 475 | 387729 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
480 | 387734 | Wing-1 Flat No 2004 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 475 | 387729 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
481 | 387735 | Wing-1 Flat No 2004 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 475 | 387729 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
482 | 387736 | Wing-1 Flat No 2004 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 475 | 387729 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
483 | 387737 | Wing-1 Flat No 2004 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 475 | 387729 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
484 | 387786 | Wing-1 Flat No 2004 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 475 | 387729 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
485 | 387795 | Wing-1 Flat No 2004 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 475 | 387729 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
486 | 451237 | Wing-1 Flat No 2004 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 475 | 387729 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
487 | 387738 | Wing-1 Flat No 2005 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
488 | 387739 | Wing-1 Flat No 2005 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 487 | 387738 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
489 | 387740 | Wing-1 Flat No 2005 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 487 | 387738 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
490 | 387741 | Wing-1 Flat No 2005 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 487 | 387738 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
491 | 387742 | Wing-1 Flat No 2005 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 487 | 387738 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
492 | 387743 | Wing-1 Flat No 2005 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 487 | 387738 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
493 | 387744 | Wing-1 Flat No 2005 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 487 | 387738 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
494 | 387745 | Wing-1 Flat No 2005 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 487 | 387738 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
495 | 387746 | Wing-1 Flat No 2005 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 487 | 387738 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
496 | 387787 | Wing-1 Flat No 2005 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 487 | 387738 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
497 | 387796 | Wing-1 Flat No 2005 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 487 | 387738 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
498 | 451238 | Wing-1 Flat No 2005 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 487 | 387738 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
499 | 387747 | Wing-1 Flat No 2006 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
500 | 387748 | Wing-1 Flat No 2006 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 499 | 387747 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
501 | 387749 | Wing-1 Flat No 2006 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 499 | 387747 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
502 | 387750 | Wing-1 Flat No 2006 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 499 | 387747 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
503 | 387751 | Wing-1 Flat No 2006 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 499 | 387747 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
504 | 387752 | Wing-1 Flat No 2006 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 499 | 387747 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
505 | 387753 | Wing-1 Flat No 2006 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 499 | 387747 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
506 | 387754 | Wing-1 Flat No 2006 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 499 | 387747 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
507 | 387755 | Wing-1 Flat No 2006 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 499 | 387747 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
508 | 387788 | Wing-1 Flat No 2006 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 499 | 387747 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
509 | 387797 | Wing-1 Flat No 2006 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 499 | 387747 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
510 | 451239 | Wing-1 Flat No 2006 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 499 | 387747 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
511 | 387756 | Wing-1 Flat No 2007 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
512 | 387757 | Wing-1 Flat No 2007 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 511 | 387756 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
513 | 387758 | Wing-1 Flat No 2007 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 511 | 387756 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
514 | 387759 | Wing-1 Flat No 2007 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 511 | 387756 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
515 | 387760 | Wing-1 Flat No 2007 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 511 | 387756 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
516 | 387761 | Wing-1 Flat No 2007 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 511 | 387756 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
517 | 387762 | Wing-1 Flat No 2007 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 511 | 387756 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
518 | 387763 | Wing-1 Flat No 2007 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 511 | 387756 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
519 | 387764 | Wing-1 Flat No 2007 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 511 | 387756 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
520 | 387789 | Wing-1 Flat No 2007 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 511 | 387756 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
521 | 387798 | Wing-1 Flat No 2007 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 511 | 387756 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
522 | 451240 | Wing-1 Flat No 2007 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 511 | 387756 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
523 | 387765 | Wing-1 Flat No 2008 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
524 | 387766 | Wing-1 Flat No 2008 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 523 | 387765 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
525 | 387767 | Wing-1 Flat No 2008 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 523 | 387765 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
526 | 387768 | Wing-1 Flat No 2008 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 523 | 387765 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
527 | 387769 | Wing-1 Flat No 2008 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 523 | 387765 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
528 | 387770 | Wing-1 Flat No 2008 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 523 | 387765 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
529 | 387771 | Wing-1 Flat No 2008 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 523 | 387765 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
530 | 387772 | Wing-1 Flat No 2008 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 523 | 387765 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
531 | 387773 | Wing-1 Flat No 2008 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 523 | 387765 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
532 | 387790 | Wing-1 Flat No 2008 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 523 | 387765 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
533 | 387799 | Wing-1 Flat No 2008 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 523 | 387765 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
534 | 451241 | Wing-1 Flat No 2008 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 523 | 387765 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
535 | 387774 | Wing-1 Flat No 2009 | NA | 0.0000 | 0.0000 | 438 | 387701 | 31 | 0 | [6 empty] | 0.0000
536 | 387775 | Wing.1 Flat No 2009 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 535 | 387774 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
537 | 387776 | Wing-1 Flat No 2009 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 535 | 387774 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
538 | 387777 | Wing-1 Flat No 2009 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 535 | 387774 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
539 | 387778 | Wing-1 Flat No 2009 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 535 | 387774 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
540 | 387779 | Wing-1 Flat No 2009 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 535 | 387774 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
541 | 387780 | Wing-1 Flat No 2009 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 535 | 387774 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
542 | 387781 | Wing-1 Flat No 2009 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 535 | 387774 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
543 | 387782 | Wing-1 Flat No 2009 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 535 | 387774 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
544 | 387791 | Wing-1 Flat No 2009 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 535 | 387774 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
545 | 387800 | Wing-1 Flat No 2009 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 535 | 387774 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
546 | 451242 | Wing-1 Flat No 2009 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 535 | 387774 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
547 | 388501 | Wing-1 21st Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
548 | 388502 | Wing-1 Flat No 2101 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
549 | 388503 | Wing-1 Flat No 2101 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 548 | 388502 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
550 | 388504 | Wing-1 Flat No 2101 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 548 | 388502 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
551 | 388505 | Wing-1 Flat No 2101 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 548 | 388502 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
552 | 388506 | Wing-1 Flat No 2101 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 548 | 388502 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
553 | 388507 | Wing-1 Flat No 2101 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 548 | 388502 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
554 | 388508 | Wing-1 Flat No 2101 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 548 | 388502 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
555 | 388509 | Wing-1 Flat No 2101 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 548 | 388502 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
556 | 388510 | Wing-1 Flat No 2101 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 548 | 388502 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
557 | 388583 | Wing-1 Flat No 2101 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 548 | 388502 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
558 | 388592 | Wing-1 Flat No 2101 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 548 | 388502 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
559 | 451243 | Wing-1 Flat No 2101 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 548 | 388502 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
560 | 388511 | Wing-1 Flat No 2102 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
561 | 388512 | Wing-1 Flat No 2102 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 560 | 388511 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
562 | 388513 | Wing-1 Flat No 2102 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 560 | 388511 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
563 | 388514 | Wing-1 Flat No 2102 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 560 | 388511 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
564 | 388515 | Wing-1 Flat No 2102 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 560 | 388511 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
565 | 388516 | Wing-1 Flat No 2102 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 560 | 388511 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
566 | 388517 | Wing-1 Flat No 2102 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 560 | 388511 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
567 | 388518 | Wing-1 Flat No 2102 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 560 | 388511 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
568 | 388519 | Wing-1 Flat No 2102 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 560 | 388511 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
569 | 388584 | Wing-1 Flat No 2102 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 560 | 388511 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
570 | 388593 | Wing-1 Flat No 2102 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 560 | 388511 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
571 | 451244 | Wing-1 Flat No 2102 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 560 | 388511 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
572 | 388520 | Wing-1 Flat No 2103 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
573 | 388521 | Wing-1 Flat No 2103 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 572 | 388520 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
574 | 388522 | Wing-1 Flat No 2103 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 572 | 388520 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
575 | 388523 | Wing-1 Flat No 2103 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 572 | 388520 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
576 | 388524 | Wing-1 Flat No 2103 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 572 | 388520 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
577 | 388525 | Wing-1 Flat No 2103 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 572 | 388520 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
578 | 388526 | Wing-1 Flat No 2103 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 572 | 388520 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
579 | 388527 | Wing-1 Flat No 2103 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 572 | 388520 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
580 | 388528 | Wing-1 Flat No 2103 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 572 | 388520 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
581 | 388585 | Wing-1 Flat No 2103 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 572 | 388520 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
582 | 388594 | Wing-1 Flat No 2103 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 572 | 388520 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
583 | 451245 | Wing-1 Flat No 2103 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 572 | 388520 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
584 | 388529 | Wing-1 Flat No 2104 (Refuge Area) | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
585 | 388530 | Wing-1 Flat No 2104 Int Flat Chemical Grouting Work | Sq.Ft | 552.9600 | 552.9600 | 584 | 388529 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
586 | 388531 | Wing-1 Flat No 2104 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 584 | 388529 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
587 | 388532 | Wing-1 Flat No 2104 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 584 | 388529 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
588 | 388533 | Wing-1 Flat No 2104 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 584 | 388529 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
589 | 388534 | Wing-1 Flat No 2104 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 584 | 388529 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
590 | 388535 | Wing-1 Flat No 2104 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 584 | 388529 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
591 | 388536 | Wing-1 Flat No 2104 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 584 | 388529 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
592 | 388537 | Wing-1 Flat No 2104 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 584 | 388529 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
593 | 388586 | Wing-1 Flat No 2104 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 584 | 388529 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
594 | 388595 | Wing-1 Flat No 2104 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 584 | 388529 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
595 | 451246 | Wing-1 Flat No 2104 (Refuge Area) Bore Packing + Perma Eazee | Flat | 1.0000 | 1.0000 | 584 | 388529 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
596 | 388538 | Wing-1 Flat No 2105 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
597 | 388539 | Wing-1 Flat No 2105 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 596 | 388538 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
598 | 388540 | Wing-1 Flat No 2105 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 596 | 388538 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
599 | 388541 | Wing-1 Flat No 2105 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 596 | 388538 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
600 | 388542 | Wing-1 Flat No 2105 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 596 | 388538 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
601 | 388543 | Wing-1 Flat No 2105 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 596 | 388538 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
602 | 388544 | Wing-1 Flat No 2105 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 596 | 388538 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
603 | 388545 | Wing-1 Flat No 2105 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 596 | 388538 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
604 | 388546 | Wing-1 Flat No 2105 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 596 | 388538 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
605 | 388587 | Wing-1 Flat No 2105 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 596 | 388538 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
606 | 388596 | Wing-1 Flat No 2105 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 596 | 388538 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
607 | 451247 | Wing-1 Flat No 2105 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 596 | 388538 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
608 | 388547 | Wing-1 Flat No 2106 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
609 | 388548 | Wing-1 Flat No 2106 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 608 | 388547 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
610 | 388549 | Wing-1 Flat No 2106 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 608 | 388547 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
611 | 388550 | Wing-1 Flat No 2106 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 608 | 388547 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
612 | 388551 | Wing-1 Flat No 2106 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 608 | 388547 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
613 | 388552 | Wing-1 Flat No 2106 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 608 | 388547 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
614 | 388553 | Wing-1 Flat No 2106 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 608 | 388547 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
615 | 388554 | Wing-1 Flat No 2106 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 608 | 388547 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
616 | 388555 | Wing-1 Flat No 2106 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 608 | 388547 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
617 | 388588 | Wing-1 Flat No 2106 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 608 | 388547 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
618 | 388597 | Wing-1 Flat No 2106 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 608 | 388547 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
619 | 451248 | Wing-1 Flat No 2106 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 608 | 388547 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
620 | 388556 | Wing-1 Flat No 2107 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
621 | 388557 | Wing-1 Flat No 2107 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 620 | 388556 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
622 | 388558 | Wing-1 Flat No 2107 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 620 | 388556 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
623 | 388559 | Wing-1 Flat No 2107 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 620 | 388556 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
624 | 388560 | Wing-1 Flat No 2107 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 620 | 388556 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
625 | 388561 | Wing-1 Flat No 2107 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 620 | 388556 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
626 | 388562 | Wing-1 Flat No 2107 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 620 | 388556 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
627 | 388563 | Wing-1 Flat No 2107 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 620 | 388556 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
628 | 388564 | Wing-1 Flat No 2107 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 620 | 388556 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
629 | 388589 | Wing-1 Flat No 2107 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 620 | 388556 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
630 | 388598 | Wing-1 Flat No 2107 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 620 | 388556 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
631 | 451249 | Wing-1 Flat No 2107 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 620 | 388556 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
632 | 388565 | Wing-1 Flat No 2108 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
633 | 388566 | Wing-1 Flat No 2108 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 632 | 388565 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
634 | 388567 | Wing-1 Flat No 2108 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 632 | 388565 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
635 | 388568 | Wing-1 Flat No 2108 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 632 | 388565 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
636 | 388569 | Wing-1 Flat No 2108 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 632 | 388565 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
637 | 388570 | Wing-1 Flat No 2108 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 632 | 388565 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
638 | 388571 | Wing-1 Flat No 2108 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 632 | 388565 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
639 | 388572 | Wing-1 Flat No 2108 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 632 | 388565 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
640 | 388573 | Wing-1 Flat No 2108 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 632 | 388565 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
641 | 388590 | Wing-1 Flat No 2108 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 632 | 388565 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
642 | 388599 | Wing-1 Flat No 2108 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 632 | 388565 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
643 | 451250 | Wing-1 Flat No 2108 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 632 | 388565 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
644 | 388574 | Wing-1 Flat No 2109 | NA | 0.0000 | 0.0000 | 547 | 388501 | 31 | 0 | [6 empty] | 0.0000
645 | 388575 | Wing.1 Flat No 2109 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 644 | 388574 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
646 | 388576 | Wing-1 Flat No 2109 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 644 | 388574 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
647 | 388577 | Wing-1 Flat No 2109 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 644 | 388574 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
648 | 388578 | Wing-1 Flat No 2109 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 644 | 388574 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
649 | 388579 | Wing-1 Flat No 2109 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 644 | 388574 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
650 | 388580 | Wing-1 Flat No 2109 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 644 | 388574 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
651 | 388581 | Wing-1 Flat No 2109 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 644 | 388574 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
652 | 388582 | Wing-1 Flat No 2109 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 644 | 388574 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
653 | 388591 | Wing-1 Flat No 2109 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 644 | 388574 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
654 | 388600 | Wing-1 Flat No 2109 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 644 | 388574 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
655 | 451251 | Wing-1 Flat No 2109 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 644 | 388574 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
656 | 387801 | Wing-1 22nd Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
657 | 387802 | Wing-1 Flat No 2201 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
658 | 387803 | Wing-1 Flat No 2201 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 657 | 387802 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
659 | 387804 | Wing-1 Flat No 2201 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 657 | 387802 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
660 | 387805 | Wing-1 Flat No 2201 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 657 | 387802 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
661 | 387806 | Wing-1 Flat No 2201 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 657 | 387802 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
662 | 387807 | Wing-1 Flat No 2201 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 657 | 387802 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
663 | 387808 | Wing-1 Flat No 2201 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 657 | 387802 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
664 | 387809 | Wing-1 Flat No 2201 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 657 | 387802 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
665 | 387810 | Wing-1 Flat No 2201 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 657 | 387802 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
666 | 387883 | Wing-1 Flat No 2201 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 657 | 387802 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
667 | 387892 | Wing-1 Flat No 2201 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 657 | 387802 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
668 | 451252 | Wing-1 Flat No 2201 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 657 | 387802 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
669 | 387811 | Wing-1 Flat No 2202 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
670 | 387812 | Wing-1 Flat No 2202 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 669 | 387811 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
671 | 387813 | Wing-1 Flat No 2202 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 669 | 387811 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
672 | 387814 | Wing-1 Flat No 2202 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 669 | 387811 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
673 | 387815 | Wing-1 Flat No 2202 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 669 | 387811 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
674 | 387816 | Wing-1 Flat No 2202 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 669 | 387811 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
675 | 387817 | Wing-1 Flat No 2202 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 669 | 387811 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
676 | 387818 | Wing-1 Flat No 2202 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 669 | 387811 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
677 | 387819 | Wing-1 Flat No 2202 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 669 | 387811 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
678 | 387884 | Wing-1 Flat No 2202 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 669 | 387811 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
679 | 387893 | Wing-1 Flat No 2202 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 669 | 387811 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
680 | 451253 | Wing-1 Flat No 2202 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 669 | 387811 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
681 | 387820 | Wing-1 Flat No 2203 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
682 | 387821 | Wing-1 Flat No 2203 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 681 | 387820 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
683 | 387822 | Wing-1 Flat No 2203 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 681 | 387820 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
684 | 387823 | Wing-1 Flat No 2203 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 681 | 387820 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
685 | 387824 | Wing-1 Flat No 2203 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 681 | 387820 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
686 | 387825 | Wing-1 Flat No 2203 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 681 | 387820 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
687 | 387826 | Wing-1 Flat No 2203 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 681 | 387820 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
688 | 387827 | Wing-1 Flat No 2203 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 681 | 387820 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
689 | 387828 | Wing-1 Flat No 2203 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 681 | 387820 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
690 | 387885 | Wing-1 Flat No 2203 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 681 | 387820 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
691 | 387894 | Wing-1 Flat No 2203 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 681 | 387820 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
692 | 451254 | Wing-1 Flat No 2203 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 681 | 387820 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
693 | 387829 | Wing-1 Flat No 2204 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
694 | 387830 | Wing-1 Flat No 2204 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 693 | 387829 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
695 | 387831 | Wing-1 Flat No 2204 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 693 | 387829 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
696 | 387832 | Wing-1 Flat No 2204 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 693 | 387829 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
697 | 387833 | Wing-1 Flat No 2204 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 693 | 387829 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
698 | 387834 | Wing-1 Flat No 2204 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 693 | 387829 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
699 | 387835 | Wing-1 Flat No 2204 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 693 | 387829 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
700 | 387836 | Wing-1 Flat No 2204 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 693 | 387829 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
701 | 387837 | Wing-1 Flat No 2204 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 693 | 387829 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
702 | 387886 | Wing-1 Flat No 2204 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 693 | 387829 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
703 | 387895 | Wing-1 Flat No 2204 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 693 | 387829 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
704 | 451255 | Wing-1 Flat No 2204 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 693 | 387829 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
705 | 387838 | Wing-1 Flat No 2205 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
706 | 387839 | Wing-1 Flat No 2205 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 705 | 387838 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
707 | 387840 | Wing-1 Flat No 2205 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 705 | 387838 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
708 | 387841 | Wing-1 Flat No 2205 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 705 | 387838 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
709 | 387842 | Wing-1 Flat No 2205 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 705 | 387838 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
710 | 387843 | Wing-1 Flat No 2205 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 705 | 387838 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
711 | 387844 | Wing-1 Flat No 2205 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 705 | 387838 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
712 | 387845 | Wing-1 Flat No 2205 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 705 | 387838 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
713 | 387846 | Wing-1 Flat No 2205 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 705 | 387838 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
714 | 387887 | Wing-1 Flat No 2205 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 705 | 387838 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
715 | 387896 | Wing-1 Flat No 2205 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 705 | 387838 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
716 | 451256 | Wing-1 Flat No 2205 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 705 | 387838 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
717 | 387847 | Wing-1 Flat No 2206 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
718 | 387848 | Wing-1 Flat No 2206 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 717 | 387847 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
719 | 387849 | Wing-1 Flat No 2206 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 717 | 387847 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
720 | 387850 | Wing-1 Flat No 2206 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 717 | 387847 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
721 | 387851 | Wing-1 Flat No 2206 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 717 | 387847 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
722 | 387852 | Wing-1 Flat No 2206 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 717 | 387847 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
723 | 387853 | Wing-1 Flat No 2206 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 717 | 387847 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
724 | 387854 | Wing-1 Flat No 2206 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 717 | 387847 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
725 | 387855 | Wing-1 Flat No 2206 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 717 | 387847 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
726 | 387888 | Wing-1 Flat No 2206 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 717 | 387847 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
727 | 387897 | Wing-1 Flat No 2206 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 717 | 387847 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
728 | 451257 | Wing-1 Flat No 2206 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 717 | 387847 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
729 | 387856 | Wing-1 Flat No 2207 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
730 | 387857 | Wing-1 Flat No 2207 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 729 | 387856 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
731 | 387858 | Wing-1 Flat No 2207 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 729 | 387856 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
732 | 387859 | Wing-1 Flat No 2207 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 729 | 387856 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
733 | 387860 | Wing-1 Flat No 2207 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 729 | 387856 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
734 | 387861 | Wing-1 Flat No 2207 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 729 | 387856 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
735 | 387862 | Wing-1 Flat No 2207 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 729 | 387856 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
736 | 387863 | Wing-1 Flat No 2207 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 729 | 387856 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
737 | 387864 | Wing-1 Flat No 2207 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 729 | 387856 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
738 | 387889 | Wing-1 Flat No 2207 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 729 | 387856 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
739 | 387898 | Wing-1 Flat No 2207 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 729 | 387856 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
740 | 451258 | Wing-1 Flat No 2207 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 729 | 387856 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
741 | 387865 | Wing-1 Flat No 2208 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
742 | 387866 | Wing-1 Flat No 2208 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 741 | 387865 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
743 | 387867 | Wing-1 Flat No 2208 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 741 | 387865 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
744 | 387868 | Wing-1 Flat No 2208 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 741 | 387865 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
745 | 387869 | Wing-1 Flat No 2208 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 741 | 387865 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
746 | 387870 | Wing-1 Flat No 2208 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 741 | 387865 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
747 | 387871 | Wing-1 Flat No 2208 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 741 | 387865 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
748 | 387872 | Wing-1 Flat No 2208 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 741 | 387865 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
749 | 387873 | Wing-1 Flat No 2208 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 741 | 387865 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
750 | 387890 | Wing-1 Flat No 2208 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 741 | 387865 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
751 | 387899 | Wing-1 Flat No 2208 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 741 | 387865 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
752 | 451259 | Wing-1 Flat No 2208 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 741 | 387865 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
753 | 387874 | Wing-1 Flat No 2209 | NA | 0.0000 | 0.0000 | 656 | 387801 | 31 | 0 | [6 empty] | 0.0000
754 | 387875 | Wing.1 Flat No 2209 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 753 | 387874 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
755 | 387876 | Wing-1 Flat No 2209 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 753 | 387874 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
756 | 387877 | Wing-1 Flat No 2209 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 753 | 387874 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
757 | 387878 | Wing-1 Flat No 2209 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 753 | 387874 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
758 | 387879 | Wing-1 Flat No 2209 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 753 | 387874 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
759 | 387880 | Wing-1 Flat No 2209 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 753 | 387874 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
760 | 387881 | Wing-1 Flat No 2209 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 753 | 387874 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
761 | 387882 | Wing-1 Flat No 2209 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 753 | 387874 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
762 | 387891 | Wing-1 Flat No 2209 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 753 | 387874 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
763 | 387900 | Wing-1 Flat No 2209 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 753 | 387874 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
764 | 451260 | Wing-1 Flat No 2209 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 753 | 387874 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
765 | 387901 | Wing-1 23rd Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
766 | 387902 | Wing-1 Flat No 2301 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
767 | 387903 | Wing-1 Flat No 2301 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 766 | 387902 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
768 | 387904 | Wing-1 Flat No 2301 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 766 | 387902 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
769 | 387905 | Wing-1 Flat No 2301 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 766 | 387902 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
770 | 387906 | Wing-1 Flat No 2301 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 766 | 387902 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
771 | 387907 | Wing-1 Flat No 2301 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 766 | 387902 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
772 | 387908 | Wing-1 Flat No 2301 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 766 | 387902 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
773 | 387909 | Wing-1 Flat No 2301 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 766 | 387902 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
774 | 387910 | Wing-1 Flat No 2301 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 766 | 387902 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
775 | 387983 | Wing-1 Flat No 2301 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 766 | 387902 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
776 | 387992 | Wing-1 Flat No 2301 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 766 | 387902 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
777 | 451261 | Wing-1 Flat No 2301 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 766 | 387902 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
778 | 387911 | Wing-1 Flat No 2302 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
779 | 387912 | Wing-1 Flat No 2302 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 778 | 387911 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
780 | 387913 | Wing-1 Flat No 2302 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 778 | 387911 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
781 | 387914 | Wing-1 Flat No 2302 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 778 | 387911 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
782 | 387915 | Wing-1 Flat No 2302 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 778 | 387911 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
783 | 387916 | Wing-1 Flat No 2302 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 778 | 387911 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
784 | 387917 | Wing-1 Flat No 2302 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 778 | 387911 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
785 | 387918 | Wing-1 Flat No 2302 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 778 | 387911 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
786 | 387919 | Wing-1 Flat No 2302 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 778 | 387911 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
787 | 387984 | Wing-1 Flat No 2302 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 778 | 387911 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
788 | 387993 | Wing-1 Flat No 2302 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 778 | 387911 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
789 | 451262 | Wing-1 Flat No 2302 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 778 | 387911 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
790 | 387920 | Wing-1 Flat No 2303 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
791 | 387921 | Wing-1 Flat No 2303 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 790 | 387920 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
792 | 387922 | Wing-1 Flat No 2303 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 790 | 387920 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
793 | 387923 | Wing-1 Flat No 2303 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 790 | 387920 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
794 | 387924 | Wing-1 Flat No 2303 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 790 | 387920 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
795 | 387925 | Wing-1 Flat No 2303 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 790 | 387920 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
796 | 387926 | Wing-1 Flat No 2303 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 790 | 387920 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
797 | 387927 | Wing-1 Flat No 2303 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 790 | 387920 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
798 | 387928 | Wing-1 Flat No 2303 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 790 | 387920 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
799 | 387985 | Wing-1 Flat No 2303 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 790 | 387920 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
800 | 387994 | Wing-1 Flat No 2303 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 790 | 387920 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
801 | 451263 | Wing-1 Flat No 2303 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 790 | 387920 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
802 | 387929 | Wing-1 Flat No 2304 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
803 | 387930 | Wing-1 Flat No 2304 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 802 | 387929 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
804 | 387931 | Wing-1 Flat No 2304 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 802 | 387929 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
805 | 387932 | Wing-1 Flat No 2304 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 802 | 387929 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
806 | 387933 | Wing-1 Flat No 2304 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 802 | 387929 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
807 | 387934 | Wing-1 Flat No 2304 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 802 | 387929 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
808 | 387935 | Wing-1 Flat No 2304 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 802 | 387929 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
809 | 387936 | Wing-1 Flat No 2304 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 802 | 387929 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
810 | 387937 | Wing-1 Flat No 2304 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 802 | 387929 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
811 | 387986 | Wing-1 Flat No 2304 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 802 | 387929 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
812 | 387995 | Wing-1 Flat No 2304 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 802 | 387929 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
813 | 451264 | Wing-1 Flat No 2304 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 802 | 387929 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
814 | 387938 | Wing-1 Flat No 2305 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
815 | 387939 | Wing-1 Flat No 2305 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 814 | 387938 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
816 | 387940 | Wing-1 Flat No 2305 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 814 | 387938 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
817 | 387941 | Wing-1 Flat No 2305 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 814 | 387938 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
818 | 387942 | Wing-1 Flat No 2305 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 814 | 387938 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
819 | 387943 | Wing-1 Flat No 2305 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 814 | 387938 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
820 | 387944 | Wing-1 Flat No 2305 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 814 | 387938 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
821 | 387945 | Wing-1 Flat No 2305 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 814 | 387938 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
822 | 387946 | Wing-1 Flat No 2305 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 814 | 387938 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
823 | 387987 | Wing-1 Flat No 2305 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 814 | 387938 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
824 | 387996 | Wing-1 Flat No 2305 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 814 | 387938 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
825 | 451265 | Wing-1 Flat No 2305 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 814 | 387938 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
826 | 387947 | Wing-1 Flat No 2306 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
827 | 387948 | Wing-1 Flat No 2306 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 826 | 387947 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
828 | 387949 | Wing-1 Flat No 2306 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 826 | 387947 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
829 | 387950 | Wing-1 Flat No 2306 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 826 | 387947 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
830 | 387951 | Wing-1 Flat No 2306 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 826 | 387947 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
831 | 387952 | Wing-1 Flat No 2306 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 826 | 387947 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
832 | 387953 | Wing-1 Flat No 2306 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 826 | 387947 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
833 | 387954 | Wing-1 Flat No 2306 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 826 | 387947 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
834 | 387955 | Wing-1 Flat No 2306 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 826 | 387947 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
835 | 387988 | Wing-1 Flat No 2306 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 826 | 387947 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
836 | 387997 | Wing-1 Flat No 2306 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 826 | 387947 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
837 | 451266 | Wing-1 Flat No 2306 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 826 | 387947 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
838 | 387956 | Wing-1 Flat No 2307 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
839 | 387957 | Wing-1 Flat No 2307 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 838 | 387956 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
840 | 387958 | Wing-1 Flat No 2307 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 838 | 387956 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
841 | 387959 | Wing-1 Flat No 2307 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 838 | 387956 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
842 | 387960 | Wing-1 Flat No 2307 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 838 | 387956 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
843 | 387961 | Wing-1 Flat No 2307 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 838 | 387956 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
844 | 387962 | Wing-1 Flat No 2307 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 838 | 387956 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
845 | 387963 | Wing-1 Flat No 2307 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 838 | 387956 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
846 | 387964 | Wing-1 Flat No 2307 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 838 | 387956 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
847 | 387989 | Wing-1 Flat No 2307 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 838 | 387956 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
848 | 387998 | Wing-1 Flat No 2307 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 838 | 387956 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
849 | 451267 | Wing-1 Flat No 2307 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 838 | 387956 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
850 | 387965 | Wing-1 Flat No 2308 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
851 | 387966 | Wing-1 Flat No 2308 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 850 | 387965 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
852 | 387967 | Wing-1 Flat No 2308 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 850 | 387965 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
853 | 387968 | Wing-1 Flat No 2308 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 850 | 387965 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
854 | 387969 | Wing-1 Flat No 2308 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 850 | 387965 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
855 | 387970 | Wing-1 Flat No 2308 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 850 | 387965 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
856 | 387971 | Wing-1 Flat No 2308 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 850 | 387965 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
857 | 387972 | Wing-1 Flat No 2308 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 850 | 387965 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
858 | 387973 | Wing-1 Flat No 2308 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 850 | 387965 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
859 | 387990 | Wing-1 Flat No 2308 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 850 | 387965 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
860 | 387999 | Wing-1 Flat No 2308 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 850 | 387965 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
861 | 451268 | Wing-1 Flat No 2308 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 850 | 387965 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
862 | 387974 | Wing-1 Flat No 2309 | NA | 0.0000 | 0.0000 | 765 | 387901 | 31 | 0 | [6 empty] | 0.0000
863 | 387975 | Wing.1 Flat No 2309 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 862 | 387974 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
864 | 387976 | Wing-1 Flat No 2309 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 862 | 387974 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
865 | 387977 | Wing-1 Flat No 2309 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 862 | 387974 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
866 | 387978 | Wing-1 Flat No 2309 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 862 | 387974 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
867 | 387979 | Wing-1 Flat No 2309 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 862 | 387974 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
868 | 387980 | Wing-1 Flat No 2309 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 862 | 387974 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
869 | 387981 | Wing-1 Flat No 2309 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 862 | 387974 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
870 | 387982 | Wing-1 Flat No 2309 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 862 | 387974 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
871 | 387991 | Wing-1 Flat No 2309 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 862 | 387974 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
872 | 388000 | Wing-1 Flat No 2309 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 862 | 387974 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
873 | 451269 | Wing-1 Flat No 2309 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 862 | 387974 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
874 | 388001 | Wing-1 24th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
875 | 388002 | Wing-1 Flat No 2401 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
876 | 388003 | Wing-1 Flat No 2401 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 875 | 388002 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
877 | 388004 | Wing-1 Flat No 2401 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 875 | 388002 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
878 | 388005 | Wing-1 Flat No 2401 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 875 | 388002 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
879 | 388006 | Wing-1 Flat No 2401 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 875 | 388002 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
880 | 388007 | Wing-1 Flat No 2401 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 875 | 388002 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
881 | 388008 | Wing-1 Flat No 2401 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 875 | 388002 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
882 | 388009 | Wing-1 Flat No 2401 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 875 | 388002 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
883 | 388010 | Wing-1 Flat No 2401 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 875 | 388002 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
884 | 388083 | Wing-1 Flat No 2401 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 875 | 388002 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
885 | 388092 | Wing-1 Flat No 2401 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 875 | 388002 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
886 | 451270 | Wing-1 Flat No 2401 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 875 | 388002 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
887 | 388011 | Wing-1 Flat No 2402 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
888 | 388012 | Wing-1 Flat No 2402 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 887 | 388011 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
889 | 388013 | Wing-1 Flat No 2402 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 887 | 388011 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
890 | 388014 | Wing-1 Flat No 2402 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 887 | 388011 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
891 | 388015 | Wing-1 Flat No 2402 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 887 | 388011 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
892 | 388016 | Wing-1 Flat No 2402 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 887 | 388011 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
893 | 388017 | Wing-1 Flat No 2402 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 887 | 388011 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
894 | 388018 | Wing-1 Flat No 2402 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 887 | 388011 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
895 | 388019 | Wing-1 Flat No 2402 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 887 | 388011 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
896 | 388084 | Wing-1 Flat No 2402 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 887 | 388011 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
897 | 388093 | Wing-1 Flat No 2402 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 887 | 388011 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
898 | 451271 | Wing-1 Flat No 2402 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 887 | 388011 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
899 | 388020 | Wing-1 Flat No 2403 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
900 | 388021 | Wing-1 Flat No 2403 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 899 | 388020 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
901 | 388022 | Wing-1 Flat No 2403 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 899 | 388020 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
902 | 388023 | Wing-1 Flat No 2403 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 899 | 388020 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
903 | 388024 | Wing-1 Flat No 2403 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 899 | 388020 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
904 | 388025 | Wing-1 Flat No 2403 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 899 | 388020 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
905 | 388026 | Wing-1 Flat No 2403 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 899 | 388020 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
906 | 388027 | Wing-1 Flat No 2403 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 899 | 388020 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
907 | 388028 | Wing-1 Flat No 2403 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 899 | 388020 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
908 | 388085 | Wing-1 Flat No 2403 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 899 | 388020 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
909 | 388094 | Wing-1 Flat No 2403 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 899 | 388020 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
910 | 451272 | Wing-1 Flat No 2403 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 899 | 388020 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
911 | 388029 | Wing-1 Flat No 2404 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
912 | 388030 | Wing-1 Flat No 2404 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 911 | 388029 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
913 | 388031 | Wing-1 Flat No 2404 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 911 | 388029 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
914 | 388032 | Wing-1 Flat No 2404 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 911 | 388029 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
915 | 388033 | Wing-1 Flat No 2404 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 911 | 388029 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
916 | 388034 | Wing-1 Flat No 2404 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 911 | 388029 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
917 | 388035 | Wing-1 Flat No 2404 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 911 | 388029 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
918 | 388036 | Wing-1 Flat No 2404 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 911 | 388029 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
919 | 388037 | Wing-1 Flat No 2404 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 911 | 388029 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
920 | 388086 | Wing-1 Flat No 2404 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 911 | 388029 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
921 | 388095 | Wing-1 Flat No 2404 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 911 | 388029 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
922 | 451273 | Wing-1 Flat No 2404 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 911 | 388029 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
923 | 388038 | Wing-1 Flat No 2405 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
924 | 388039 | Wing-1 Flat No 2405 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 923 | 388038 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
925 | 388040 | Wing-1 Flat No 2405 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 923 | 388038 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
926 | 388041 | Wing-1 Flat No 2405 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 923 | 388038 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
927 | 388042 | Wing-1 Flat No 2405 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 923 | 388038 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
928 | 388043 | Wing-1 Flat No 2405 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 923 | 388038 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
929 | 388044 | Wing-1 Flat No 2405 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 923 | 388038 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
930 | 388045 | Wing-1 Flat No 2405 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 923 | 388038 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
931 | 388046 | Wing-1 Flat No 2405 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 923 | 388038 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
932 | 388087 | Wing-1 Flat No 2405 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 923 | 388038 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
933 | 388096 | Wing-1 Flat No 2405 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 923 | 388038 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
934 | 451274 | Wing-1 Flat No 2405 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 923 | 388038 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
935 | 388047 | Wing-1 Flat No 2406 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
936 | 388048 | Wing-1 Flat No 2406 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 935 | 388047 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
937 | 388049 | Wing-1 Flat No 2406 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 935 | 388047 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
938 | 388050 | Wing-1 Flat No 2406 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 935 | 388047 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
939 | 388051 | Wing-1 Flat No 2406 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 935 | 388047 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
940 | 388052 | Wing-1 Flat No 2406 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 935 | 388047 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
941 | 388053 | Wing-1 Flat No 2406 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 935 | 388047 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
942 | 388054 | Wing-1 Flat No 2406 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 935 | 388047 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
943 | 388055 | Wing-1 Flat No 2406 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 935 | 388047 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
944 | 388088 | Wing-1 Flat No 2406 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 935 | 388047 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
945 | 388097 | Wing-1 Flat No 2406 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 935 | 388047 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
946 | 451275 | Wing-1 Flat No 2406 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 935 | 388047 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
947 | 388056 | Wing-1 Flat No 2407 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
948 | 388057 | Wing-1 Flat No 2407 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 947 | 388056 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
949 | 388058 | Wing-1 Flat No 2407 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 947 | 388056 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
950 | 388059 | Wing-1 Flat No 2407 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 947 | 388056 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
951 | 388060 | Wing-1 Flat No 2407 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 947 | 388056 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
952 | 388061 | Wing-1 Flat No 2407 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 947 | 388056 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
953 | 388062 | Wing-1 Flat No 2407 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 947 | 388056 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
954 | 388063 | Wing-1 Flat No 2407 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 947 | 388056 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
955 | 388064 | Wing-1 Flat No 2407 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 947 | 388056 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
956 | 388089 | Wing-1 Flat No 2407 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 947 | 388056 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
957 | 388098 | Wing-1 Flat No 2407 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 947 | 388056 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
958 | 451276 | Wing-1 Flat No 2407 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 947 | 388056 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
959 | 388065 | Wing-1 Flat No 2408 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
960 | 388066 | Wing-1 Flat No 2408 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 959 | 388065 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
961 | 388067 | Wing-1 Flat No 2408 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 959 | 388065 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
962 | 388068 | Wing-1 Flat No 2408 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 959 | 388065 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
963 | 388069 | Wing-1 Flat No 2408 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 959 | 388065 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
964 | 388070 | Wing-1 Flat No 2408 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 959 | 388065 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
965 | 388071 | Wing-1 Flat No 2408 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 959 | 388065 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
966 | 388072 | Wing-1 Flat No 2408 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 959 | 388065 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
967 | 388073 | Wing-1 Flat No 2408 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 959 | 388065 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
968 | 388090 | Wing-1 Flat No 2408 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 959 | 388065 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
969 | 388099 | Wing-1 Flat No 2408 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 959 | 388065 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
970 | 451277 | Wing-1 Flat No 2408 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 959 | 388065 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
971 | 388074 | Wing-1 Flat No 2409 | NA | 0.0000 | 0.0000 | 874 | 388001 | 31 | 0 | [6 empty] | 0.0000
972 | 388075 | Wing.1 Flat No 2409 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 971 | 388074 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
973 | 388076 | Wing-1 Flat No 2409 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 971 | 388074 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
974 | 388077 | Wing-1 Flat No 2409 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 971 | 388074 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
975 | 388078 | Wing-1 Flat No 2409 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 971 | 388074 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
976 | 388079 | Wing-1 Flat No 2409 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 971 | 388074 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
977 | 388080 | Wing-1 Flat No 2409 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 971 | 388074 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
978 | 388081 | Wing-1 Flat No 2409 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 971 | 388074 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
979 | 388082 | Wing-1 Flat No 2409 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 971 | 388074 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
980 | 388091 | Wing-1 Flat No 2409 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 971 | 388074 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
981 | 388100 | Wing-1 Flat No 2409 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 971 | 388074 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
982 | 451278 | Wing-1 Flat No 2409 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 971 | 388074 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
983 | 388101 | Wing-1 25th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
984 | 388102 | Wing-1 Flat No 2501 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
985 | 388103 | Wing-1 Flat No 2501 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 984 | 388102 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
986 | 388104 | Wing-1 Flat No 2501 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 984 | 388102 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
987 | 388105 | Wing-1 Flat No 2501 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 984 | 388102 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
988 | 388106 | Wing-1 Flat No 2501 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 984 | 388102 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
989 | 388107 | Wing-1 Flat No 2501 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 984 | 388102 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
990 | 388108 | Wing-1 Flat No 2501 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 984 | 388102 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
991 | 388109 | Wing-1 Flat No 2501 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 984 | 388102 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
992 | 388110 | Wing-1 Flat No 2501 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 984 | 388102 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
993 | 388183 | Wing-1 Flat No 2501 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 984 | 388102 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
994 | 388192 | Wing-1 Flat No 2501 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 984 | 388102 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
995 | 451279 | Wing-1 Flat No 2501 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 984 | 388102 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
996 | 451280 | Wing-1 Flat No 2501 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 984 | 388102 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
997 | 388111 | Wing-1 Flat No 2502 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
998 | 388112 | Wing-1 Flat No 2502 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 997 | 388111 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
999 | 388113 | Wing-1 Flat No 2502 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 997 | 388111 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1000 | 388114 | Wing-1 Flat No 2502 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 997 | 388111 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1001 | 388115 | Wing-1 Flat No 2502 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 997 | 388111 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1002 | 388116 | Wing-1 Flat No 2502 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 997 | 388111 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1003 | 388117 | Wing-1 Flat No 2502 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 997 | 388111 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1004 | 388118 | Wing-1 Flat No 2502 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 997 | 388111 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1005 | 388119 | Wing-1 Flat No 2502 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 997 | 388111 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1006 | 388184 | Wing-1 Flat No 2502 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 997 | 388111 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1007 | 388193 | Wing-1 Flat No 2502 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 997 | 388111 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1008 | 451281 | Wing-1 Flat No 2502 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 997 | 388111 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1009 | 388120 | Wing-1 Flat No 2503 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1010 | 388121 | Wing-1 Flat No 2503 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1009 | 388120 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1011 | 388122 | Wing-1 Flat No 2503 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1009 | 388120 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1012 | 388123 | Wing-1 Flat No 2503 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1009 | 388120 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1013 | 388124 | Wing-1 Flat No 2503 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1009 | 388120 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1014 | 388125 | Wing-1 Flat No 2503 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1009 | 388120 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1015 | 388126 | Wing-1 Flat No 2503 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1009 | 388120 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1016 | 388127 | Wing-1 Flat No 2503 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1009 | 388120 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1017 | 388128 | Wing-1 Flat No 2503 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1009 | 388120 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1018 | 388185 | Wing-1 Flat No 2503 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1009 | 388120 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1019 | 388194 | Wing-1 Flat No 2503 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1009 | 388120 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1020 | 451282 | Wing-1 Flat No 2503 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1009 | 388120 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1021 | 388129 | Wing-1 Flat No 2504 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1022 | 388130 | Wing-1 Flat No 2504 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1021 | 388129 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1023 | 388131 | Wing-1 Flat No 2504 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1021 | 388129 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1024 | 388132 | Wing-1 Flat No 2504 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1021 | 388129 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1025 | 388133 | Wing-1 Flat No 2504 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1021 | 388129 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1026 | 388134 | Wing-1 Flat No 2504 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1021 | 388129 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1027 | 388135 | Wing-1 Flat No 2504 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1021 | 388129 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1028 | 388136 | Wing-1 Flat No 2504 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1021 | 388129 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1029 | 388137 | Wing-1 Flat No 2504 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1021 | 388129 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1030 | 388186 | Wing-1 Flat No 2504 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1021 | 388129 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1031 | 388195 | Wing-1 Flat No 2504 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1021 | 388129 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1032 | 451283 | Wing-1 Flat No 2504 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1021 | 388129 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1033 | 388138 | Wing-1 Flat No 2505 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1034 | 388139 | Wing-1 Flat No 2505 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1033 | 388138 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1035 | 388140 | Wing-1 Flat No 2505 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1033 | 388138 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1036 | 388141 | Wing-1 Flat No 2505 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1033 | 388138 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1037 | 388142 | Wing-1 Flat No 2505 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1033 | 388138 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1038 | 388143 | Wing-1 Flat No 2505 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1033 | 388138 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1039 | 388144 | Wing-1 Flat No 2505 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1033 | 388138 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1040 | 388145 | Wing-1 Flat No 2505 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1033 | 388138 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1041 | 388146 | Wing-1 Flat No 2505 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1033 | 388138 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1042 | 388187 | Wing-1 Flat No 2505 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1033 | 388138 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1043 | 388196 | Wing-1 Flat No 2505 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1033 | 388138 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1044 | 451284 | Wing-1 Flat No 2505 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1033 | 388138 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1045 | 388147 | Wing-1 Flat No 2506 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1046 | 388148 | Wing-1 Flat No 2506 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1045 | 388147 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1047 | 388149 | Wing-1 Flat No 2506 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1045 | 388147 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1048 | 388150 | Wing-1 Flat No 2506 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1045 | 388147 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1049 | 388151 | Wing-1 Flat No 2506 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1045 | 388147 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1050 | 388152 | Wing-1 Flat No 2506 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1045 | 388147 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1051 | 388153 | Wing-1 Flat No 2506 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1045 | 388147 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1052 | 388154 | Wing-1 Flat No 2506 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1045 | 388147 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1053 | 388155 | Wing-1 Flat No 2506 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1045 | 388147 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1054 | 388188 | Wing-1 Flat No 2506 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1045 | 388147 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1055 | 388197 | Wing-1 Flat No 2506 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1045 | 388147 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1056 | 451285 | Wing-1 Flat No 2506 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1045 | 388147 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1057 | 388156 | Wing-1 Flat No 2507 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1058 | 388157 | Wing-1 Flat No 2507 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1057 | 388156 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1059 | 388158 | Wing-1 Flat No 2507 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1057 | 388156 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1060 | 388159 | Wing-1 Flat No 2507 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1057 | 388156 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1061 | 388160 | Wing-1 Flat No 2507 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1057 | 388156 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1062 | 388161 | Wing-1 Flat No 2507 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1057 | 388156 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1063 | 388162 | Wing-1 Flat No 2507 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1057 | 388156 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1064 | 388163 | Wing-1 Flat No 2507 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1057 | 388156 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1065 | 388164 | Wing-1 Flat No 2507 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1057 | 388156 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1066 | 388189 | Wing-1 Flat No 2507 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1057 | 388156 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1067 | 388198 | Wing-1 Flat No 2507 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1057 | 388156 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1068 | 451286 | Wing-1 Flat No 2507 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1057 | 388156 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1069 | 388165 | Wing-1 Flat No 2508 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1070 | 388166 | Wing-1 Flat No 2508 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1069 | 388165 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1071 | 388167 | Wing-1 Flat No 2508 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1069 | 388165 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1072 | 388168 | Wing-1 Flat No 2508 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1069 | 388165 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1073 | 388169 | Wing-1 Flat No 2508 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1069 | 388165 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1074 | 388170 | Wing-1 Flat No 2508 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1069 | 388165 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1075 | 388171 | Wing-1 Flat No 2508 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1069 | 388165 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1076 | 388172 | Wing-1 Flat No 2508 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1069 | 388165 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1077 | 388173 | Wing-1 Flat No 2508 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1069 | 388165 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1078 | 388190 | Wing-1 Flat No 2508 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1069 | 388165 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1079 | 388199 | Wing-1 Flat No 2508 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1069 | 388165 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1080 | 451287 | Wing-1 Flat No 2508 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1069 | 388165 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1081 | 388174 | Wing-1 Flat No 2509 | NA | 0.0000 | 0.0000 | 983 | 388101 | 31 | 0 | [6 empty] | 0.0000
1082 | 388175 | Wing.1 Flat No 2509 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1081 | 388174 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1083 | 388176 | Wing-1 Flat No 2509 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1081 | 388174 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1084 | 388177 | Wing-1 Flat No 2509 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1081 | 388174 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1085 | 388178 | Wing-1 Flat No 2509 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1081 | 388174 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1086 | 388179 | Wing-1 Flat No 2509 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1081 | 388174 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1087 | 388180 | Wing-1 Flat No 2509 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1081 | 388174 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1088 | 388181 | Wing-1 Flat No 2509 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1081 | 388174 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1089 | 388182 | Wing-1 Flat No 2509 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1081 | 388174 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1090 | 388191 | Wing-1 Flat No 2509 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1081 | 388174 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1091 | 388200 | Wing-1 Flat No 2509 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1081 | 388174 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1092 | 451288 | Wing-1 Flat No 2509 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1081 | 388174 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1093 | 388601 | Wing-1 26th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
1094 | 388602 | Wing-1 Flat No 2601 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1095 | 388603 | Wing-1 Flat No 2601 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 1094 | 388602 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1096 | 388604 | Wing-1 Flat No 2601 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1094 | 388602 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1097 | 388605 | Wing-1 Flat No 2601 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1094 | 388602 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1098 | 388606 | Wing-1 Flat No 2601 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1094 | 388602 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1099 | 388607 | Wing-1 Flat No 2601 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1094 | 388602 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1100 | 388608 | Wing-1 Flat No 2601 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1094 | 388602 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1101 | 388609 | Wing-1 Flat No 2601 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1094 | 388602 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1102 | 388610 | Wing-1 Flat No 2601 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1094 | 388602 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1103 | 388683 | Wing-1 Flat No 2601 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1094 | 388602 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1104 | 388692 | Wing-1 Flat No 2601 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1094 | 388602 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1105 | 451289 | Wing-1 Flat No 2601 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1094 | 388602 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1106 | 388611 | Wing-1 Flat No 2602 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1107 | 388612 | Wing-1 Flat No 2602 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1106 | 388611 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1108 | 388613 | Wing-1 Flat No 2602 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1106 | 388611 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1109 | 388614 | Wing-1 Flat No 2602 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1106 | 388611 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1110 | 388615 | Wing-1 Flat No 2602 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1106 | 388611 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1111 | 388616 | Wing-1 Flat No 2602 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1106 | 388611 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1112 | 388617 | Wing-1 Flat No 2602 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1106 | 388611 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1113 | 388618 | Wing-1 Flat No 2602 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1106 | 388611 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1114 | 388619 | Wing-1 Flat No 2602 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1106 | 388611 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1115 | 388684 | Wing-1 Flat No 2602 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1106 | 388611 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1116 | 388693 | Wing-1 Flat No 2602 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1106 | 388611 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1117 | 451290 | Wing-1 Flat No 2602 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1106 | 388611 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1118 | 388620 | Wing-1 Flat No 2603 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1119 | 388621 | Wing-1 Flat No 2603 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1118 | 388620 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1120 | 388622 | Wing-1 Flat No 2603 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1118 | 388620 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1121 | 388623 | Wing-1 Flat No 2603 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1118 | 388620 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1122 | 388624 | Wing-1 Flat No 2603 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1118 | 388620 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1123 | 388625 | Wing-1 Flat No 2603 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1118 | 388620 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1124 | 388626 | Wing-1 Flat No 2603 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1118 | 388620 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1125 | 388627 | Wing-1 Flat No 2603 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1118 | 388620 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1126 | 388628 | Wing-1 Flat No 2603 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1118 | 388620 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1127 | 388685 | Wing-1 Flat No 2603 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1118 | 388620 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1128 | 388694 | Wing-1 Flat No 2603 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1118 | 388620 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1129 | 451291 | Wing-1 Flat No 2603 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1118 | 388620 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1130 | 388629 | Wing-1 Flat No 2604 (Refuge Area) | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1131 | 388630 | Wing-1 Flat No 2604 Int Flat Chemical Grouting Work | Sq.Ft | 552.9600 | 552.9600 | 1130 | 388629 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1132 | 388631 | Wing-1 Flat No 2604 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1130 | 388629 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1133 | 388632 | Wing-1 Flat No 2604 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1130 | 388629 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1134 | 388633 | Wing-1 Flat No 2604 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1130 | 388629 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1135 | 388634 | Wing-1 Flat No 2604 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1130 | 388629 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1136 | 388635 | Wing-1 Flat No 2604 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1130 | 388629 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1137 | 388636 | Wing-1 Flat No 2604 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1130 | 388629 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1138 | 388637 | Wing-1 Flat No 2604 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1130 | 388629 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1139 | 388686 | Wing-1 Flat No 2604 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1130 | 388629 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1140 | 388695 | Wing-1 Flat No 2604 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1130 | 388629 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1141 | 451292 | Wing-1 Flat No 2604 (Refuge Area) Bore Packing + Perma Eazee | Flat | 1.0000 | 1.0000 | 1130 | 388629 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1142 | 388638 | Wing-1 Flat No 2605 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1143 | 388639 | Wing-1 Flat No 2605 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1142 | 388638 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1144 | 388640 | Wing-1 Flat No 2605 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1142 | 388638 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1145 | 388641 | Wing-1 Flat No 2605 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1142 | 388638 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1146 | 388642 | Wing-1 Flat No 2605 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1142 | 388638 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1147 | 388643 | Wing-1 Flat No 2605 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1142 | 388638 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1148 | 388644 | Wing-1 Flat No 2605 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1142 | 388638 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1149 | 388645 | Wing-1 Flat No 2605 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1142 | 388638 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1150 | 388646 | Wing-1 Flat No 2605 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1142 | 388638 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1151 | 388687 | Wing-1 Flat No 2605 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1142 | 388638 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1152 | 388696 | Wing-1 Flat No 2605 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1142 | 388638 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1153 | 451293 | Wing-1 Flat No 2605 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1142 | 388638 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1154 | 388647 | Wing-1 Flat No 2606 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1155 | 388648 | Wing-1 Flat No 2606 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1154 | 388647 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1156 | 388649 | Wing-1 Flat No 2606 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1154 | 388647 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1157 | 388650 | Wing-1 Flat No 2606 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1154 | 388647 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1158 | 388651 | Wing-1 Flat No 2606 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1154 | 388647 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1159 | 388652 | Wing-1 Flat No 2606 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1154 | 388647 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1160 | 388653 | Wing-1 Flat No 2606 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1154 | 388647 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1161 | 388654 | Wing-1 Flat No 2606 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1154 | 388647 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1162 | 388655 | Wing-1 Flat No 2606 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1154 | 388647 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1163 | 388688 | Wing-1 Flat No 2606 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1154 | 388647 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1164 | 388697 | Wing-1 Flat No 2606 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1154 | 388647 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1165 | 451294 | Wing-1 Flat No 2606 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1154 | 388647 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1166 | 388656 | Wing-1 Flat No 2607 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1167 | 388657 | Wing-1 Flat No 2607 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1166 | 388656 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1168 | 388658 | Wing-1 Flat No 2607 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1166 | 388656 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1169 | 388659 | Wing-1 Flat No 2607 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1166 | 388656 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1170 | 388660 | Wing-1 Flat No 2607 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1166 | 388656 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1171 | 388661 | Wing-1 Flat No 2607 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1166 | 388656 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1172 | 388662 | Wing-1 Flat No 2607 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1166 | 388656 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1173 | 388663 | Wing-1 Flat No 2607 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1166 | 388656 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1174 | 388664 | Wing-1 Flat No 2607 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1166 | 388656 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1175 | 388689 | Wing-1 Flat No 2607 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1166 | 388656 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1176 | 388698 | Wing-1 Flat No 2607 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1166 | 388656 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1177 | 451295 | Wing-1 Flat No 2607 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1166 | 388656 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1178 | 388665 | Wing-1 Flat No 2608 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1179 | 388666 | Wing-1 Flat No 2608 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1178 | 388665 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1180 | 388667 | Wing-1 Flat No 2608 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1178 | 388665 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1181 | 388668 | Wing-1 Flat No 2608 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1178 | 388665 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1182 | 388669 | Wing-1 Flat No 2608 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1178 | 388665 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1183 | 388670 | Wing-1 Flat No 2608 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1178 | 388665 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1184 | 388671 | Wing-1 Flat No 2608 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1178 | 388665 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1185 | 388672 | Wing-1 Flat No 2608 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1178 | 388665 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1186 | 388673 | Wing-1 Flat No 2608 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1178 | 388665 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1187 | 388690 | Wing-1 Flat No 2608 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1178 | 388665 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1188 | 388699 | Wing-1 Flat No 2608 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1178 | 388665 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1189 | 451296 | Wing-1 Flat No 2608 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1178 | 388665 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1190 | 388674 | Wing-1 Flat No 2609 | NA | 0.0000 | 0.0000 | 1093 | 388601 | 31 | 0 | [6 empty] | 0.0000
1191 | 388675 | Wing.1 Flat No 2609 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1190 | 388674 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1192 | 388676 | Wing-1 Flat No 2609 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1190 | 388674 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1193 | 388677 | Wing-1 Flat No 2609 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1190 | 388674 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1194 | 388678 | Wing-1 Flat No 2609 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1190 | 388674 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1195 | 388679 | Wing-1 Flat No 2609 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1190 | 388674 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1196 | 388680 | Wing-1 Flat No 2609 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1190 | 388674 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1197 | 388681 | Wing-1 Flat No 2609 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1190 | 388674 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1198 | 388682 | Wing-1 Flat No 2609 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1190 | 388674 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1199 | 388691 | Wing-1 Flat No 2609 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1190 | 388674 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1200 | 388700 | Wing-1 Flat No 2609 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1190 | 388674 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1201 | 451297 | Wing-1 Flat No 2609 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1190 | 388674 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1202 | 388201 | Wing-1 27th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
1203 | 388202 | Wing-1 Flat No 2701 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1204 | 388203 | Wing-1 Flat No 2701 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 1203 | 388202 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1205 | 388204 | Wing-1 Flat No 2701 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1203 | 388202 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1206 | 388205 | Wing-1 Flat No 2701 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1203 | 388202 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1207 | 388206 | Wing-1 Flat No 2701 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1203 | 388202 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1208 | 388207 | Wing-1 Flat No 2701 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1203 | 388202 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1209 | 388208 | Wing-1 Flat No 2701 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1203 | 388202 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1210 | 388209 | Wing-1 Flat No 2701 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1203 | 388202 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1211 | 388210 | Wing-1 Flat No 2701 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1203 | 388202 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1212 | 388283 | Wing-1 Flat No 2701 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1203 | 388202 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1213 | 388292 | Wing-1 Flat No 2701 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1203 | 388202 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1214 | 451298 | Wing-1 Flat No 2701 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1203 | 388202 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1215 | 388211 | Wing-1 Flat No 2702 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1216 | 388212 | Wing-1 Flat No 2702 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1215 | 388211 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1217 | 388213 | Wing-1 Flat No 2702 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1215 | 388211 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1218 | 388214 | Wing-1 Flat No 2702 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1215 | 388211 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1219 | 388215 | Wing-1 Flat No 2702 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1215 | 388211 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1220 | 388216 | Wing-1 Flat No 2702 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1215 | 388211 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1221 | 388217 | Wing-1 Flat No 2702 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1215 | 388211 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1222 | 388218 | Wing-1 Flat No 2702 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1215 | 388211 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1223 | 388219 | Wing-1 Flat No 2702 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1215 | 388211 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1224 | 388284 | Wing-1 Flat No 2702 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1215 | 388211 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1225 | 388293 | Wing-1 Flat No 2702 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1215 | 388211 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1226 | 451299 | Wing-1 Flat No 2702 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1215 | 388211 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1227 | 388220 | Wing-1 Flat No 2703 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1228 | 388221 | Wing-1 Flat No 2703 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1227 | 388220 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1229 | 388222 | Wing-1 Flat No 2703 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1227 | 388220 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1230 | 388223 | Wing-1 Flat No 2703 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1227 | 388220 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1231 | 388224 | Wing-1 Flat No 2703 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1227 | 388220 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1232 | 388225 | Wing-1 Flat No 2703 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1227 | 388220 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1233 | 388226 | Wing-1 Flat No 2703 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1227 | 388220 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1234 | 388227 | Wing-1 Flat No 2703 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1227 | 388220 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1235 | 388228 | Wing-1 Flat No 2703 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1227 | 388220 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1236 | 388285 | Wing-1 Flat No 2703 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1227 | 388220 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1237 | 388294 | Wing-1 Flat No 2703 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1227 | 388220 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1238 | 451300 | Wing-1 Flat No 2703 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1227 | 388220 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1239 | 388229 | Wing-1 Flat No 2704 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1240 | 388230 | Wing-1 Flat No 2704 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1239 | 388229 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1241 | 388231 | Wing-1 Flat No 2704 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1239 | 388229 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1242 | 388232 | Wing-1 Flat No 2704 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1239 | 388229 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1243 | 388233 | Wing-1 Flat No 2704 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1239 | 388229 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1244 | 388234 | Wing-1 Flat No 2704 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1239 | 388229 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1245 | 388235 | Wing-1 Flat No 2704 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1239 | 388229 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1246 | 388236 | Wing-1 Flat No 2704 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1239 | 388229 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1247 | 388237 | Wing-1 Flat No 2704 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1239 | 388229 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1248 | 388286 | Wing-1 Flat No 2704 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1239 | 388229 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1249 | 388295 | Wing-1 Flat No 2704 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1239 | 388229 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1250 | 451301 | Wing-1 Flat No 2704 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1239 | 388229 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1251 | 388238 | Wing-1 Flat No 2705 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1252 | 388239 | Wing-1 Flat No 2705 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1251 | 388238 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1253 | 388240 | Wing-1 Flat No 2705 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1251 | 388238 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1254 | 388241 | Wing-1 Flat No 2705 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1251 | 388238 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1255 | 388242 | Wing-1 Flat No 2705 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1251 | 388238 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1256 | 388243 | Wing-1 Flat No 2705 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1251 | 388238 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1257 | 388244 | Wing-1 Flat No 2705 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1251 | 388238 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1258 | 388245 | Wing-1 Flat No 2705 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1251 | 388238 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1259 | 388246 | Wing-1 Flat No 2705 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1251 | 388238 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1260 | 388287 | Wing-1 Flat No 2705 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1251 | 388238 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1261 | 388296 | Wing-1 Flat No 2705 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1251 | 388238 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1262 | 451302 | Wing-1 Flat No 2705 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1251 | 388238 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1263 | 388247 | Wing-1 Flat No 2706 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1264 | 388248 | Wing-1 Flat No 2706 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1263 | 388247 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1265 | 388249 | Wing-1 Flat No 2706 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1263 | 388247 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1266 | 388250 | Wing-1 Flat No 2706 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1263 | 388247 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1267 | 388251 | Wing-1 Flat No 2706 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1263 | 388247 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1268 | 388252 | Wing-1 Flat No 2706 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1263 | 388247 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1269 | 388253 | Wing-1 Flat No 2706 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1263 | 388247 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1270 | 388254 | Wing-1 Flat No 2706 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1263 | 388247 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1271 | 388255 | Wing-1 Flat No 2706 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1263 | 388247 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1272 | 388288 | Wing-1 Flat No 2706 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1263 | 388247 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1273 | 388297 | Wing-1 Flat No 2706 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1263 | 388247 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1274 | 451303 | Wing-1 Flat No 2706 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1263 | 388247 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1275 | 388256 | Wing-1 Flat No 2707 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1276 | 388257 | Wing-1 Flat No 2707 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1275 | 388256 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1277 | 388258 | Wing-1 Flat No 2707 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1275 | 388256 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1278 | 388259 | Wing-1 Flat No 2707 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1275 | 388256 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1279 | 388260 | Wing-1 Flat No 2707 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1275 | 388256 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1280 | 388261 | Wing-1 Flat No 2707 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1275 | 388256 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1281 | 388262 | Wing-1 Flat No 2707 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1275 | 388256 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1282 | 388263 | Wing-1 Flat No 2707 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1275 | 388256 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1283 | 388264 | Wing-1 Flat No 2707 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1275 | 388256 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1284 | 388289 | Wing-1 Flat No 2707 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1275 | 388256 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1285 | 388298 | Wing-1 Flat No 2707 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1275 | 388256 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1286 | 451304 | Wing-1 Flat No 2707 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1275 | 388256 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1287 | 388265 | Wing-1 Flat No 2708 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1288 | 388266 | Wing-1 Flat No 2708 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1287 | 388265 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1289 | 388267 | Wing-1 Flat No 2708 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1287 | 388265 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1290 | 388268 | Wing-1 Flat No 2708 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1287 | 388265 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1291 | 388269 | Wing-1 Flat No 2708 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1287 | 388265 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1292 | 388270 | Wing-1 Flat No 2708 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1287 | 388265 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1293 | 388271 | Wing-1 Flat No 2708 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1287 | 388265 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1294 | 388272 | Wing-1 Flat No 2708 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1287 | 388265 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1295 | 388273 | Wing-1 Flat No 2708 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1287 | 388265 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1296 | 388290 | Wing-1 Flat No 2708 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1287 | 388265 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1297 | 388299 | Wing-1 Flat No 2708 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1287 | 388265 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1298 | 451305 | Wing-1 Flat No 2708 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1287 | 388265 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1299 | 388274 | Wing-1 Flat No 2709 | NA | 0.0000 | 0.0000 | 1202 | 388201 | 31 | 0 | [6 empty] | 0.0000
1300 | 388275 | Wing.1 Flat No 2709 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1299 | 388274 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1301 | 388276 | Wing-1 Flat No 2709 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1299 | 388274 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1302 | 388277 | Wing-1 Flat No 2709 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1299 | 388274 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1303 | 388278 | Wing-1 Flat No 2709 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1299 | 388274 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1304 | 388279 | Wing-1 Flat No 2709 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1299 | 388274 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1305 | 388280 | Wing-1 Flat No 2709 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1299 | 388274 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1306 | 388281 | Wing-1 Flat No 2709 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1299 | 388274 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1307 | 388282 | Wing-1 Flat No 2709 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1299 | 388274 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1308 | 388291 | Wing-1 Flat No 2709 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1299 | 388274 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1309 | 388300 | Wing-1 Flat No 2709 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1299 | 388274 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1310 | 451306 | Wing-1 Flat No 2709 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1299 | 388274 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1311 | 388301 | Wing-1 28th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
1312 | 388302 | Wing-1 Flat No 2801 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1313 | 388303 | Wing-1 Flat No 2801 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 1312 | 388302 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1314 | 388304 | Wing-1 Flat No 2801 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1312 | 388302 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1315 | 388305 | Wing-1 Flat No 2801 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1312 | 388302 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1316 | 388306 | Wing-1 Flat No 2801 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1312 | 388302 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1317 | 388307 | Wing-1 Flat No 2801 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1312 | 388302 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1318 | 388308 | Wing-1 Flat No 2801 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1312 | 388302 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1319 | 388309 | Wing-1 Flat No 2801 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1312 | 388302 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1320 | 388310 | Wing-1 Flat No 2801 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1312 | 388302 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1321 | 388383 | Wing-1 Flat No 2801 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1312 | 388302 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1322 | 388392 | Wing-1 Flat No 2801 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1312 | 388302 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1323 | 451307 | Wing-1 Flat No 2801 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1312 | 388302 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1324 | 388311 | Wing-1 Flat No 2802 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1325 | 388312 | Wing-1 Flat No 2802 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1324 | 388311 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1326 | 388313 | Wing-1 Flat No 2802 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1324 | 388311 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1327 | 388314 | Wing-1 Flat No 2802 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1324 | 388311 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1328 | 388315 | Wing-1 Flat No 2802 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1324 | 388311 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1329 | 388316 | Wing-1 Flat No 2802 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1324 | 388311 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1330 | 388317 | Wing-1 Flat No 2802 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1324 | 388311 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1331 | 388318 | Wing-1 Flat No 2802 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1324 | 388311 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1332 | 388319 | Wing-1 Flat No 2802 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1324 | 388311 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1333 | 388384 | Wing-1 Flat No 2802 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1324 | 388311 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1334 | 388393 | Wing-1 Flat No 2802 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1324 | 388311 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1335 | 451308 | Wing-1 Flat No 2802 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1324 | 388311 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1336 | 388320 | Wing-1 Flat No 2803 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1337 | 388321 | Wing-1 Flat No 2803 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1336 | 388320 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1338 | 388322 | Wing-1 Flat No 2803 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1336 | 388320 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1339 | 388323 | Wing-1 Flat No 2803 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1336 | 388320 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1340 | 388324 | Wing-1 Flat No 2803 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1336 | 388320 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1341 | 388325 | Wing-1 Flat No 2803 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1336 | 388320 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1342 | 388326 | Wing-1 Flat No 2803 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1336 | 388320 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1343 | 388327 | Wing-1 Flat No 2803 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1336 | 388320 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1344 | 388328 | Wing-1 Flat No 2803 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1336 | 388320 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1345 | 388385 | Wing-1 Flat No 2803 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1336 | 388320 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1346 | 388394 | Wing-1 Flat No 2803 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1336 | 388320 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1347 | 451457 | Wing-1 Flat No 2803 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1336 | 388320 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1348 | 388329 | Wing-1 Flat No 2804 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1349 | 388330 | Wing-1 Flat No 2804 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1348 | 388329 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1350 | 388331 | Wing-1 Flat No 2804 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1348 | 388329 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1351 | 388332 | Wing-1 Flat No 2804 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1348 | 388329 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1352 | 388333 | Wing-1 Flat No 2804 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1348 | 388329 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1353 | 388334 | Wing-1 Flat No 2804 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1348 | 388329 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1354 | 388335 | Wing-1 Flat No 2804 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1348 | 388329 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1355 | 388336 | Wing-1 Flat No 2804 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1348 | 388329 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1356 | 388337 | Wing-1 Flat No 2804 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1348 | 388329 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1357 | 388386 | Wing-1 Flat No 2804 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1348 | 388329 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1358 | 388395 | Wing-1 Flat No 2804 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1348 | 388329 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1359 | 451458 | Wing-1 Flat No 2804 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1348 | 388329 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1360 | 388338 | Wing-1 Flat No 2805 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1361 | 388339 | Wing-1 Flat No 2805 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1360 | 388338 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1362 | 388340 | Wing-1 Flat No 2805 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1360 | 388338 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1363 | 388341 | Wing-1 Flat No 2805 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1360 | 388338 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1364 | 388342 | Wing-1 Flat No 2805 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1360 | 388338 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1365 | 388343 | Wing-1 Flat No 2805 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1360 | 388338 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1366 | 388344 | Wing-1 Flat No 2805 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1360 | 388338 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1367 | 388345 | Wing-1 Flat No 2805 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1360 | 388338 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1368 | 388346 | Wing-1 Flat No 2805 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1360 | 388338 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1369 | 388387 | Wing-1 Flat No 2805 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1360 | 388338 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1370 | 388396 | Wing-1 Flat No 2805 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1360 | 388338 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1371 | 451459 | Wing-1 Flat No 2805 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1360 | 388338 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1372 | 388347 | Wing-1 Flat No 2806 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1373 | 388348 | Wing-1 Flat No 2806 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1372 | 388347 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1374 | 388349 | Wing-1 Flat No 2806 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1372 | 388347 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1375 | 388350 | Wing-1 Flat No 2806 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1372 | 388347 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1376 | 388351 | Wing-1 Flat No 2806 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1372 | 388347 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1377 | 388352 | Wing-1 Flat No 2806 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1372 | 388347 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1378 | 388353 | Wing-1 Flat No 2806 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1372 | 388347 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1379 | 388354 | Wing-1 Flat No 2806 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1372 | 388347 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1380 | 388355 | Wing-1 Flat No 2806 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1372 | 388347 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1381 | 388388 | Wing-1 Flat No 2806 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1372 | 388347 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1382 | 388397 | Wing-1 Flat No 2806 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1372 | 388347 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1383 | 451460 | Wing-1 Flat No 2806 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1372 | 388347 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1384 | 388356 | Wing-1 Flat No 2807 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1385 | 388357 | Wing-1 Flat No 2807 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1384 | 388356 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1386 | 388358 | Wing-1 Flat No 2807 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1384 | 388356 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1387 | 388359 | Wing-1 Flat No 2807 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1384 | 388356 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1388 | 388360 | Wing-1 Flat No 2807 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1384 | 388356 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1389 | 388361 | Wing-1 Flat No 2807 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1384 | 388356 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1390 | 388362 | Wing-1 Flat No 2807 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1384 | 388356 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1391 | 388363 | Wing-1 Flat No 2807 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1384 | 388356 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1392 | 388364 | Wing-1 Flat No 2807 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1384 | 388356 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1393 | 388389 | Wing-1 Flat No 2807 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1384 | 388356 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1394 | 388398 | Wing-1 Flat No 2807 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1384 | 388356 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1395 | 451461 | Wing-1 Flat No 2807 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1384 | 388356 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1396 | 388365 | Wing-1 Flat No 2808 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1397 | 388366 | Wing-1 Flat No 2808 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1396 | 388365 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1398 | 388367 | Wing-1 Flat No 2808 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1396 | 388365 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1399 | 388368 | Wing-1 Flat No 2808 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1396 | 388365 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1400 | 388369 | Wing-1 Flat No 2808 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1396 | 388365 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1401 | 388370 | Wing-1 Flat No 2808 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1396 | 388365 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1402 | 388371 | Wing-1 Flat No 2808 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1396 | 388365 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1403 | 388372 | Wing-1 Flat No 2808 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1396 | 388365 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1404 | 388373 | Wing-1 Flat No 2808 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1396 | 388365 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1405 | 388390 | Wing-1 Flat No 2808 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1396 | 388365 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1406 | 388399 | Wing-1 Flat No 2808 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1396 | 388365 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1407 | 451462 | Wing-1 Flat No 2808 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1396 | 388365 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1408 | 388374 | Wing-1 Flat No 2809 | NA | 0.0000 | 0.0000 | 1311 | 388301 | 31 | 0 | [6 empty] | 0.0000
1409 | 388375 | Wing.1 Flat No 2809 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1408 | 388374 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1410 | 388376 | Wing-1 Flat No 2809 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1408 | 388374 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1411 | 388377 | Wing-1 Flat No 2809 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1408 | 388374 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1412 | 388378 | Wing-1 Flat No 2809 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1408 | 388374 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1413 | 388379 | Wing-1 Flat No 2809 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1408 | 388374 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1414 | 388380 | Wing-1 Flat No 2809 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1408 | 388374 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1415 | 388381 | Wing-1 Flat No 2809 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1408 | 388374 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1416 | 388382 | Wing-1 Flat No 2809 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1408 | 388374 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1417 | 388391 | Wing-1 Flat No 2809 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1408 | 388374 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1418 | 388400 | Wing-1 Flat No 2809 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1408 | 388374 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1419 | 451463 | Wing-1 Flat No 2809 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1408 | 388374 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1420 | 674189 | Wing-1 29th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
1421 | 674190 | Wing-1 Flat No 2901 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1422 | 674191 | Wing-1 Flat No 2901 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 1421 | 674190 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1423 | 674192 | Wing-1 Flat No 2901 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1421 | 674190 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1424 | 674193 | Wing-1 Flat No 2901 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1421 | 674190 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1425 | 674194 | Wing-1 Flat No 2901 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1421 | 674190 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1426 | 674195 | Wing-1 Flat No 2901 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1421 | 674190 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1427 | 674196 | Wing-1 Flat No 2901 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1421 | 674190 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1428 | 674197 | Wing-1 Flat No 2901 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1421 | 674190 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1429 | 674198 | Wing-1 Flat No 2901 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1421 | 674190 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1430 | 674271 | Wing-1 Flat No 2901 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1421 | 674190 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1431 | 674280 | Wing-1 Flat No 2901 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1421 | 674190 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1432 | 674289 | Wing-1 Flat No 2901 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1421 | 674190 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1433 | 674199 | Wing-1 Flat No 2902 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1434 | 674200 | Wing-1 Flat No 2902 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1433 | 674199 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1435 | 674201 | Wing-1 Flat No 2902 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1433 | 674199 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1436 | 674202 | Wing-1 Flat No 2902 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1433 | 674199 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1437 | 674203 | Wing-1 Flat No 2902 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1433 | 674199 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1438 | 674204 | Wing-1 Flat No 2902 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1433 | 674199 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1439 | 674205 | Wing-1 Flat No 2902 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1433 | 674199 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1440 | 674206 | Wing-1 Flat No 2902 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1433 | 674199 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1441 | 674207 | Wing-1 Flat No 2902 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1433 | 674199 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1442 | 674272 | Wing-1 Flat No 2902 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1433 | 674199 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1443 | 674281 | Wing-1 Flat No 2902 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1433 | 674199 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1444 | 674290 | Wing-1 Flat No 2902 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1433 | 674199 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1445 | 674208 | Wing-1 Flat No 2903 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1446 | 674209 | Wing-1 Flat No 2903 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1445 | 674208 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1447 | 674210 | Wing-1 Flat No 2903 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1445 | 674208 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1448 | 674211 | Wing-1 Flat No 2903 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1445 | 674208 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1449 | 674212 | Wing-1 Flat No 2903 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1445 | 674208 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1450 | 674213 | Wing-1 Flat No 2903 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1445 | 674208 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1451 | 674214 | Wing-1 Flat No 2903 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1445 | 674208 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1452 | 674215 | Wing-1 Flat No 2903 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1445 | 674208 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1453 | 674216 | Wing-1 Flat No 2903 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1445 | 674208 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1454 | 674273 | Wing-1 Flat No 2903 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1445 | 674208 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1455 | 674282 | Wing-1 Flat No 2903 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1445 | 674208 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1456 | 674291 | Wing-1 Flat No 2903 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1445 | 674208 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1457 | 674217 | Wing-1 Flat No 2904 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1458 | 674218 | Wing-1 Flat No 2904 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1457 | 674217 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1459 | 674219 | Wing-1 Flat No 2904 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1457 | 674217 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1460 | 674220 | Wing-1 Flat No 2904 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1457 | 674217 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1461 | 674221 | Wing-1 Flat No 2904 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1457 | 674217 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1462 | 674222 | Wing-1 Flat No 2904 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1457 | 674217 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1463 | 674223 | Wing-1 Flat No 2904 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1457 | 674217 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1464 | 674224 | Wing-1 Flat No 2904 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1457 | 674217 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1465 | 674225 | Wing-1 Flat No 2904 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1457 | 674217 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1466 | 674274 | Wing-1 Flat No 2904 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1457 | 674217 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1467 | 674283 | Wing-1 Flat No 2904 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1457 | 674217 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1468 | 674292 | Wing-1 Flat No 2904 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1457 | 674217 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1469 | 674226 | Wing-1 Flat No 2905 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1470 | 674227 | Wing-1 Flat No 2905 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1469 | 674226 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1471 | 674228 | Wing-1 Flat No 2905 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1469 | 674226 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1472 | 674229 | Wing-1 Flat No 2905 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1469 | 674226 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1473 | 674230 | Wing-1 Flat No 2905 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1469 | 674226 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1474 | 674231 | Wing-1 Flat No 2905 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1469 | 674226 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1475 | 674232 | Wing-1 Flat No 2905 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1469 | 674226 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1476 | 674233 | Wing-1 Flat No 2905 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1469 | 674226 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1477 | 674234 | Wing-1 Flat No 2905 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1469 | 674226 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1478 | 674275 | Wing-1 Flat No 2905 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1469 | 674226 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1479 | 674284 | Wing-1 Flat No 2905 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1469 | 674226 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1480 | 674293 | Wing-1 Flat No 2905 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1469 | 674226 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1481 | 674235 | Wing-1 Flat No 2906 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1482 | 674236 | Wing-1 Flat No 2906 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1481 | 674235 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1483 | 674237 | Wing-1 Flat No 2906 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1481 | 674235 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1484 | 674238 | Wing-1 Flat No 2906 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1481 | 674235 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1485 | 674239 | Wing-1 Flat No 2906 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1481 | 674235 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1486 | 674240 | Wing-1 Flat No 2906 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1481 | 674235 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1487 | 674241 | Wing-1 Flat No 2906 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1481 | 674235 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1488 | 674242 | Wing-1 Flat No 2906 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1481 | 674235 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1489 | 674243 | Wing-1 Flat No 2906 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1481 | 674235 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1490 | 674276 | Wing-1 Flat No 2906 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1481 | 674235 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1491 | 674285 | Wing-1 Flat No 2906 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1481 | 674235 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1492 | 674294 | Wing-1 Flat No 2906 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1481 | 674235 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1493 | 674244 | Wing-1 Flat No 2907 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1494 | 674245 | Wing-1 Flat No 2907 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1493 | 674244 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1495 | 674246 | Wing-1 Flat No 2907 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1493 | 674244 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1496 | 674247 | Wing-1 Flat No 2907 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1493 | 674244 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1497 | 674248 | Wing-1 Flat No 2907 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1493 | 674244 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1498 | 674249 | Wing-1 Flat No 2907 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1493 | 674244 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1499 | 674250 | Wing-1 Flat No 2907 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1493 | 674244 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1500 | 674251 | Wing-1 Flat No 2907 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1493 | 674244 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1501 | 674252 | Wing-1 Flat No 2907 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1493 | 674244 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1502 | 674277 | Wing-1 Flat No 2907 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1493 | 674244 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1503 | 674286 | Wing-1 Flat No 2907 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1493 | 674244 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1504 | 674295 | Wing-1 Flat No 2907 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1493 | 674244 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1505 | 674253 | Wing-1 Flat No 2908 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1506 | 674254 | Wing-1 Flat No 2908 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1505 | 674253 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1507 | 674255 | Wing-1 Flat No 2908 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1505 | 674253 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1508 | 674256 | Wing-1 Flat No 2908 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1505 | 674253 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1509 | 674257 | Wing-1 Flat No 2908 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1505 | 674253 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1510 | 674258 | Wing-1 Flat No 2908 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1505 | 674253 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1511 | 674259 | Wing-1 Flat No 2908 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1505 | 674253 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1512 | 674260 | Wing-1 Flat No 2908 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1505 | 674253 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1513 | 674261 | Wing-1 Flat No 2908 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1505 | 674253 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1514 | 674278 | Wing-1 Flat No 2908 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1505 | 674253 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1515 | 674287 | Wing-1 Flat No 2908 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1505 | 674253 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1516 | 674296 | Wing-1 Flat No 2908 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1505 | 674253 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1517 | 674262 | Wing-1 Flat No 2909 | NA | 0.0000 | 0.0000 | 1420 | 674189 | 31 | 0 | [6 empty] | 0.0000
1518 | 674263 | Wing.1 Flat No 2909 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1517 | 674262 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1519 | 674264 | Wing-1 Flat No 2909 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1517 | 674262 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1520 | 674265 | Wing-1 Flat No 2909 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1517 | 674262 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1521 | 674266 | Wing-1 Flat No 2909 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1517 | 674262 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1522 | 674267 | Wing-1 Flat No 2909 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1517 | 674262 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1523 | 674268 | Wing-1 Flat No 2909 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1517 | 674262 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1524 | 674269 | Wing-1 Flat No 2909 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1517 | 674262 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1525 | 674270 | Wing-1 Flat No 2909 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1517 | 674262 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1526 | 674279 | Wing-1 Flat No 2909 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1517 | 674262 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1527 | 674288 | Wing-1 Flat No 2909 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1517 | 674262 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1528 | 674297 | Wing-1 Flat No 2909 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1517 | 674262 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1529 | 674298 | Wing-1 30th Floor | NA | 0.0000 | 0.0000 | 1 | 674188 | 31 | 0 | [6 empty] | 0.0000
1530 | 674299 | Wing-1 Flat No 3001 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1531 | 674300 | Wing-1 Flat No 3001 Int Flat Chemical Grouting Work | Sq.Ft | 702.3200 | 702.3200 | 1530 | 674299 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1532 | 674301 | Wing-1 Flat No 3001 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1530 | 674299 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1533 | 674302 | Wing-1 Flat No 3001 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1530 | 674299 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1534 | 674303 | Wing-1 Flat No 3001 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1530 | 674299 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1535 | 674304 | Wing-1 Flat No 3001 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1530 | 674299 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1536 | 674305 | Wing-1 Flat No 3001 Utility Chemical Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1530 | 674299 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1537 | 674306 | Wing-1 Flat No 3001 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.1700 | 36.1700 | 1530 | 674299 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1538 | 674307 | Wing-1 Flat No 3001 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1530 | 674299 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1539 | 674380 | Wing-1 Flat No 3001 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1530 | 674299 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1540 | 674389 | Wing-1 Flat No 3001 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1530 | 674299 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1541 | 674398 | Wing-1 Flat No 3001 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1530 | 674299 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1542 | 674308 | Wing-1 Flat No 3002 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1543 | 674309 | Wing-1 Flat No 3002 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1542 | 674308 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1544 | 674310 | Wing-1 Flat No 3002 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1542 | 674308 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1545 | 674311 | Wing-1 Flat No 3002 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1542 | 674308 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1546 | 674312 | Wing-1 Flat No 3002 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1542 | 674308 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1547 | 674313 | Wing-1 Flat No 3002 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1542 | 674308 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1548 | 674314 | Wing-1 Flat No 3002 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1542 | 674308 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1549 | 674315 | Wing-1 Flat No 3002 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1542 | 674308 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1550 | 674316 | Wing-1 Flat No 3002 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1542 | 674308 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1551 | 674381 | Wing-1 Flat No 3002 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1542 | 674308 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1552 | 674390 | Wing-1 Flat No 3002 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1542 | 674308 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1553 | 674399 | Wing-1 Flat No 3002 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1542 | 674308 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1554 | 674317 | Wing-1 Flat No 3003 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1555 | 674318 | Wing-1 Flat No 3003 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1554 | 674317 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1556 | 674319 | Wing-1 Flat No 3003 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1554 | 674317 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1557 | 674320 | Wing-1 Flat No 3003 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1554 | 674317 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1558 | 674321 | Wing-1 Flat No 3003 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1554 | 674317 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1559 | 674322 | Wing-1 Flat No 3003 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1554 | 674317 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1560 | 674323 | Wing-1 Flat No 3003 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1554 | 674317 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1561 | 674324 | Wing-1 Flat No 3003 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1554 | 674317 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1562 | 674325 | Wing-1 Flat No 3003 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1554 | 674317 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1563 | 674382 | Wing-1 Flat No 3003 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1554 | 674317 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1564 | 674391 | Wing-1 Flat No 3003 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1554 | 674317 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1565 | 674400 | Wing-1 Flat No 3003 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1554 | 674317 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1566 | 674326 | Wing-1 Flat No 3004 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1567 | 674327 | Wing-1 Flat No 3004 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1566 | 674326 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1568 | 674328 | Wing-1 Flat No 3004 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1566 | 674326 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1569 | 674329 | Wing-1 Flat No 3004 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1566 | 674326 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1570 | 674330 | Wing-1 Flat No 3004 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1566 | 674326 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1571 | 674331 | Wing-1 Flat No 3004 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1566 | 674326 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1572 | 674332 | Wing-1 Flat No 3004 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1566 | 674326 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1573 | 674333 | Wing-1 Flat No 3004 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1566 | 674326 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1574 | 674334 | Wing-1 Flat No 3004 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1566 | 674326 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1575 | 674383 | Wing-1 Flat No 3004 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1566 | 674326 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1576 | 674392 | Wing-1 Flat No 3004 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1566 | 674326 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1577 | 674401 | Wing-1 Flat No 3004 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1566 | 674326 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1578 | 674335 | Wing-1 Flat No 3005 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1579 | 674336 | Wing-1 Flat No 3005 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1578 | 674335 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1580 | 674337 | Wing-1 Flat No 3005 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1578 | 674335 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1581 | 674338 | Wing-1 Flat No 3005 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1578 | 674335 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1582 | 674339 | Wing-1 Flat No 3005 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1578 | 674335 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1583 | 674340 | Wing-1 Flat No 3005 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1578 | 674335 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1584 | 674341 | Wing-1 Flat No 3005 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1578 | 674335 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1585 | 674342 | Wing-1 Flat No 3005 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1578 | 674335 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1586 | 674343 | Wing-1 Flat No 3005 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1578 | 674335 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1587 | 674384 | Wing-1 Flat No 3005 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1578 | 674335 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1588 | 674393 | Wing-1 Flat No 3005 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1578 | 674335 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1589 | 674402 | Wing-1 Flat No 3005 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1578 | 674335 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1590 | 674344 | Wing-1 Flat No 3006 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1591 | 674345 | Wing-1 Flat No 3006 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1590 | 674344 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1592 | 674346 | Wing-1 Flat No 3006 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1590 | 674344 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1593 | 674347 | Wing-1 Flat No 3006 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1590 | 674344 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1594 | 674348 | Wing-1 Flat No 3006 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1590 | 674344 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1595 | 674349 | Wing-1 Flat No 3006 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1590 | 674344 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1596 | 674350 | Wing-1 Flat No 3006 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1590 | 674344 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1597 | 674351 | Wing-1 Flat No 3006 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1590 | 674344 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1598 | 674352 | Wing-1 Flat No 3006 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1590 | 674344 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1599 | 674385 | Wing-1 Flat No 3006 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1590 | 674344 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1600 | 674394 | Wing-1 Flat No 3006 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1590 | 674344 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1601 | 674403 | Wing-1 Flat No 3006 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1590 | 674344 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1602 | 674353 | Wing-1 Flat No 3007 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1603 | 674354 | Wing-1 Flat No 3007 Int Flat Chemical Grouting Work | Sq.Ft | 711.1500 | 711.1500 | 1602 | 674353 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1604 | 674355 | Wing-1 Flat No 3007 C.Toilet Chemical Coat W/P | Sq.Ft | 33.9100 | 33.9100 | 1602 | 674353 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1605 | 674356 | Wing-1 Flat No 3007 C.Toilet IPS W/P | Sq.Ft | 33.9100 | 33.9100 | 1602 | 674353 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1606 | 674357 | Wing-1 Flat No 3007 M.Toilet Chemical Coat W/P | Sq.Ft | 43.5900 | 43.5900 | 1602 | 674353 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1607 | 674358 | Wing-1 Flat No 3007 M.Toilet IPS W/P | Sq.Ft | 43.5900 | 43.5900 | 1602 | 674353 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1608 | 674359 | Wing-1 Flat No 3007 Utility Chemical Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1602 | 674353 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1609 | 674360 | Wing-1 Flat No 3007 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 35.5200 | 35.5200 | 1602 | 674353 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1610 | 674361 | Wing-1 Flat No 3007 Balcony Chemical Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1602 | 674353 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1611 | 674386 | Wing-1 Flat No 3007 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 54.6100 | 54.6100 | 1602 | 674353 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1612 | 674395 | Wing-1 Flat No 3007 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1602 | 674353 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1613 | 674404 | Wing-1 Flat No 3007 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1602 | 674353 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1614 | 674362 | Wing-1 Flat No 3008 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1615 | 674363 | Wing-1 Flat No 3008 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1614 | 674362 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1616 | 674364 | Wing-1 Flat No 3008 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1614 | 674362 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1617 | 674365 | Wing-1 Flat No 3008 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1614 | 674362 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1618 | 674366 | Wing-1 Flat No 3008 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1614 | 674362 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1619 | 674367 | Wing-1 Flat No 3008 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1614 | 674362 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1620 | 674368 | Wing-1 Flat No 3008 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1614 | 674362 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1621 | 674369 | Wing-1 Flat No 3008 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1614 | 674362 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1622 | 674370 | Wing-1 Flat No 3008 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1614 | 674362 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1623 | 674387 | Wing-1 Flat No 3008 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1614 | 674362 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1624 | 674396 | Wing-1 Flat No 3008 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1614 | 674362 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1625 | 674405 | Wing-1 Flat No 3008 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1614 | 674362 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
1626 | 674371 | Wing-1 Flat No 3009 | NA | 0.0000 | 0.0000 | 1529 | 674298 | 31 | 0 | [6 empty] | 0.0000
1627 | 674372 | Wing.1 Flat No 3009 Int Flat Chemical Grouting Work | Sq.Ft | 537.2500 | 537.2500 | 1626 | 674371 | 4 | 27902 | Int Flat Chemical Grouting Work | [5 empty] | 0.0000
1628 | 674373 | Wing-1 Flat No 3009 C.Toilet Chemical Coat W/P | Sq.Ft | 31.6500 | 31.6500 | 1626 | 674371 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1629 | 674374 | Wing-1 Flat No 3009 C.Toilet IPS W/P | Sq.Ft | 31.6500 | 31.6500 | 1626 | 674371 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1630 | 674375 | Wing-1 Flat No 3009 M.Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 1626 | 674371 | 4 | 27905 | Toilet Chemical Coat W/P | [5 empty] | 0.0000
1631 | 674376 | Wing-1 Flat No 3009 M.Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 1626 | 674371 | 4 | 27901 | Toilet IPS W/P | [5 empty] | 0.0000
1632 | 674377 | Wing-1 Flat No 3009 Utility Chemical Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1626 | 674371 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1633 | 674378 | Wing-1 Flat No 3009 Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.8800 | 34.8800 | 1626 | 674371 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1634 | 674379 | Wing-1 Flat No 3009 Balcony Chemical Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1626 | 674371 | 4 | 27906 | Utility Chemical Coat W/P | [5 empty] | 0.0000
1635 | 674388 | Wing-1 Flat No 3009 Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.3700 | 40.3700 | 1626 | 674371 | 4 | 27913 | Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
1636 | 674397 | Wing-1 Flat No 3009 IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 1626 | 674371 | 4 | 27904 | IPS Seal Pack at Toilet & Balcony Door | [5 empty] | 0.0000
1637 | 674406 | Wing-1 Flat No 3009 Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 1626 | 674371 | 4 | 27903 | Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000