## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work | Selected Group :- Wing-1 Garbage Room Painting Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 674525 | Wing-2 Garbage Room Painting Work | NA | 0.0000 | 0.0000 | 0 | 658598 | 31 | 0 | [6 empty] | 0.0000
2 | 674526 | Wing-2 Podium Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
3 | 674527 | Wing-2 1st Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
4 | 674528 | Wing-2 2nd Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
5 | 674529 | Wing-2 3rd Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
6 | 674530 | Wing-2 4th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
7 | 674531 | Wing-2 5th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
8 | 674532 | Wing-2 6th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
9 | 674533 | Wing-2 7th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
10 | 674534 | Wing-2 8th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
11 | 674535 | Wing-2 9th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
12 | 674536 | Wing-2 10th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
13 | 674537 | Wing-2 11th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
14 | 674538 | Wing-2 12th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
15 | 674539 | Wing-2 13th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
16 | 674540 | Wing-2 14th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
17 | 674541 | Wing-2 15th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
18 | 674542 | Wing-2 16th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
19 | 674543 | Wing-2 17th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
20 | 674544 | Wing-2 18th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
21 | 674545 | Wing-2 19th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
22 | 674546 | Wing-2 20th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
23 | 674547 | Wing-2 21st Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
24 | 674548 | Wing-2 22nd Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
25 | 674549 | Wing-2 23rd Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
26 | 674550 | Wing-2 24th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
27 | 674551 | Wing-2 25th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
28 | 674552 | Wing-2 26th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
29 | 674553 | Wing-2 27th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
30 | 674554 | Wing-2 28th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
31 | 674555 | Wing-2 29th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000
32 | 674556 | Wing-2 30th Floor Garbage Room Painting Work | Sq.Ft | 252.6000 | 252.6000 | 1 | 674525 | 4 | 34980 | Wing-1 Garbage Room Texture Painting | [5 empty] | 0.0000