## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP | Selected Group :- 540 KLD STP
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 532898 | 540 KLD STP | NA | 0.0000 | 0.0000 | 0 | 344000 | 31 | 0 | [6 empty] | 0.0000
2 | 532899 | 540 KLD STP Column Concrete | Cu.Mtrs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32345 | STP Column Concrete | [5 empty] | 0.0000
3 | 532900 | 540 KLD STP Column Steel | Kgs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32346 | STP Column Steel | [5 empty] | 0.0000
4 | 532901 | 540 KLD STP Footing Concrete Work | Cu.Mtrs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32343 | STP Footing Concrete Work | [5 empty] | 0.0000
5 | 532902 | 540 KLD STP Footing Steel | Kgs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32344 | STP Footing Steel | [5 empty] | 0.0000
6 | 532903 | 540 KLD STP Raft Slab Concrete | Cu.Mtrs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32347 | STP Raft Slab Concrete | [5 empty] | 0.0000
7 | 532904 | 540 KLD STP Raft Slab Steel | Kgs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32348 | STP Raft Slab Steel | [5 empty] | 0.0000
8 | 532905 | 540 KLD STP RCC Walls Concrete | Cu.Mtrs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32349 | STP RCC Walls Concrete | [5 empty] | 0.0000
9 | 532906 | 540 KLD STP RCC Walls Steel | Kgs | 0.0000 | 0.0000 | 1 | 532898 | 4 | 32350 | STP RCC Walls Steel | [5 empty] | 0.0000
10 | 534312 | 540 KLD STP RCC Work(L) | Job | 1.0000 | 1.0000 | 1 | 532898 | 4 | 32391 | STP RCC Work(L) | [5 empty] | 0.0000
11 | 535081 | 540 KLD STP excavation work | Cu.Mtrs | 1.0000 | 1.0000 | 1 | 532898 | 4 | 32456 | excavation work for STP | [5 empty] | 0.0000
12 | 535462 | 540KLD STP W/P Work | NA | 0.0000 | 0.0000 | 1 | 532898 | 31 | 0 |  | SERVICES / UTILITY |  |  |  |  | 0.0000
13 | 535463 | 540KLD STP Membrane W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12 | 535462 | 4 | 32535 | 500KLD STP Membrane W/P Work | [5 empty] | 0.0000
14 | 535955 | 540KLD STP Screeding Work | Cu.Mtrs | 1.0000 | 1.0000 | 12 | 535462 | 4 | 32585 | 500KLD STP Screeding Work | [5 empty] | 0.0000
15 | 575450 | 540KLD STP W/P Misc. Material | No. | 1.0000 | 1.0000 | 12 | 535462 | 4 | 34042 | 500KLD STP W/P Misc. Material | [5 empty] | 0.0000
16 | 542667 | 540 KLD STP Beam, Buffle Wall Steel | Kgs | 1.0000 | 1.0000 | 1 | 532898 | 4 | 33052 | STP Beam, Buffle Wall Steel | [5 empty] | 0.0000
17 | 664324 | 540 KLD STP Top Slab, Beam Concrete | Cu.Mtrs | 1.0000 | 1.0000 | 1 | 532898 | 4 | 34597 | STP Top Slab, Beam Concrete | [5 empty] | 0.0000
18 | 664325 | 540 KLD STP Top Slab, Beam Steel | Kgs | 1.0000 | 1.0000 | 1 | 532898 | 4 | 34598 | STP Top Slab, Beam Steel | [5 empty] | 0.0000
19 | 664326 | 540 KLD STP Pump Room Top Slab, Beam, Column Concrete | Cu.Mtrs | 1.0000 | 1.0000 | 1 | 532898 | 4 | 34599 | STP Pump Room Top Slab, Beam Concrete | [5 empty] | 0.0000
20 | 664327 | 540 KLD STP Pump Room Top Slab, Beam, Column Steel | Kgs | 1.0000 | 1.0000 | 1 | 532898 | 4 | 34600 | STP Pump Room Top Slab, Beam Steel | [5 empty] | 0.0000
21 | 673953 | 540 KLD STP Rework | NA | 0.0000 | 0.0000 | 1 | 532898 | 31 | 0 | [6 empty] | 0.0000
22 | 673954 | 540KLD STP Raft Slab & Pardi Rework- Concrete | Cu.Mtrs | 152.6900 | 152.6900 | 21 | 673953 | 4 | 34928 | 540KLD STP Raft Slab & Pardi Rework- Concrete | [5 empty] | 0.0000
23 | 673955 | 540KLD STP Raft Slab & Pardi Rework- Steel | Kgs | 1.0000 | 1.0000 | 21 | 673953 | 4 | 34929 | 540KLD STP Raft Slab & Pardi Rework- Steel | [5 empty] | 0.0000
24 | 674627 | 540KLD STP Pardi Breaking Work | No. | 1.0000 | 1.0000 | 21 | 673953 | 4 | 34983 | 540KLD STP Pardi Breaking Work | [5 empty] | 0.0000