## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor | Selected Group :- Podium Floor
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 449308 | Podium Floor | NA | 0.0000 | 0.0000 | 0 | 445329 | 31 | 0 | [6 empty] | 0.0000
2 | 449311 | Flat P1 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
3 | 450650 | Wing -1 (3BHK) Flat P1 Kitchen Toilet Utility WB counter | Sq.Ft | 468.6400 | 468.6400 | 2 | 449311 | 4 | 29826 | WB Counter Dado | [5 empty] | 0.0000
4 | 497335 | Wing .1 (3BHK) Flat P1 Utility Dado (M) | Sq.Ft | 108.0000 | 108.0000 | 2 | 449311 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
5 | 497336 | Wing .1 (3BHK)Flat P1 Kitchen Dado (M) | Sq.Ft | 33.1100 | 33.1100 | 2 | 449311 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
6 | 497337 | Wing .1 (3BHK)Flat P1 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 2 | 449311 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
7 | 497338 | Wing .1 (3BHK)Flat P1 Common Toilet Dado(Light) | Sq.Ft | 145.7200 | 145.7200 | 2 | 449311 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
8 | 497339 | Wing .1 (3BHK)Flat P1 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 2 | 449311 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
9 | 497340 | Wing .1 (3BHK)Flat P1 Master Toilet Dado(Light) | Sq.Ft | 149.3500 | 149.3500 | 2 | 449311 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
10 | 497548 | Wing .1 (3BHK).P1 WB Dado (M) | Sq.Ft | 13.4700 | 13.4700 | 2 | 449311 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
11 | 449312 | Flat P2 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
12 | 449318 | Wing -1 (3BHK) Flat P2 Kitchen Toilet Utility WB counter | Sq.Ft | 477.1000 | 477.1000 | 11 | 449312 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
13 | 497341 | Wing .1 (3BHK)Flat P2 Kitchen Dado (M) | Sq.Ft | 33.1100 | 33.1100 | 11 | 449312 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
14 | 497342 | Wing .1 (3BHK)Flat P2 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 11 | 449312 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
15 | 497343 | Wing .1 (3BHK)Flat P2 Common Toilet Dado(Light) | Sq.Ft | 145.6900 | 145.6900 | 11 | 449312 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
16 | 497344 | Wing .1 (3BHK)Flat P2 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 11 | 449312 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
17 | 497345 | Wing .1 (3BHK)Flat P2 Master Toilet Dado(Light) | Sq.Ft | 174.7800 | 174.7800 | 11 | 449312 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
18 | 497346 | Wing .1 (3BHK) Flat P2 Utility .Dado (M) | Sq.Ft | 106.5600 | 106.5600 | 11 | 449312 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
19 | 497549 | Wing .1 (3BHK) P2 WB Dado (M) | Sq.Ft | 11.2200 | 11.2200 | 11 | 449312 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
20 | 449313 | Flat P3 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
21 | 449320 | Wing -1 (2BHK)Flat P3 Kitchen Toilet Utility WB counter | Sq.Ft | 456.4600 | 456.4600 | 20 | 449313 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
22 | 497347 | Wing .1 (2BHK) Flat P3 Kitchen Dado (M) | Sq.Ft | 29.8400 | 29.8400 | 20 | 449313 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
23 | 497348 | Wing .1 (2BHK) Flat P3 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 20 | 449313 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
24 | 497349 | Wing .1 (2BHK) Flat P3 Common Toilet Dado(Light) | Sq.Ft | 140.8700 | 140.8700 | 20 | 449313 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
25 | 497350 | Wing .1 (2BHK) Flat P3 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 20 | 449313 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
26 | 497351 | Wing .1 (2BHK) Flat P3 Master Toilet Dado(Light) | Sq.Ft | 162.6700 | 162.6700 | 20 | 449313 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
27 | 497352 | Wing .1 (2BHK) Flat P3 Utility .Dado (M) | Sq.Ft | 110.3300 | 110.3300 | 20 | 449313 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
28 | 497550 | Wing .1 (2BHK).P3 WB Dado (M) | Sq.Ft | 16.4600 | 16.4600 | 20 | 449313 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
29 | 449314 | Flat P4 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
30 | 449322 | Wing -1 (2BHK)Flat P4 Kitchen Toilet Utility WB counter | Sq.Ft | 463.0000 | 463.0000 | 29 | 449314 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
31 | 497353 | Wing .1 (2BHK) Flat P4 Kitchen Dado (M) | Sq.Ft | 31.7400 | 31.7400 | 29 | 449314 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
32 | 497354 | Wing .1 (2BHK) Flat P4 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 29 | 449314 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
33 | 497355 | Wing .1 (2BHK) Flat P4 Common Toilet Dado(Light) | Sq.Ft | 136.0300 | 136.0300 | 29 | 449314 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
34 | 497356 | Wing .1 (2BHK) Flat P4 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 29 | 449314 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
35 | 497357 | Wing .1 (2BHK) Flat P4 Master Toilet Dado(Light) | Sq.Ft | 155.4100 | 155.4100 | 29 | 449314 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
36 | 497358 | Wing.1 (2BHK) Flat P4 Utility Dado (M) | Sq.Ft | 109.9500 | 109.9500 | 29 | 449314 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
37 | 497551 | Wing .1 (2BHK).P4 WB Dado (M) | Sq.Ft | 16.4600 | 16.4600 | 29 | 449314 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
38 | 449315 | Flat P5 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
39 | 449324 | Wing -1 (2BHK)Flat P5 Kitchen Toilet Utility WB counter | Sq.Ft | 463.2400 | 463.2400 | 38 | 449315 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
40 | 497359 | Wing .1 (2BHK) Flat P5 Kitchen Dado (M) | Sq.Ft | 31.7400 | 31.7400 | 38 | 449315 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
41 | 497360 | Wing .1 (2BHK) Flat P5 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 38 | 449315 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
42 | 497361 | Wing .1 (2BHK) Flat P5 Common Toilet Dado(Light) | Sq.Ft | 136.0300 | 136.0300 | 38 | 449315 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
43 | 497362 | Wing .1 (2BHK) Flat P5 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 38 | 449315 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
44 | 497363 | Wing .1 (2BHK) Flat P5 Master Toilet Dado(Light) | Sq.Ft | 155.4100 | 155.4100 | 38 | 449315 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
45 | 497364 | Wing.1 (2BHK) Flat P5 Utility Dado (M) | Sq.Ft | 109.9500 | 109.9500 | 38 | 449315 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
46 | 497552 | Wing .1 (2BHK) P5 WB Dado (M) | Sq.Ft | 16.4600 | 16.4600 | 38 | 449315 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
47 | 676864 | Flat P6 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
48 | 676865 | Wing -1 (3BHK) Flat P6 Kitchen Toilet Utility WB counter | Sq.Ft | 477.1000 | 477.1000 | 47 | 676864 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
49 | 676866 | Wing .1 (3BHK)Flat P6 Kitchen Dado (M) | Sq.Ft | 33.1100 | 33.1100 | 47 | 676864 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
50 | 676867 | Wing .1 (3BHK)Flat P6 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 47 | 676864 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
51 | 676868 | Wing .1 (3BHK)Flat P6 Common Toilet Dado(Light) | Sq.Ft | 145.6900 | 145.6900 | 47 | 676864 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
52 | 676869 | Wing .1 (3BHK)Flat P6 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 47 | 676864 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
53 | 676870 | Wing .1 (3BHK)Flat P6 Master Toilet Dado(Light) | Sq.Ft | 174.7800 | 174.7800 | 47 | 676864 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
54 | 676871 | Wing .1 (3BHK) Flat P6 Utility .Dado (M) | Sq.Ft | 106.5600 | 106.5600 | 47 | 676864 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
55 | 676872 | Wing .1 (3BHK) P6 WB Dado (M) | Sq.Ft | 11.2200 | 11.2200 | 47 | 676864 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
56 | 676873 | Flat P7 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
57 | 676874 | Wing -1 (3BHK) Flat P7 Kitchen Toilet Utility WB counter | Sq.Ft | 477.1000 | 477.1000 | 56 | 676873 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
58 | 676875 | Wing .1 (3BHK)Flat P7 Kitchen Dado (M) | Sq.Ft | 33.1100 | 33.1100 | 56 | 676873 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
59 | 676876 | Wing .1 (3BHK)Flat P7 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 56 | 676873 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
60 | 676877 | Wing .1 (3BHK)Flat P7 Common Toilet Dado(Light) | Sq.Ft | 145.6900 | 145.6900 | 56 | 676873 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
61 | 676878 | Wing .1 (3BHK)Flat P7 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 56 | 676873 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
62 | 676879 | Wing .1 (3BHK)Flat P7 Master Toilet Dado(Light) | Sq.Ft | 174.7800 | 174.7800 | 56 | 676873 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
63 | 676880 | Wing .1 (3BHK) Flat P7 Utility .Dado (M) | Sq.Ft | 106.5600 | 106.5600 | 56 | 676873 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
64 | 676881 | Wing .1 (3BHK) P7 WB Dado (M) | Sq.Ft | 11.2200 | 11.2200 | 56 | 676873 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
65 | 676882 | Flat P8 | NA | 0.0000 | 0.0000 | 1 | 449308 | 31 | 0 | [6 empty] | 0.0000
66 | 676883 | Wing -1 (2BHK)Flat P8 Kitchen Toilet Utility WB counter | Sq.Ft | 456.4600 | 456.4600 | 65 | 676882 | 4 | 29774 | Kitchen - Dado | [5 empty] | 0.0000
67 | 676884 | Wing .1 (2BHK) Flat P8 Kitchen Dado (M) | Sq.Ft | 29.8400 | 29.8400 | 65 | 676882 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000
68 | 676885 | Wing .1 (2BHK) Flat P8 Common Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 65 | 676882 | 4 | 30246 | Common Toilet Dado(Dark) | [5 empty] | 0.0000
69 | 676886 | Wing .1 (2BHK) Flat P8 Common Toilet Dado(Light) | Sq.Ft | 140.8700 | 140.8700 | 65 | 676882 | 4 | 30247 | Common Toilet Dado(Light) | [5 empty] | 0.0000
70 | 676887 | Wing .1 (2BHK) Flat P8 Master Toilet Dado(Dark) | Sq.Ft | 7.2700 | 7.2700 | 65 | 676882 | 4 | 30244 | Master Toilet Dado(Dark) | [5 empty] | 0.0000
71 | 676888 | Wing .1 (2BHK) Flat P8 Master Toilet Dado(Light) | Sq.Ft | 162.6700 | 162.6700 | 65 | 676882 | 4 | 30245 | Master Toilet Dado(Light) | [5 empty] | 0.0000
72 | 676889 | Wing .1 (2BHK) Flat P8 Utility .Dado (M) | Sq.Ft | 110.3300 | 110.3300 | 65 | 676882 | 4 | 29825 | Utility -Dado | [5 empty] | 0.0000
73 | 676890 | Wing .1 (2BHK).P8 WB Dado (M) | Sq.Ft | 16.4600 | 16.4600 | 65 | 676882 | 4 | 30226 | Kitchen Dado (M) | [5 empty] | 0.0000