## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure | Selected Group :- F Super Structure
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 623449 | F Super Structure | NA | 0.0000 | 0.0000 | 0 | 556895 | 31 | 0 | [6 empty] | 0.0000
2 | 623450 | F - Super structure RCC Work (L) | NA | 0.0000 | 0.0000 | 1 | 623449 | 31 | 0 | [6 empty] | 0.0000
3 | 623451 | F - 1st Slab RCC Work (L) | Sq.Ft | 13749.8 | 13749.8 | 2 | 623450 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
4 | 623452 | F - 2nd Slab RCC Work (L) | Sq.Ft | 13749.8 | 13749.8 | 2 | 623450 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
5 | 623453 | F - 3rd Slab RCC Work (L) | Sq.Ft | 12939 | 12939 | 2 | 623450 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
6 | 623454 | F - 4th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34378 | A - 4th Slab RCC Work (L) | [5 empty] | 0.0000
7 | 623455 | F - 5th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
8 | 623456 | F - 6th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
9 | 623457 | F - 7th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
10 | 623458 | F - 8th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
11 | 623459 | F - 9th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
12 | 623460 | F - 10th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
13 | 623461 | F - 11th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
14 | 623462 | F - 12th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
15 | 623463 | F - 13th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
16 | 623464 | F - 14th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
17 | 623465 | F - 15th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
18 | 623466 | F - 16th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
19 | 623467 | F - 17th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
20 | 623468 | F - 18th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
21 | 623469 | F - 19th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
22 | 623470 | F - 20th Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
23 | 623471 | F - 21st Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
24 | 623472 | F - 22nd Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
25 | 623473 | F - 23rd Slab RCC Work (L) | Sq.Ft | 8996.9 | 8996.9 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
26 | 623474 | F - 24th Slab RCC Work (L) | Sq.Ft | 8658.1 | 8658.1 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
27 | 623475 | F - LMR & OHWT RCC Work (L) | Sq.Ft | 2330.4000 | 2330.4000 | 2 | 623450 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
28 | 623476 | F - Super Structure Aluform Work | Sq.Ft | 181928 | 181928 | 2 | 623450 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000
29 | 623477 | F - Super Structure RCC Work (M) | NA | 0.0000 | 0.0000 | 1 | 623449 | 31 | 0 | [6 empty] | 0.0000
30 | 623478 | F - 1st Slab RCC Work (M) | Sq.Ft | 13749.8 | 13749.8 | 29 | 623477 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
31 | 623479 | F - 2nd Slab RCC Work (M) | Sq.Ft | 13749.8 | 13749.8 | 29 | 623477 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
32 | 623480 | F - 3rd Slab RCC Work (M) | Sq.Ft | 12939 | 12939 | 29 | 623477 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
33 | 623481 | F - 4th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
34 | 623482 | F - 5th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
35 | 623483 | F - 6th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
36 | 623484 | F - 7th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
37 | 623485 | F - 8th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
38 | 623486 | F - 9th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
39 | 623487 | F - 10th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
40 | 623488 | F - 11th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
41 | 623489 | F - 12th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
42 | 623490 | F - 13th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
43 | 623491 | F - 14th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
44 | 623492 | F - 15th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
45 | 623493 | F - 16th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
46 | 623494 | F - 17th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
47 | 623495 | F - 18th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34388 | A - 18th Slab RCC Work (M) | [5 empty] | 0.0000
48 | 623496 | F - 19th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34389 | A - 19th Slab RCC Work (M) | [5 empty] | 0.0000
49 | 623497 | F - 20th Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
50 | 623498 | F - 21st Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
51 | 623499 | F - 22nd Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
52 | 623500 | F - 23rd Slab RCC Work (M) | Sq.Ft | 8996.9 | 8996.9 | 29 | 623477 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
53 | 623501 | F - 24th (Terrace) Slab RCC Work (M) | Sq.Ft | 8658.1 | 8658.1 | 29 | 623477 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
54 | 623502 | F - LMR & OHWT RCC Work (M) | Sq.Ft | 2330.4000 | 2330.4000 | 29 | 623477 | 4 | 34391 | A - LMR & OHWT RCC Work (M) | [5 empty] | 0.0000
55 | 623503 | F - Super Structure Aluform (M) | Sq.Ft | 181928 | 181928 | 29 | 623477 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000