## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting | Selected Group :- MHADA- Internal Ceiling Painting
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 438994 | MHADA- Internal Ceiling Painting | NA | 0.0000 | 0.0000 | 0 | 416333 | 31 | 0 |  |  | Internal Finishing |  |  |  | 0.0000
2 | 438995 | MHADA-1st Floor | NA | 0.0000 | 0.0000 | 1 | 438994 | 31 | 0 |  |  | Internal Finishing |  |  |  | 0.0000
3 | 438996 | MHADA-Flat No 101 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
4 | 439102 | MHADA-Flat No 101 Ceiling OBD Painting Work | Sq.Ft | 596.52 | 596.52 | 3 | 438996 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
5 | 439103 | MHADA-Flat No 102 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
6 | 439104 | MHADA-Flat No 102 Ceiling OBD Painting Work | Sq.Ft | 498.14 | 498.14 | 5 | 439103 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
7 | 439105 | MHADA-Flat No 103 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
8 | 439106 | MHADA-Flat No 103 Ceiling OBD Painting Work | Sq.Ft | 409.22 | 409.22 | 7 | 439105 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
9 | 439107 | MHADA-Flat No 104 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
10 | 439108 | MHADA-Flat No 104 Ceiling OBD Painting Work | Sq.Ft | 470.64 | 470.64 | 9 | 439107 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
11 | 439109 | MHADA-Flat No 105 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
12 | 439110 | MHADA-Flat No 105 Ceiling OBD Painting Work | Sq.Ft | 304.26 | 304.26 | 11 | 439109 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
13 | 439111 | MHADA-Flat No 106 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
14 | 439113 | MHADA-Flat No 107 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
15 | 439114 | MHADA-Flat No 107 Ceiling OBD Painting Work | Sq.Ft | 297.0600 | 297.0600 | 14 | 439113 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
16 | 439115 | MHADA-Flat No 108 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
17 | 439116 | MHADA-Flat No 108 Ceiling OBD Painting Work | Sq.Ft | 253.0600 | 253.0600 | 16 | 439115 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
18 | 439117 | MHADA-Flat No 109 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
19 | 439119 | MHADA-Flat No 110 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
20 | 439120 | MHADA-Flat No 110 Ceiling OBD Painting Work | Sq.Ft | 319.4500 | 319.4500 | 19 | 439119 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
21 | 439121 | MHADA-Flat No 111 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
22 | 439122 | MHADA-Flat No 111 Ceiling OBD Painting Work | Sq.Ft | 318.0700 | 318.0700 | 21 | 439121 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
23 | 439123 | MHADA-Flat No 112 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
24 | 439124 | MHADA-Flat No 112 Ceiling OBD Painting Work | Sq.Ft | 198.6500 | 198.6500 | 23 | 439123 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
25 | 439125 | MHADA-Flat No 113 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
26 | 439126 | MHADA-Flat No 113 Ceiling OBD Painting Work | Sq.Ft | 187.5300 | 187.5300 | 25 | 439125 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
27 | 439127 | MHADA-Flat No 114 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
28 | 439128 | MHADA-Flat No 114 Ceiling OBD Painting Work | Sq.Ft | 257.9200 | 257.9200 | 27 | 439127 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
29 | 439129 | MHADA-Flat No 115 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
30 | 439130 | MHADA-Flat No 115 Ceiling OBD Painting Work | Sq.Ft | 378.6100 | 378.6100 | 29 | 439129 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
31 | 439131 | MHADA-Flat No 116 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
32 | 439132 | MHADA-Flat No 116 Ceiling OBD Painting Work | Sq.Ft | 391.9300 | 391.9300 | 31 | 439131 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
33 | 439133 | MHADA-Flat No 117 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
34 | 439134 | MHADA-Flat No 117 Ceiling OBD Painting Work | Sq.Ft | 445.1100 | 445.1100 | 33 | 439133 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
35 | 439135 | MHADA-Flat No 118 | NA | 0.0000 | 0.0000 | 2 | 438995 | 31 | 0 | [6 empty] | 0.0000
36 | 439136 | MHADA-Flat No 118 Ceiling OBD Painting Work | Sq.Ft | 440.8700 | 440.8700 | 35 | 439135 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
37 | 439137 | MHADA-2nd Floor | NA | 0.0000 | 0.0000 | 1 | 438994 | 31 | 0 |  |  | Internal Finishing |  |  |  | 0.0000
38 | 439138 | MHADA-Flat No 201 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
39 | 439139 | MHADA-Flat No 201 Ceiling OBD Painting Work | Sq.Ft | 596.52 | 596.52 | 38 | 439138 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
40 | 439140 | MHADA-Flat No 202 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
41 | 439141 | MHADA-Flat No 202 Ceiling OBD Painting Work | Sq.Ft | 498.14 | 498.14 | 40 | 439140 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
42 | 439142 | MHADA-Flat No 203 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
43 | 439143 | MHADA-Flat No 203 Ceiling OBD Painting Work | Sq.Ft | 409.22 | 409.22 | 42 | 439142 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
44 | 439144 | MHADA-Flat No 204 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
45 | 439145 | MHADA-Flat No 204 Ceiling OBD Painting Work | Sq.Ft | 470.64 | 470.64 | 44 | 439144 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
46 | 439146 | MHADA-Flat No 205 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
47 | 439147 | MHADA-Flat No 205 Ceiling OBD Painting Work | Sq.Ft | 304.26 | 304.26 | 46 | 439146 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
48 | 439148 | MHADA-Flat No 206 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
49 | 439149 | MHADA-Flat No 206 Ceiling OBD Painting Work | Sq.Ft | 180.2200 | 180.2200 | 48 | 439148 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
50 | 439150 | MHADA-Flat No 207 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
51 | 439151 | MHADA-Flat No 207 Ceiling OBD Painting Work | Sq.Ft | 296.8300 | 296.8300 | 50 | 439150 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
52 | 439152 | MHADA-Flat No 208 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
53 | 439153 | MHADA-Flat No 208 Ceiling OBD Painting Work | Sq.Ft | 297.2000 | 297.2000 | 52 | 439152 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
54 | 439154 | MHADA-Flat No 209 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
55 | 439155 | MHADA-Flat No 209 Ceiling OBD Painting Work | Sq.Ft | 178.3300 | 178.3300 | 54 | 439154 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
56 | 439156 | MHADA-Flat No 210 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
57 | 439157 | MHADA-Flat No 210 Ceiling OBD Painting Work | Sq.Ft | 319.4600 | 319.4600 | 56 | 439156 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
58 | 439158 | MHADA-Flat No 211 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
59 | 439159 | MHADA-Flat No 211 Ceiling OBD Painting Work | Sq.Ft | 317.9600 | 317.9600 | 58 | 439158 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
60 | 439160 | MHADA-Flat No 212 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
61 | 439161 | MHADA-Flat No 212 Ceiling OBD Painting Work | Sq.Ft | 198.5600 | 198.5600 | 60 | 439160 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
62 | 439162 | MHADA-Flat No 213 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
63 | 439163 | MHADA-Flat No 213 Ceiling OBD Painting Work | Sq.Ft | 187.0700 | 187.0700 | 62 | 439162 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
64 | 439164 | MHADA-Flat No 214 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
65 | 439165 | MHADA-Flat No 214 Ceiling OBD Painting Work | Sq.Ft | 257.9200 | 257.9200 | 64 | 439164 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
66 | 439166 | MHADA-Flat No 215 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
67 | 439167 | MHADA-Flat No 215 Ceiling OBD Painting Work | Sq.Ft | 378.6100 | 378.6100 | 66 | 439166 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
68 | 439168 | MHADA-Flat No 216 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
69 | 439169 | MHADA-Flat No 216 Ceiling OBD Painting Work | Sq.Ft | 391.9300 | 391.9300 | 68 | 439168 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
70 | 439170 | MHADA-Flat No 217 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
71 | 439171 | MHADA-Flat No 217 Ceiling OBD Painting Work | Sq.Ft | 445.1100 | 445.1100 | 70 | 439170 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
72 | 439172 | MHADA-Flat No 218 | NA | 0.0000 | 0.0000 | 37 | 439137 | 31 | 0 | [6 empty] | 0.0000
73 | 439173 | MHADA-Flat No 218 Ceiling OBD Painting Work | Sq.Ft | 440.8700 | 440.8700 | 72 | 439172 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
74 | 439174 | MHADA-3rd Floor | NA | 0.0000 | 0.0000 | 1 | 438994 | 31 | 0 |  |  | Internal Finishing |  |  |  | 0.0000
75 | 439175 | MHADA-Flat No 301 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
76 | 439176 | MHADA-Flat No 301 Ceiling OBD Painting Work | Sq.Ft | 596.52 | 596.52 | 75 | 439175 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
77 | 439177 | MHADA-Flat No 302 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
78 | 439178 | MHADA-Flat No 302 Ceiling OBD Painting Work | Sq.Ft | 498.14 | 498.14 | 77 | 439177 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
79 | 439179 | MHADA-Flat No 303 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
80 | 439180 | MHADA-Flat No 303 Ceiling OBD Painting Work | Sq.Ft | 409.22 | 409.22 | 79 | 439179 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
81 | 439181 | MHADA-Flat No 304 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
82 | 439182 | MHADA-Flat No 304 Ceiling OBD Painting Work | Sq.Ft | 470.64 | 470.64 | 81 | 439181 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
83 | 439183 | MHADA-Flat No 305 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
84 | 439184 | MHADA-Flat No 305 Ceiling OBD Painting Work | Sq.Ft | 304.26 | 304.26 | 83 | 439183 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
85 | 439185 | MHADA-Flat No 306 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
86 | 439186 | MHADA-Flat No 306 Ceiling OBD Painting Work | Sq.Ft | 180.2200 | 180.2200 | 85 | 439185 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
87 | 439187 | MHADA-Flat No 307 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
88 | 439188 | MHADA-Flat No 307 Ceiling OBD Painting Work | Sq.Ft | 296.8300 | 296.8300 | 87 | 439187 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
89 | 439189 | MHADA-Flat No 308 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
90 | 439190 | MHADA-Flat No 308 Ceiling OBD Painting Work | Sq.Ft | 297.2000 | 297.2000 | 89 | 439189 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
91 | 439191 | MHADA-Flat No 309 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
92 | 439192 | MHADA-Flat No 309 Ceiling OBD Painting Work | Sq.Ft | 178.3300 | 178.3300 | 91 | 439191 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
93 | 439193 | MHADA-Flat No 310 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
94 | 439194 | MHADA-Flat No 310 Ceiling OBD Painting Work | Sq.Ft | 319.4600 | 319.4600 | 93 | 439193 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
95 | 439195 | MHADA-Flat No 311 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
96 | 439196 | MHADA-Flat No 311 Ceiling OBD Painting Work | Sq.Ft | 317.9600 | 317.9600 | 95 | 439195 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
97 | 439197 | MHADA-Flat No 312 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
98 | 439198 | MHADA-Flat No 312 Ceiling OBD Painting Work | Sq.Ft | 198.5600 | 198.5600 | 97 | 439197 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
99 | 439199 | MHADA-Flat No 313 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
100 | 439200 | MHADA-Flat No 313 Ceiling OBD Painting Work | Sq.Ft | 187.0700 | 187.0700 | 99 | 439199 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
101 | 439201 | MHADA-Flat No 314 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
102 | 439202 | MHADA-Flat No 314 Ceiling OBD Painting Work | Sq.Ft | 257.9200 | 257.9200 | 101 | 439201 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
103 | 439203 | MHADA-Flat No 315 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
104 | 439204 | MHADA-Flat No 315 Ceiling OBD Painting Work | Sq.Ft | 378.6100 | 378.6100 | 103 | 439203 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
105 | 439205 | MHADA-Flat No 316 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
106 | 439206 | MHADA-Flat No 316 Ceiling OBD Painting Work | Sq.Ft | 391.9300 | 391.9300 | 105 | 439205 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
107 | 439207 | MHADA-Flat No 317 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
108 | 439208 | MHADA-Flat No 317 Ceiling OBD Painting Work | Sq.Ft | 445.1100 | 445.1100 | 107 | 439207 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
109 | 439209 | MHADA-Flat No 318 | NA | 0.0000 | 0.0000 | 74 | 439174 | 31 | 0 | [6 empty] | 0.0000
110 | 439210 | MHADA-Flat No 318 Ceiling OBD Painting Work | Sq.Ft | 440.8700 | 440.8700 | 109 | 439209 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
111 | 439211 | MHADA-4th Floor | NA | 0.0000 | 0.0000 | 1 | 438994 | 31 | 0 |  |  | Internal Finishing |  |  |  | 0.0000
112 | 439212 | MHADA-Flat No 401 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
113 | 439213 | MHADA-Flat No 401 Ceiling OBD Painting Work | Sq.Ft | 596.52 | 596.52 | 112 | 439212 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
114 | 439214 | MHADA-Flat No 402 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
115 | 439215 | MHADA-Flat No 402 Ceiling OBD Painting Work | Sq.Ft | 498.14 | 498.14 | 114 | 439214 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
116 | 439216 | MHADA-Flat No 403 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
117 | 439217 | MHADA-Flat No 403 Ceiling OBD Painting Work | Sq.Ft | 409.22 | 409.22 | 116 | 439216 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
118 | 439218 | MHADA-Flat No 404 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
119 | 439219 | MHADA-Flat No 404 Ceiling OBD Painting Work | Sq.Ft | 470.64 | 470.64 | 118 | 439218 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
120 | 439220 | MHADA-Flat No 405 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
121 | 439221 | MHADA-Flat No 405 Ceiling OBD Painting Work | Sq.Ft | 304.26 | 304.26 | 120 | 439220 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
122 | 439222 | MHADA-Flat No 406 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
123 | 439223 | MHADA-Flat No 406 Ceiling OBD Painting Work | Sq.Ft | 180.2200 | 180.2200 | 122 | 439222 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
124 | 439224 | MHADA-Flat No 407 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
125 | 439225 | MHADA-Flat No 407 Ceiling OBD Painting Work | Sq.Ft | 296.8300 | 296.8300 | 124 | 439224 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
126 | 439226 | MHADA-Flat No 408 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
127 | 439227 | MHADA-Flat No 408 Ceiling OBD Painting Work | Sq.Ft | 297.2000 | 297.2000 | 126 | 439226 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
128 | 439228 | MHADA-Flat No 409 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
129 | 439229 | MHADA-Flat No 409 Ceiling OBD Painting Work | Sq.Ft | 178.3300 | 178.3300 | 128 | 439228 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
130 | 439230 | MHADA-Flat No 410 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
131 | 439231 | MHADA-Flat No 410 Ceiling OBD Painting Work | Sq.Ft | 319.4600 | 319.4600 | 130 | 439230 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
132 | 439232 | MHADA-Flat No 411 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
133 | 439233 | MHADA-Flat No 411 Ceiling OBD Painting Work | Sq.Ft | 317.9600 | 317.9600 | 132 | 439232 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
134 | 439234 | MHADA-Flat No 412 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
135 | 439235 | MHADA-Flat No 412 Ceiling OBD Painting Work | Sq.Ft | 198.5600 | 198.5600 | 134 | 439234 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
136 | 439236 | MHADA-Flat No 413 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
137 | 439237 | MHADA-Flat No 413 Ceiling OBD Painting Work | Sq.Ft | 187.0700 | 187.0700 | 136 | 439236 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
138 | 439238 | MHADA-Flat No 414 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
139 | 439239 | MHADA-Flat No 414 Ceiling OBD Painting Work | Sq.Ft | 257.9200 | 257.9200 | 138 | 439238 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
140 | 439240 | MHADA-Flat No 415 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
141 | 439241 | MHADA-Flat No 415 Ceiling OBD Painting Work | Sq.Ft | 378.6100 | 378.6100 | 140 | 439240 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
142 | 439242 | MHADA-Flat No 416 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
143 | 439243 | MHADA-Flat No 416 Ceiling OBD Painting Work | Sq.Ft | 391.9300 | 391.9300 | 142 | 439242 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
144 | 439244 | MHADA-Flat No 417 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
145 | 439245 | MHADA-Flat No 417 Ceiling OBD Painting Work | Sq.Ft | 445.1100 | 445.1100 | 144 | 439244 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
146 | 439246 | MHADA-Flat No 418 | NA | 0.0000 | 0.0000 | 111 | 439211 | 31 | 0 | [6 empty] | 0.0000
147 | 439247 | MHADA-Flat No 418 Ceiling OBD Painting Work | Sq.Ft | 440.8700 | 440.8700 | 146 | 439246 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
148 | 439248 | MHADA-5th Floor | NA | 0.0000 | 0.0000 | 1 | 438994 | 31 | 0 |  |  | Internal Finishing |  |  |  | 0.0000
149 | 439249 | MHADA-Flat No 501 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
150 | 439250 | MHADA-Flat No 501 Ceiling OBD Painting Work | Sq.Ft | 596.52 | 596.52 | 149 | 439249 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
151 | 439251 | MHADA-Flat No 502 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
152 | 439252 | MHADA-Flat No 502 Ceiling OBD Painting Work | Sq.Ft | 498.14 | 498.14 | 151 | 439251 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
153 | 439253 | MHADA-Flat No 503 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
154 | 439254 | MHADA-Flat No 503 Ceiling OBD Painting Work | Sq.Ft | 409.22 | 409.22 | 153 | 439253 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
155 | 439255 | MHADA-Flat No 504 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
156 | 439256 | MHADA-Flat No 504 Ceiling OBD Painting Work | Sq.Ft | 470.64 | 470.64 | 155 | 439255 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
157 | 439257 | MHADA-Flat No 505 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
158 | 439258 | MHADA-Flat No 505 Ceiling OBD Painting Work | Sq.Ft | 304.26 | 304.26 | 157 | 439257 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
159 | 439259 | MHADA-Flat No 506 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
160 | 439260 | MHADA-Flat No 506 Ceiling OBD Painting Work | Sq.Ft | 180.2200 | 180.2200 | 159 | 439259 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
161 | 439261 | MHADA-Flat No 507 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
162 | 439262 | MHADA-Flat No 507 Ceiling OBD Painting Work | Sq.Ft | 296.8300 | 296.8300 | 161 | 439261 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
163 | 439263 | MHADA-Flat No 508 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
164 | 439264 | MHADA-Flat No 508 Ceiling OBD Painting Work | Sq.Ft | 297.2000 | 297.2000 | 163 | 439263 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
165 | 439265 | MHADA-Flat No 509 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
166 | 439266 | MHADA-Flat No 509 Ceiling OBD Painting Work | Sq.Ft | 178.3300 | 178.3300 | 165 | 439265 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
167 | 439267 | MHADA-Flat No 510 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
168 | 439268 | MHADA-Flat No 510 Ceiling OBD Painting Work | Sq.Ft | 319.4600 | 319.4600 | 167 | 439267 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
169 | 439269 | MHADA-Flat No 511 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
170 | 439270 | MHADA-Flat No 511 Ceiling OBD Painting Work | Sq.Ft | 317.9600 | 317.9600 | 169 | 439269 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
171 | 439271 | MHADA-Flat No 512 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
172 | 439272 | MHADA-Flat No 512 Ceiling OBD Painting Work | Sq.Ft | 198.5600 | 198.5600 | 171 | 439271 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
173 | 439273 | MHADA-Flat No 513 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
174 | 439274 | MHADA-Flat No 513 Ceiling OBD Painting Work | Sq.Ft | 187.0700 | 187.0700 | 173 | 439273 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
175 | 439275 | MHADA-Flat No 514 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
176 | 439276 | MHADA-Flat No 514 Ceiling OBD Painting Work | Sq.Ft | 257.9200 | 257.9200 | 175 | 439275 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
177 | 439277 | MHADA-Flat No 515 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
178 | 439278 | MHADA-Flat No 515 Ceiling OBD Painting Work | Sq.Ft | 378.6100 | 378.6100 | 177 | 439277 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
179 | 439279 | MHADA-Flat No 516 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
180 | 439280 | MHADA-Flat No 516 Ceiling OBD Painting Work | Sq.Ft | 391.9300 | 391.9300 | 179 | 439279 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
181 | 439281 | MHADA-Flat No 517 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
182 | 439282 | MHADA-Flat No 517 Ceiling OBD Painting Work | Sq.Ft | 445.1100 | 445.1100 | 181 | 439281 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000
183 | 439283 | MHADA-Flat No 518 | NA | 0.0000 | 0.0000 | 148 | 439248 | 31 | 0 | [6 empty] | 0.0000
184 | 439284 | MHADA-Flat No 518 Ceiling OBD Painting Work | Sq.Ft | 440.8700 | 440.8700 | 183 | 439283 | 4 | 28817 | Ceiling OBD Painting Work | BUILDING | Internal Finishing |  |  |  | 0.0000