## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work | Selected Group :- Wing-2 Garbage Room Tiling Work
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 600618 | Wing-2 Garbage Room Tiling Work | NA | 0.0000 | 0.0000 | 0 | 600460 | 31 | 0 | [6 empty] | 0.0000
2 | 600619 | Wing-2 Podium Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
3 | 600620 | Wing-2 Podium Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 2 | 600619 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
4 | 600621 | Wing-2 Podium Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 2 | 600619 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
5 | 600622 | Wing-2 1st Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
6 | 600623 | Wing.2 1st Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 5 | 600622 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
7 | 600624 | Wing.2 1st Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 5 | 600622 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
8 | 600625 | Wing-2 2nd Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
9 | 600626 | Wing.2 2nd Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 8 | 600625 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
10 | 600627 | Wing.2 2nd Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 8 | 600625 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
11 | 600628 | Wing-2 3rd Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
12 | 600629 | Wing.2 3rd Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 11 | 600628 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
13 | 600630 | Wing.2 3rd Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 11 | 600628 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
14 | 600631 | Wing-2 4th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
15 | 600632 | Wing.2 4th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 14 | 600631 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
16 | 600633 | Wing.2 4th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 14 | 600631 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
17 | 600634 | Wing-2 5th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
18 | 600635 | Wing.2 5th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 17 | 600634 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
19 | 600636 | Wing.2 5th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 17 | 600634 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
20 | 600637 | Wing-2 6th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
21 | 600638 | Wing.2 6th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 20 | 600637 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
22 | 600639 | Wing.2 6th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 20 | 600637 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
23 | 600640 | Wing-2 7th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
24 | 600641 | Wing.2 7th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 23 | 600640 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
25 | 600642 | Wing.2 7th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 23 | 600640 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
26 | 600643 | Wing-2 8th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
27 | 600644 | Wing.2 8th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 26 | 600643 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
28 | 600645 | Wing.2 8th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 26 | 600643 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
29 | 600646 | Wing-2 9th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
30 | 600647 | Wing.2 9th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 29 | 600646 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
31 | 600648 | Wing.2 9th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 29 | 600646 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
32 | 600649 | Wing-2 10th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
33 | 600650 | Wing.2 10th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 32 | 600649 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
34 | 600651 | Wing.2 10th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 32 | 600649 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
35 | 600652 | Wing-2 11th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
36 | 600653 | Wing.2 11th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 35 | 600652 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
37 | 600654 | Wing.2 11th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 35 | 600652 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
38 | 600655 | Wing-2 12th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
39 | 600656 | Wing.2 12th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 38 | 600655 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
40 | 600657 | Wing.2 12th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 38 | 600655 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
41 | 600658 | Wing-2 13th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
42 | 600659 | Wing.2 13th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 41 | 600658 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
43 | 600660 | Wing.2 13th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 41 | 600658 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
44 | 600661 | Wing-2 14th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
45 | 600662 | Wing.2 14th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 44 | 600661 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
46 | 600663 | Wing.2 14th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 44 | 600661 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
47 | 600664 | Wing-2 15th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
48 | 600665 | Wing.2 15th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 47 | 600664 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
49 | 600666 | Wing.2 15th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 47 | 600664 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
50 | 600667 | Wing-2 16th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
51 | 600668 | Wing.2 16th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 50 | 600667 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
52 | 600669 | Wing.2 16th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 50 | 600667 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
53 | 600670 | Wing-2 17th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
54 | 600671 | Wing.2 17th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 53 | 600670 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
55 | 600672 | Wing.2 17th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 53 | 600670 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
56 | 600673 | Wing-2 18th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
57 | 600674 | Wing.2 18th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 56 | 600673 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
58 | 600675 | Wing.2 18th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 56 | 600673 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
59 | 600676 | Wing-2 19th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
60 | 600677 | Wing.2 19th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 59 | 600676 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
61 | 600678 | Wing.2 19th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 59 | 600676 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
62 | 600679 | Wing-2 20th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
63 | 600680 | Wing.2 20th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 62 | 600679 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
64 | 600681 | Wing.2 20th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 62 | 600679 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
65 | 600682 | Wing-2 21st Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
66 | 600683 | Wing.2 21st Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 65 | 600682 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
67 | 600684 | Wing.2 21st Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 65 | 600682 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
68 | 600685 | Wing-2 22nd Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
69 | 600686 | Wing.2 22nd Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 68 | 600685 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
70 | 600687 | Wing.2 22nd Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 68 | 600685 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
71 | 600688 | Wing-2 23rd Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
72 | 600689 | Wing.2 23rd Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 71 | 600688 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
73 | 600690 | Wing.2 23rd Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 71 | 600688 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
74 | 600691 | Wing-2 24th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
75 | 600692 | Wing.2 24th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 74 | 600691 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
76 | 600693 | Wing.2 24th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 74 | 600691 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
77 | 600694 | Wing-2 25th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
78 | 600695 | Wing.2 25th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 77 | 600694 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
79 | 600696 | Wing.2 25th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 77 | 600694 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
80 | 600697 | Wing-2 26th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
81 | 600698 | Wing.2 26th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 80 | 600697 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
82 | 600699 | Wing.2 26th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 80 | 600697 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
83 | 600700 | Wing-2 27th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
84 | 600701 | Wing.2 27th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 83 | 600700 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
85 | 600702 | Wing.2 27th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 83 | 600700 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
86 | 600703 | Wing-2 28th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
87 | 600704 | Wing.2 28th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 86 | 600703 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
88 | 600705 | Wing.2 28th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 86 | 600703 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
89 | 600706 | Wing-2 29th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
90 | 600707 | Wing.2 29th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 89 | 600706 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
91 | 600708 | Wing.2 29th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 89 | 600706 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000
92 | 600709 | Wing-2 30th Floor Garbage Room Tiling | NA | 0.0000 | 0.0000 | 1 | 600618 | 31 | 0 | [6 empty] | 0.0000
93 | 600710 | Wing.2 30th Floor Garbage Room Flooring Work | Sq.Ft | 61.6900 | 61.6900 | 92 | 600709 | 4 | 34124 | Wing-2 Garbage Room Flooring Work | [5 empty] | 0.0000
94 | 600711 | Wing.2 30th Floor Garbage Room Dado Work | Sq.Ft | 131.75 | 131.75 | 92 | 600709 | 4 | 34125 | Wing-2 Garbage Room Dado Work | [5 empty] | 0.0000