## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado | Selected Group :- Garbage Chute Dado
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 479601 | Garbage Chute Dado | NA | 0.0000 | 0.0000 | 0 | 479597 | 31 | 0 | [6 empty] | 0.0000
2 | 479602 | Wing 1 Podium Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
3 | 574942 | Wing 1 1st Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
4 | 574943 | Wing 1 2nd Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
5 | 574944 | Wing 1 3rd Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
6 | 574945 | Wing 1 4th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
7 | 574946 | Wing 1 5th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
8 | 574947 | Wing 1 6th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
9 | 574948 | Wing 1 7th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
10 | 574949 | Wing 1 8th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
11 | 574950 | Wing 1 9th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
12 | 574951 | Wing 1 10th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
13 | 574952 | Wing 1 11th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
14 | 574953 | Wing 1 12th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
15 | 574954 | Wing 1 13th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
16 | 574955 | Wing 1 14th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
17 | 574956 | Wing 1 15th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
18 | 574957 | Wing 1 16th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
19 | 574958 | Wing 1 17th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
20 | 574959 | Wing 1 18th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
21 | 574960 | Wing 1 19th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
22 | 574961 | Wing 1 20th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work |  |  |  |  | Started | 0.0000
23 | 574962 | Wing 1 21st Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
24 | 574963 | Wing 1 22nd Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
25 | 574964 | Wing 1 23rd Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
26 | 574965 | Wing 1 24th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
27 | 574966 | Wing 1 25th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
28 | 574967 | Wing 1 26th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
29 | 574968 | Wing 1 27th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
30 | 574969 | Wing 1 28th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
31 | 574970 | Wing 1 29th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000
32 | 574971 | Wing 1 30th Floor Garbage Chute Dado Work | Sq.Ft | 124 | 124 | 1 | 479601 | 4 | 30396 | Wing 1 Garbage Chute Dado Work | [5 empty] | 0.0000