## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint | Selected Group :- Duct External Paint
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 479656 | Duct External Paint | NA | 0.0000 | 0.0000 | 0 | 463663 | 31 | 0 | [6 empty] | 0.0000
2 | 479657 | Podium Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
3 | 479658 | Podium Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 2 | 479657 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
4 | 479659 | 1st Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
5 | 479660 | 1st Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 4 | 479659 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
6 | 479661 | 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
7 | 479662 | 2nd Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 6 | 479661 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
8 | 479663 | 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
9 | 479664 | 3rd Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 8 | 479663 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
10 | 479665 | 4th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
11 | 479666 | 4th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 10 | 479665 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
12 | 479667 | 5th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
13 | 479668 | 5th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 12 | 479667 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
14 | 479674 | 6th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
15 | 479675 | 6th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 14 | 479674 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
16 | 479676 | 7th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
17 | 479677 | 7th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 16 | 479676 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
18 | 479678 | 8th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
19 | 479679 | 8th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 18 | 479678 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
20 | 479680 | 9th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
21 | 479681 | 9th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 20 | 479680 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
22 | 479682 | 10th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
23 | 479683 | 10th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 22 | 479682 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
24 | 479684 | 11th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
25 | 479685 | 11th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 24 | 479684 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
26 | 479686 | 12th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
27 | 479687 | 12th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 26 | 479686 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
28 | 479688 | 13th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
29 | 479689 | 13th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 28 | 479688 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
30 | 479690 | 14th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
31 | 479691 | 14th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 30 | 479690 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
32 | 479692 | 15th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
33 | 479693 | 15th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 32 | 479692 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
34 | 479694 | 16th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
35 | 479695 | 16th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 34 | 479694 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
36 | 479696 | 17th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
37 | 479697 | 17th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 36 | 479696 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
38 | 479698 | 18th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
39 | 479699 | 18th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 38 | 479698 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
40 | 479700 | 19th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
41 | 479701 | 19th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 40 | 479700 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
42 | 479702 | 20th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
43 | 479703 | 20th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 42 | 479702 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
44 | 479704 | 21st Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
45 | 479705 | 21st Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 44 | 479704 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
46 | 479706 | 22nd Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
47 | 479707 | 22nd Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 46 | 479706 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
48 | 479708 | 23rd Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
49 | 479709 | 23rd Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 48 | 479708 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
50 | 479710 | 24th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
51 | 479711 | 24th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 50 | 479710 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
52 | 479712 | 25th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
53 | 479713 | 25th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 52 | 479712 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
54 | 479714 | 26th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
55 | 479715 | 26th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 54 | 479714 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
56 | 479716 | 27th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
57 | 479717 | 27th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 56 | 479716 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
58 | 479718 | 28th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
59 | 479719 | 28th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 58 | 479718 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
60 | 677786 | 29th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
61 | 677787 | 29th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 60 | 677786 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000
62 | 677788 | 30th Floor | NA | 0.0000 | 0.0000 | 1 | 479656 | 31 | 0 | [6 empty] | 0.0000
63 | 677789 | 30th Floor Wing 1 Duct External Painting | Sq.Ft | 4601.61 | 4601.61 | 62 | 677788 | 4 | 30406 | Wing 1 Duct External Painting | [5 empty] | 0.0000