## Sheet1
Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI | Project :-GANGA ASMI
Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor | Selected Group :- Wing-2 Podium Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 606744 | Wing-2 Podium Floor | NA | 0.0000 | 0.0000 | 0 | 398352 | 31 | 0 | [6 empty] | 0.0000
2 | 606745 | Wing-2 P1 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
3 | 606746 | Wing-2 P1 Flat Int Flat Chemical Grouting Work | Sq.Ft | 577.4100 | 577.4100 | 2 | 606745 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
4 | 606747 | Wing-2 P1 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 33.9800 | 33.9800 | 2 | 606745 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
5 | 606748 | Wing-2 P1 Flat C. Toilet IPS W/P | Sq.Ft | 33.9800 | 33.9800 | 2 | 606745 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
6 | 606749 | Wing-2 P1 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 2 | 606745 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
7 | 606750 | Wing-2 P1 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 2 | 606745 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
8 | 606751 | Wing-2 P1 Flat Utility Chemical Coat W/P | Sq.Ft | 36.5700 | 36.5700 | 2 | 606745 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
9 | 606752 | Wing-2 P1 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 36.5700 | 36.5700 | 2 | 606745 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
10 | 606753 | Wing-2 P1 Flat Balcony Chemical Coat W/P | Sq.Ft | 53.2800 | 53.2800 | 2 | 606745 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
11 | 606754 | Wing-2 P1 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 53.2800 | 53.2800 | 2 | 606745 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
12 | 606756 | Wing-2 P1 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 2 | 606745 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
13 | 606760 | Wing-2 P1 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 2 | 606745 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
14 | 606761 | Wing-2 P2 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
15 | 606762 | Wing.2 P2 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.66 | 506.66 | 14 | 606761 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
16 | 606763 | Wing.2 P2 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.52 | 30.52 | 14 | 606761 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
17 | 606764 | Wing.2 P2 Flat C. Toilet IPS W/P | Sq.Ft | 30.52 | 30.52 | 14 | 606761 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
18 | 606765 | Wing.2 P2 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 14 | 606761 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
19 | 606766 | Wing.2 P2 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 14 | 606761 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
20 | 606767 | Wing.2 P2 Flat Utility Chemical Coat W/P | Sq.Ft | 34.88 | 34.88 | 14 | 606761 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
21 | 606768 | Wing.2 P2 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.88 | 34.88 | 14 | 606761 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
22 | 606769 | Wing.2 P2 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.37 | 40.37 | 14 | 606761 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
23 | 606770 | Wing.2 P2 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.37 | 40.37 | 14 | 606761 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
24 | 606771 | Wing-2 P2 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 14 | 606761 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
25 | 606772 | Wing.2 P2 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 14 | 606761 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
26 | 606775 | Wing-2 P3 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
27 | 606776 | Wing-2 P3 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.66 | 506.66 | 26 | 606775 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
28 | 606777 | Wing-2 P3 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.52 | 30.52 | 26 | 606775 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
29 | 606778 | Wing-2 P3 Flat C. Toilet IPS W/P | Sq.Ft | 30.52 | 30.52 | 26 | 606775 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
30 | 606779 | Wing-2 P3 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 26 | 606775 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
31 | 606780 | Wing-2 P3 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 26 | 606775 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
32 | 606781 | Wing-2 P3 Flat Utility Chemical Coat W/P | Sq.Ft | 34.88 | 34.88 | 26 | 606775 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
33 | 606782 | Wing-2 P3 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.88 | 34.88 | 26 | 606775 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
34 | 606783 | Wing-2 P3 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.37 | 40.37 | 26 | 606775 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
35 | 606784 | Wing-2 P3 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.37 | 40.37 | 26 | 606775 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
36 | 606785 | Wing-2 P3 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 26 | 606775 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
37 | 606786 | Wing-2 P3 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 26 | 606775 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
38 | 606787 | Wing-2 P4 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
39 | 606788 | Wing-2 P4 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.66 | 506.66 | 38 | 606787 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
40 | 606789 | Wing-2 P4 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.52 | 30.52 | 38 | 606787 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
41 | 606790 | Wing-2 P4 Flat C. Toilet IPS W/P | Sq.Ft | 30.52 | 30.52 | 38 | 606787 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
42 | 606791 | Wing-2 P4 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 38 | 606787 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
43 | 606792 | Wing-2 P4 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 38 | 606787 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
44 | 606793 | Wing-2 P4 Flat Utility Chemical Coat W/P | Sq.Ft | 34.88 | 34.88 | 38 | 606787 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
45 | 606794 | Wing-2 P4 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.88 | 34.88 | 38 | 606787 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
46 | 606795 | Wing-2 P4 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.37 | 40.37 | 38 | 606787 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
47 | 606796 | Wing-2 P4 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.37 | 40.37 | 38 | 606787 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
48 | 606797 | Wing-2 P4 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 38 | 606787 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
49 | 606798 | Wing-2 P4 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 38 | 606787 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
50 | 606799 | Wing-2 P5 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
51 | 606800 | Wing-2 P5 Flat Int Flat Chemical Grouting Work | Sq.Ft | 579.41 | 579.41 | 50 | 606799 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
52 | 606801 | Wing-2 P5 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 33.91 | 33.91 | 50 | 606799 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
53 | 606802 | Wing-2 P5 Flat C. Toilet IPS W/P | Sq.Ft | 33.91 | 33.91 | 50 | 606799 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
54 | 606803 | Wing-2 P5 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 50 | 606799 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
55 | 606804 | Wing-2 P5 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 50 | 606799 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
56 | 606805 | Wing-2 P5 Flat Utility Chemical Coat W/P | Sq.Ft | 0 | 0 | 50 | 606799 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
57 | 606806 | Wing-2 P5 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 0 | 0 | 50 | 606799 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
58 | 606807 | Wing-2 P5 Flat Balcony Chemical Coat W/P | Sq.Ft | 36.33 | 36.33 | 50 | 606799 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
59 | 606808 | Wing-2 P5 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 36.33 | 36.33 | 50 | 606799 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
60 | 606809 | Wing-2 P5 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 50 | 606799 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
61 | 606810 | Wing-2 P5 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 50 | 606799 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
62 | 606811 | Wing-2 P6 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
63 | 606812 | Wing-2 P6 Flat Int Flat Chemical Grouting Work | Sq.Ft | 696.22 | 696.22 | 62 | 606811 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
64 | 606813 | Wing-2 P6 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 33.91 | 33.91 | 62 | 606811 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
65 | 606814 | Wing-2 P6 Flat C. Toilet IPS W/P | Sq.Ft | 33.91 | 33.91 | 62 | 606811 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
66 | 606815 | Wing-2 P6 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 62 | 606811 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
67 | 606816 | Wing-2 P6 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 62 | 606811 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
68 | 606817 | Wing-2 P6 Flat Utility Chemical Coat W/P | Sq.Ft | 32.29 | 32.29 | 62 | 606811 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
69 | 606818 | Wing-2 P6 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 32.29 | 32.29 | 62 | 606811 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
70 | 606819 | Wing-2 P6 Flat Balcony Chemical Coat W/P | Sq.Ft | 53.2800 | 53.2800 | 62 | 606811 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
71 | 606820 | Wing-2 P6 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 53.2800 | 53.2800 | 62 | 606811 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
72 | 606821 | Wing-2 P6 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 62 | 606811 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
73 | 606822 | Wing-2 P6 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 62 | 606811 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
74 | 606823 | Wing-2 P7 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
75 | 606824 | Wing-2 P7 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.66 | 506.66 | 74 | 606823 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
76 | 606825 | Wing-2 P7 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.52 | 30.52 | 74 | 606823 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
77 | 606826 | Wing-2 P7 Flat C. Toilet IPS W/P | Sq.Ft | 30.52 | 30.52 | 74 | 606823 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
78 | 606827 | Wing-2 P7 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 74 | 606823 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
79 | 606828 | Wing-2 P7 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 74 | 606823 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
80 | 606829 | Wing-2 P7 Flat Utility Chemical Coat W/P | Sq.Ft | 34.88 | 34.88 | 74 | 606823 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
81 | 606830 | Wing-2 P7 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.88 | 34.88 | 74 | 606823 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
82 | 606831 | Wing-2 P7 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.37 | 40.37 | 74 | 606823 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
83 | 606832 | Wing-2 P7 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.37 | 40.37 | 74 | 606823 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
84 | 606833 | Wing-2 P7 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 74 | 606823 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
85 | 606834 | Wing-2 P7 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 74 | 606823 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
86 | 606835 | Wing-2 P8 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
87 | 606836 | Wing-2 P8 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.66 | 506.66 | 86 | 606835 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
88 | 606837 | Wing-2 P8 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.52 | 30.52 | 86 | 606835 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
89 | 606838 | Wing-2 P8 Flat C. Toilet IPS W/P | Sq.Ft | 30.52 | 30.52 | 86 | 606835 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
90 | 606839 | Wing-2 P8 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 86 | 606835 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
91 | 606840 | Wing-2 P8 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 86 | 606835 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
92 | 606841 | Wing-2 P8 Flat Utility Chemical Coat W/P | Sq.Ft | 34.88 | 34.88 | 86 | 606835 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
93 | 606842 | Wing-2 P8 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.88 | 34.88 | 86 | 606835 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
94 | 606843 | Wing-2 P8 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.37 | 40.37 | 86 | 606835 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
95 | 606844 | Wing-2 P8 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.37 | 40.37 | 86 | 606835 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
96 | 606845 | Wing-2 P8 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 86 | 606835 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
97 | 606846 | Wing-2 P8 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 86 | 606835 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000
98 | 606847 | Wing-2 P9 Flat Waterproofing | NA | 0.0000 | 0.0000 | 1 | 606744 | 31 | 0 | [6 empty] | 0.0000
99 | 606848 | Wing-2 P9 Flat Int Flat Chemical Grouting Work | Sq.Ft | 506.66 | 506.66 | 98 | 606847 | 4 | 34185 | Wing-2 Int Flat Chemical Grouting Work | [5 empty] | 0.0000
100 | 606849 | Wing-2 P9 Flat C. Toilet Chemical Coat W/P | Sq.Ft | 30.52 | 30.52 | 98 | 606847 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
101 | 606850 | Wing-2 P9 Flat C. Toilet IPS W/P | Sq.Ft | 30.52 | 30.52 | 98 | 606847 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
102 | 606851 | Wing-2 P9 Flat M. Toilet Chemical Coat W/P | Sq.Ft | 38.7500 | 38.7500 | 98 | 606847 | 4 | 34186 | Wing-2 Toilet Chemical Coat W/P | [5 empty] | 0.0000
103 | 606852 | Wing-2 P9 Flat M. Toilet IPS W/P | Sq.Ft | 38.7500 | 38.7500 | 98 | 606847 | 4 | 34187 | Wing-2 Toilet IPS W/P | [5 empty] | 0.0000
104 | 606853 | Wing-2 P9 Flat Utility Chemical Coat W/P | Sq.Ft | 34.88 | 34.88 | 98 | 606847 | 4 | 34188 | Wing-2 Utility Chemical Coat W/P | [5 empty] | 0.0000
105 | 606854 | Wing-2 P9 Flat Utility Brickbatt+Finish Coat W/P | Sq.Ft | 34.88 | 34.88 | 98 | 606847 | 4 | 34189 | Wing-2 Utility Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
106 | 606855 | Wing-2 P9 Flat Balcony Chemical Coat W/P | Sq.Ft | 40.37 | 40.37 | 98 | 606847 | 4 | 34190 | Wing-2 Balcony Chemical Coat W/P | [5 empty] | 0.0000
107 | 606856 | Wing-2 P9 Flat Balcony Brickbatt+Finish Coat W/P | Sq.Ft | 40.37 | 40.37 | 98 | 606847 | 4 | 34191 | Wing-2 Balcony Brickbatt+Finish Coat W/P | [5 empty] | 0.0000
108 | 606857 | Wing-2 P9 Flat IPS Seal Pack at Toilet & Balcony Door | Flat | 1.0000 | 1.0000 | 98 | 606847 | 4 | 34192 | Wing-2 IPS Seal Pack at Toilet & Balcony | [5 empty] | 0.0000
109 | 606858 | Wing-2 P9 Flat Bore Packing + Perma Eazee Coat | Flat | 1.0000 | 1.0000 | 98 | 606847 | 4 | 34193 | Wing-2 Bore Packing + Perma Eazee Coat | [5 empty] | 0.0000