## Sheet1
Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI | Project :- SRA MORWADI
Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L) | Selected Group :- G- Common W/P (L)
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
549624 | G-1st Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
549624 | G-1st Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.001. | 2.0000 | Labour | 0 | 0.0000
549624 | G-1st Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.001. | 2.0000 | Labour | 0 | 0.0000
549624 | G-1st Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.001. | 375.0000 | Material | 0 | 0.0000
549628 | G-2nd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.002. | 0.0000 | Labour | 0 | 0.0000
549628 | G-2nd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.002. | 2.0000 | Labour | 0 | 0.0000
549628 | G-2nd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.002. | 2.0000 | Labour | 0 | 0.0000
549628 | G-2nd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.002. | 375.0000 | Material | 0 | 0.0000
549629 | G-3rd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.003. | 0.0000 | Labour | 0 | 0.0000
549629 | G-3rd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.003. | 2.0000 | Labour | 0 | 0.0000
549629 | G-3rd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.003. | 2.0000 | Labour | 0 | 0.0000
549629 | G-3rd Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.003. | 375.0000 | Material | 0 | 0.0000
549630 | G-4th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.004. | 0.0000 | Labour | 0 | 0.0000
549630 | G-4th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.004. | 2.0000 | Labour | 0 | 0.0000
549630 | G-4th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.004. | 2.0000 | Labour | 0 | 0.0000
549630 | G-4th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.004. | 375.0000 | Material | 0 | 0.0000
549632 | G-5th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.005. | 0.0000 | Labour | 0 | 0.0000
549632 | G-5th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.005. | 2.0000 | Labour | 0 | 0.0000
549632 | G-5th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.005. | 2.0000 | Labour | 0 | 0.0000
549632 | G-5th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.005. | 375.0000 | Material | 0 | 0.0000
549633 | G-6th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.006. | 0.0000 | Labour | 0 | 0.0000
549633 | G-6th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.006. | 2.0000 | Labour | 0 | 0.0000
549633 | G-6th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.006. | 2.0000 | Labour | 0 | 0.0000
549633 | G-6th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.006. | 375.0000 | Material | 0 | 0.0000
549634 | G-7th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.007. | 0.0000 | Labour | 0 | 0.0000
549634 | G-7th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.007. | 2.0000 | Labour | 0 | 0.0000
549634 | G-7th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.007. | 2.0000 | Labour | 0 | 0.0000
549634 | G-7th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.007. | 375.0000 | Material | 0 | 0.0000
549635 | G-8th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 2608.4400 | 0.0000 | 165.001.010.004.002.001.008. | 0.0000 | Labour | 0 | 0.0000
549635 | G-8th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 2608.4400 | 2.0000 | 165.001.010.004.002.001.008. | 2.0000 | Labour | 0 | 0.0000
549635 | G-8th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 2608.4400 | 2.0000 | 165.001.010.004.002.001.008. | 2.0000 | Labour | 0 | 0.0000
549635 | G-8th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 4.17 | 375.0000 | 165.001.010.004.002.001.008. | 375.0000 | Material | 0 | 0.0000
549637 | G-9th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.009. | 0.0000 | Labour | 0 | 0.0000
549637 | G-9th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.009. | 2.0000 | Labour | 0 | 0.0000
549637 | G-9th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.009. | 2.0000 | Labour | 0 | 0.0000
549637 | G-9th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.009. | 375.0000 | Material | 0 | 0.0000
549639 | G-10th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.010. | 0.0000 | Labour | 0 | 0.0000
549639 | G-10th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.010. | 2.0000 | Labour | 0 | 0.0000
549639 | G-10th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.010. | 2.0000 | Labour | 0 | 0.0000
549639 | G-10th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.010. | 375.0000 | Material | 0 | 0.0000
549640 | G-11th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.011. | 0.0000 | Labour | 0 | 0.0000
549640 | G-11th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.011. | 2.0000 | Labour | 0 | 0.0000
549640 | G-11th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.011. | 2.0000 | Labour | 0 | 0.0000
549640 | G-11th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.011. | 375.0000 | Material | 0 | 0.0000
549641 | G-12th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 1250.0200 | 0.0000 | 165.001.010.004.002.001.012. | 0.0000 | Labour | 0 | 0.0000
549641 | G-12th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.012. | 2.0000 | Labour | 0 | 0.0000
549641 | G-12th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 1250.0200 | 2.0000 | 165.001.010.004.002.001.012. | 2.0000 | Labour | 0 | 0.0000
549641 | G-12th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 2 | 375.0000 | 165.001.010.004.002.001.012. | 375.0000 | Material | 0 | 0.0000
549642 | G-13th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12225 | Chemical Grouting (L) | Sq.Ft | 2608.4400 | 0.0000 | 165.001.010.004.002.001.013. | 0.0000 | Labour | 0 | 0.0000
549642 | G-13th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12224 | Chemical Grouting (M) | Sq.Ft | 2608.4400 | 2.0000 | 165.001.010.004.002.001.013. | 2.0000 | Labour | 0 | 0.0000
549642 | G-13th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8377 | Ghadai work- BCP | Sq.Ft | 2608.4400 | 2.0000 | 165.001.010.004.002.001.013. | 2.0000 | Labour | 0 | 0.0000
549642 | G-13th Floor Lobby W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | Cement 43 Grade | Bags | 4.17 | 375.0000 | 165.001.010.004.002.001.013. | 375.0000 | Material | 0 | 0.0000