## Sheet1
Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS | Project :- GANGA DHAM TOWERS
Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work | Selected Group :- C Vertical Core Cut For Plumbing Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
527358 | C101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
527358 | C101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.001.001.001. | 0.0000 | Labour | 0 | 0.0000
527359 | C102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
527359 | C102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.001.002.001. | 0.0000 | Labour | 0 | 0.0000
527360 | C103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
527360 | C103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.001.003.001. | 0.0000 | Labour | 0 | 0.0000
527361 | C104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
527361 | C104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.001.004.001. | 0.0000 | Labour | 0 | 0.0000
527367 | C201 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
527367 | C201 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.002.001.001. | 0.0000 | Labour | 0 | 0.0000
527368 | C202 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
527368 | C202 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.002.002.001. | 0.0000 | Labour | 0 | 0.0000
527369 | C203 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
527369 | C203 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.002.003.001. | 0.0000 | Labour | 0 | 0.0000
527370 | C204 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
527370 | C204 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.002.004.001. | 0.0000 | Labour | 0 | 0.0000
527376 | C301 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.003.001.001. | 0.0000 | Labour | 0 | 0.0000
527376 | C301 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.003.001.001. | 0.0000 | Labour | 0 | 0.0000
527377 | C302 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.003.002.001. | 0.0000 | Labour | 0 | 0.0000
527377 | C302 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.003.002.001. | 0.0000 | Labour | 0 | 0.0000
527378 | C303 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.003.003.001. | 0.0000 | Labour | 0 | 0.0000
527378 | C303 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.003.003.001. | 0.0000 | Labour | 0 | 0.0000
527379 | C304 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.003.004.001. | 0.0000 | Labour | 0 | 0.0000
527379 | C304 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.003.004.001. | 0.0000 | Labour | 0 | 0.0000
527385 | C401 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
527385 | C401 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.004.001.001. | 0.0000 | Labour | 0 | 0.0000
527386 | C402 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
527386 | C402 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.004.002.001. | 0.0000 | Labour | 0 | 0.0000
527387 | C403 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
527387 | C403 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.004.003.001. | 0.0000 | Labour | 0 | 0.0000
527388 | C404 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
527388 | C404 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.004.004.001. | 0.0000 | Labour | 0 | 0.0000
527394 | C501 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.005.001.001. | 0.0000 | Labour | 0 | 0.0000
527394 | C501 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.005.001.001. | 0.0000 | Labour | 0 | 0.0000
527395 | C502 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.005.002.001. | 0.0000 | Labour | 0 | 0.0000
527395 | C502 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.005.002.001. | 0.0000 | Labour | 0 | 0.0000
527396 | C503 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.005.003.001. | 0.0000 | Labour | 0 | 0.0000
527396 | C503 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.005.003.001. | 0.0000 | Labour | 0 | 0.0000
527397 | C504 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.005.004.001. | 0.0000 | Labour | 0 | 0.0000
527397 | C504 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.005.004.001. | 0.0000 | Labour | 0 | 0.0000
527403 | C601 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.006.001.001. | 0.0000 | Labour | 0 | 0.0000
527403 | C601 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.006.001.001. | 0.0000 | Labour | 0 | 0.0000
527404 | C602 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.006.002.001. | 0.0000 | Labour | 0 | 0.0000
527404 | C602 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.006.002.001. | 0.0000 | Labour | 0 | 0.0000
527405 | C603 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.006.003.001. | 0.0000 | Labour | 0 | 0.0000
527405 | C603 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.006.003.001. | 0.0000 | Labour | 0 | 0.0000
527406 | C604 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.006.004.001. | 0.0000 | Labour | 0 | 0.0000
527406 | C604 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.006.004.001. | 0.0000 | Labour | 0 | 0.0000
527412 | C701 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.007.001.001. | 0.0000 | Labour | 0 | 0.0000
527412 | C701 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.007.001.001. | 0.0000 | Labour | 0 | 0.0000
527413 | C702 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.007.002.001. | 0.0000 | Labour | 0 | 0.0000
527413 | C702 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.007.002.001. | 0.0000 | Labour | 0 | 0.0000
527414 | C703 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.007.003.001. | 0.0000 | Labour | 0 | 0.0000
527414 | C703 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.007.003.001. | 0.0000 | Labour | 0 | 0.0000
527415 | C704 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.007.004.001. | 0.0000 | Labour | 0 | 0.0000
527415 | C704 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.007.004.001. | 0.0000 | Labour | 0 | 0.0000
527421 | C801 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.008.001.001. | 0.0000 | Labour | 0 | 0.0000
527421 | C801 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.008.001.001. | 0.0000 | Labour | 0 | 0.0000
527422 | C802 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.008.002.001. | 0.0000 | Labour | 0 | 0.0000
527422 | C802 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.008.002.001. | 0.0000 | Labour | 0 | 0.0000
527423 | C803 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.008.003.001. | 0.0000 | Labour | 0 | 0.0000
527423 | C803 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.008.003.001. | 0.0000 | Labour | 0 | 0.0000
527424 | C804 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.008.004.001. | 0.0000 | Labour | 0 | 0.0000
527424 | C804 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.008.004.001. | 0.0000 | Labour | 0 | 0.0000
527430 | C901 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.009.001.001. | 0.0000 | Labour | 0 | 0.0000
527430 | C901 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.009.001.001. | 0.0000 | Labour | 0 | 0.0000
527431 | C902 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.009.002.001. | 0.0000 | Labour | 0 | 0.0000
527431 | C902 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.009.002.001. | 0.0000 | Labour | 0 | 0.0000
527432 | C903 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.009.003.001. | 0.0000 | Labour | 0 | 0.0000
527432 | C903 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.009.003.001. | 0.0000 | Labour | 0 | 0.0000
527433 | C904 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.009.004.001. | 0.0000 | Labour | 0 | 0.0000
527433 | C904 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.009.004.001. | 0.0000 | Labour | 0 | 0.0000
527439 | C1001 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.010.001.001. | 0.0000 | Labour | 0 | 0.0000
527439 | C1001 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.010.001.001. | 0.0000 | Labour | 0 | 0.0000
527440 | C1002 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.010.002.001. | 0.0000 | Labour | 0 | 0.0000
527440 | C1002 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.010.002.001. | 0.0000 | Labour | 0 | 0.0000
527441 | C1003 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.010.003.001. | 0.0000 | Labour | 0 | 0.0000
527441 | C1003 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.010.003.001. | 0.0000 | Labour | 0 | 0.0000
527442 | C1004 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.010.004.001. | 0.0000 | Labour | 0 | 0.0000
527442 | C1004 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.010.004.001. | 0.0000 | Labour | 0 | 0.0000
527448 | C1101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.011.001.001. | 0.0000 | Labour | 0 | 0.0000
527448 | C1101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.011.001.001. | 0.0000 | Labour | 0 | 0.0000
527449 | C1102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.011.002.001. | 0.0000 | Labour | 0 | 0.0000
527449 | C1102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.011.002.001. | 0.0000 | Labour | 0 | 0.0000
527450 | C1103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.011.003.001. | 0.0000 | Labour | 0 | 0.0000
527450 | C1103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.011.003.001. | 0.0000 | Labour | 0 | 0.0000
527451 | C1104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.011.004.001. | 0.0000 | Labour | 0 | 0.0000
527451 | C1104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.011.004.001. | 0.0000 | Labour | 0 | 0.0000
527457 | C1201 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.012.001.001. | 0.0000 | Labour | 0 | 0.0000
527457 | C1201 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.012.001.001. | 0.0000 | Labour | 0 | 0.0000
527458 | C1202 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.012.002.001. | 0.0000 | Labour | 0 | 0.0000
527458 | C1202 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.012.002.001. | 0.0000 | Labour | 0 | 0.0000
527459 | C1203 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.012.003.001. | 0.0000 | Labour | 0 | 0.0000
527459 | C1203 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.012.003.001. | 0.0000 | Labour | 0 | 0.0000
527460 | C1204 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.012.004.001. | 0.0000 | Labour | 0 | 0.0000
527460 | C1204 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.012.004.001. | 0.0000 | Labour | 0 | 0.0000
527466 | C1301 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.013.001.001. | 0.0000 | Labour | 0 | 0.0000
527466 | C1301 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.013.001.001. | 0.0000 | Labour | 0 | 0.0000
527467 | C1302 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.013.002.001. | 0.0000 | Labour | 0 | 0.0000
527467 | C1302 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.013.002.001. | 0.0000 | Labour | 0 | 0.0000
527468 | C1303 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.013.003.001. | 0.0000 | Labour | 0 | 0.0000
527468 | C1303 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.013.003.001. | 0.0000 | Labour | 0 | 0.0000
527469 | C1304 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.013.004.001. | 0.0000 | Labour | 0 | 0.0000
527469 | C1304 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.013.004.001. | 0.0000 | Labour | 0 | 0.0000
527475 | C1401 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.014.001.001. | 0.0000 | Labour | 0 | 0.0000
527475 | C1401 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.014.001.001. | 0.0000 | Labour | 0 | 0.0000
527476 | C1402 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.014.002.001. | 0.0000 | Labour | 0 | 0.0000
527476 | C1402 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.014.002.001. | 0.0000 | Labour | 0 | 0.0000
527477 | C1403 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.014.003.001. | 0.0000 | Labour | 0 | 0.0000
527477 | C1403 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.014.003.001. | 0.0000 | Labour | 0 | 0.0000
527478 | C1404 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.014.004.001. | 0.0000 | Labour | 0 | 0.0000
527478 | C1404 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.014.004.001. | 0.0000 | Labour | 0 | 0.0000
527484 | C1501 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.015.001.001. | 0.0000 | Labour | 0 | 0.0000
527484 | C1501 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.015.001.001. | 0.0000 | Labour | 0 | 0.0000
527485 | C1502 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.015.002.001. | 0.0000 | Labour | 0 | 0.0000
527485 | C1502 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.015.002.001. | 0.0000 | Labour | 0 | 0.0000
527486 | C1503 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.015.003.001. | 0.0000 | Labour | 0 | 0.0000
527486 | C1503 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.015.003.001. | 0.0000 | Labour | 0 | 0.0000
527487 | C1504 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.015.004.001. | 0.0000 | Labour | 0 | 0.0000
527487 | C1504 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.015.004.001. | 0.0000 | Labour | 0 | 0.0000
527493 | C1601 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.016.001.001. | 0.0000 | Labour | 0 | 0.0000
527493 | C1601 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.016.001.001. | 0.0000 | Labour | 0 | 0.0000
527494 | C1602 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.016.002.001. | 0.0000 | Labour | 0 | 0.0000
527494 | C1602 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.016.002.001. | 0.0000 | Labour | 0 | 0.0000
527495 | C1603 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.016.003.001. | 0.0000 | Labour | 0 | 0.0000
527495 | C1603 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.016.003.001. | 0.0000 | Labour | 0 | 0.0000
527496 | C1604 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.016.004.001. | 0.0000 | Labour | 0 | 0.0000
527496 | C1604 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.016.004.001. | 0.0000 | Labour | 0 | 0.0000
527502 | C1701 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.017.001.001. | 0.0000 | Labour | 0 | 0.0000
527502 | C1701 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.017.001.001. | 0.0000 | Labour | 0 | 0.0000
527503 | C1702 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.017.002.001. | 0.0000 | Labour | 0 | 0.0000
527503 | C1702 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.017.002.001. | 0.0000 | Labour | 0 | 0.0000
527504 | C1703 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.017.003.001. | 0.0000 | Labour | 0 | 0.0000
527504 | C1703 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.017.003.001. | 0.0000 | Labour | 0 | 0.0000
527505 | C1704 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.017.004.001. | 0.0000 | Labour | 0 | 0.0000
527505 | C1704 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.017.004.001. | 0.0000 | Labour | 0 | 0.0000
527511 | C1801 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.018.001.001. | 0.0000 | Labour | 0 | 0.0000
527511 | C1801 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.018.001.001. | 0.0000 | Labour | 0 | 0.0000
527512 | C1802 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.018.002.001. | 0.0000 | Labour | 0 | 0.0000
527512 | C1802 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.018.002.001. | 0.0000 | Labour | 0 | 0.0000
527513 | C1803 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.018.003.001. | 0.0000 | Labour | 0 | 0.0000
527513 | C1803 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.018.003.001. | 0.0000 | Labour | 0 | 0.0000
527514 | C1804 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.018.004.001. | 0.0000 | Labour | 0 | 0.0000
527514 | C1804 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.018.004.001. | 0.0000 | Labour | 0 | 0.0000
527520 | C1901 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.019.001.001. | 0.0000 | Labour | 0 | 0.0000
527520 | C1901 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.019.001.001. | 0.0000 | Labour | 0 | 0.0000
527521 | C1902 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.019.002.001. | 0.0000 | Labour | 0 | 0.0000
527521 | C1902 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.019.002.001. | 0.0000 | Labour | 0 | 0.0000
527522 | C1903 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.019.003.001. | 0.0000 | Labour | 0 | 0.0000
527522 | C1903 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.019.003.001. | 0.0000 | Labour | 0 | 0.0000
527523 | C1904 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.019.004.001. | 0.0000 | Labour | 0 | 0.0000
527523 | C1904 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.019.004.001. | 0.0000 | Labour | 0 | 0.0000
527529 | C2001 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.020.001.001. | 0.0000 | Labour | 0 | 0.0000
527529 | C2001 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.020.001.001. | 0.0000 | Labour | 0 | 0.0000
527530 | C2002 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.020.002.001. | 0.0000 | Labour | 0 | 0.0000
527530 | C2002 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.020.002.001. | 0.0000 | Labour | 0 | 0.0000
527531 | C2003 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.020.003.001. | 0.0000 | Labour | 0 | 0.0000
527531 | C2003 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.020.003.001. | 0.0000 | Labour | 0 | 0.0000
527532 | C2004 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.020.004.001. | 0.0000 | Labour | 0 | 0.0000
527532 | C2004 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.020.004.001. | 0.0000 | Labour | 0 | 0.0000
527538 | C2101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.021.001.001. | 0.0000 | Labour | 0 | 0.0000
527538 | C2101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.021.001.001. | 0.0000 | Labour | 0 | 0.0000
527539 | C2102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.021.002.001. | 0.0000 | Labour | 0 | 0.0000
527539 | C2102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.021.002.001. | 0.0000 | Labour | 0 | 0.0000
527540 | C2103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.021.003.001. | 0.0000 | Labour | 0 | 0.0000
527540 | C2103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.021.003.001. | 0.0000 | Labour | 0 | 0.0000
527541 | C2104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.021.004.001. | 0.0000 | Labour | 0 | 0.0000
527541 | C2104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.021.004.001. | 0.0000 | Labour | 0 | 0.0000
527547 | C2201 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.022.001.001. | 0.0000 | Labour | 0 | 0.0000
527547 | C2201 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.022.001.001. | 0.0000 | Labour | 0 | 0.0000
527548 | C2202 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.022.002.001. | 0.0000 | Labour | 0 | 0.0000
527548 | C2202 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.022.002.001. | 0.0000 | Labour | 0 | 0.0000
527549 | C2203 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.022.003.001. | 0.0000 | Labour | 0 | 0.0000
527549 | C2203 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.022.003.001. | 0.0000 | Labour | 0 | 0.0000
527550 | C2204 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.022.004.001. | 0.0000 | Labour | 0 | 0.0000
527550 | C2204 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.022.004.001. | 0.0000 | Labour | 0 | 0.0000
527556 | C2301 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.023.001.001. | 0.0000 | Labour | 0 | 0.0000
527556 | C2301 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.023.001.001. | 0.0000 | Labour | 0 | 0.0000
527557 | C2302 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.023.002.001. | 0.0000 | Labour | 0 | 0.0000
527557 | C2302 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.023.002.001. | 0.0000 | Labour | 0 | 0.0000
527558 | C2303 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.023.003.001. | 0.0000 | Labour | 0 | 0.0000
527558 | C2303 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.023.003.001. | 0.0000 | Labour | 0 | 0.0000
527559 | C2304 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.023.004.001. | 0.0000 | Labour | 0 | 0.0000
527559 | C2304 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.023.004.001. | 0.0000 | Labour | 0 | 0.0000
527565 | C2401 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.024.001.001. | 0.0000 | Labour | 0 | 0.0000
527565 | C2401 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.024.001.001. | 0.0000 | Labour | 0 | 0.0000
527566 | C2402 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.024.002.001. | 0.0000 | Labour | 0 | 0.0000
527566 | C2402 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.024.002.001. | 0.0000 | Labour | 0 | 0.0000
527567 | C2403 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.024.003.001. | 0.0000 | Labour | 0 | 0.0000
527567 | C2403 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.024.003.001. | 0.0000 | Labour | 0 | 0.0000
527568 | C2404 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.024.004.001. | 0.0000 | Labour | 0 | 0.0000
527568 | C2404 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.024.004.001. | 0.0000 | Labour | 0 | 0.0000
527574 | C2501 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.025.001.001. | 0.0000 | Labour | 0 | 0.0000
527574 | C2501 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.025.001.001. | 0.0000 | Labour | 0 | 0.0000
527575 | C2502 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.025.002.001. | 0.0000 | Labour | 0 | 0.0000
527575 | C2502 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.025.002.001. | 0.0000 | Labour | 0 | 0.0000
527576 | C2503 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.025.003.001. | 0.0000 | Labour | 0 | 0.0000
527576 | C2503 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.025.003.001. | 0.0000 | Labour | 0 | 0.0000
527577 | C2504 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.025.004.001. | 0.0000 | Labour | 0 | 0.0000
527577 | C2504 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.025.004.001. | 0.0000 | Labour | 0 | 0.0000
527583 | C2601 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.026.001.001. | 0.0000 | Labour | 0 | 0.0000
527583 | C2601 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.026.001.001. | 0.0000 | Labour | 0 | 0.0000
527584 | C2602 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.026.002.001. | 0.0000 | Labour | 0 | 0.0000
527584 | C2602 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.026.002.001. | 0.0000 | Labour | 0 | 0.0000
527585 | C2603 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.026.003.001. | 0.0000 | Labour | 0 | 0.0000
527585 | C2603 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.026.003.001. | 0.0000 | Labour | 0 | 0.0000
527586 | C2604 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.026.004.001. | 0.0000 | Labour | 0 | 0.0000
527586 | C2604 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.026.004.001. | 0.0000 | Labour | 0 | 0.0000
527592 | C2701 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.027.001.001. | 0.0000 | Labour | 0 | 0.0000
527592 | C2701 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.027.001.001. | 0.0000 | Labour | 0 | 0.0000
527593 | C2702 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.027.002.001. | 0.0000 | Labour | 0 | 0.0000
527593 | C2702 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.027.002.001. | 0.0000 | Labour | 0 | 0.0000
527594 | C2703 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.027.003.001. | 0.0000 | Labour | 0 | 0.0000
527594 | C2703 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.027.003.001. | 0.0000 | Labour | 0 | 0.0000
527595 | C2704 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.027.004.001. | 0.0000 | Labour | 0 | 0.0000
527595 | C2704 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.027.004.001. | 0.0000 | Labour | 0 | 0.0000
527601 | C2801 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.028.001.001. | 0.0000 | Labour | 0 | 0.0000
527601 | C2801 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.028.001.001. | 0.0000 | Labour | 0 | 0.0000
527602 | C2802 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.028.002.001. | 0.0000 | Labour | 0 | 0.0000
527602 | C2802 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.028.002.001. | 0.0000 | Labour | 0 | 0.0000
527603 | C2803 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.028.003.001. | 0.0000 | Labour | 0 | 0.0000
527603 | C2803 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.028.003.001. | 0.0000 | Labour | 0 | 0.0000
527604 | C2804 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.028.004.001. | 0.0000 | Labour | 0 | 0.0000
527604 | C2804 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.028.004.001. | 0.0000 | Labour | 0 | 0.0000
527610 | C2901 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.029.001.001. | 0.0000 | Labour | 0 | 0.0000
527610 | C2901 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.029.001.001. | 0.0000 | Labour | 0 | 0.0000
527611 | C2902 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.029.002.001. | 0.0000 | Labour | 0 | 0.0000
527611 | C2902 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.029.002.001. | 0.0000 | Labour | 0 | 0.0000
527612 | C2903 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.029.003.001. | 0.0000 | Labour | 0 | 0.0000
527612 | C2903 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.029.003.001. | 0.0000 | Labour | 0 | 0.0000
527613 | C2904 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.029.004.001. | 0.0000 | Labour | 0 | 0.0000
527613 | C2904 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.029.004.001. | 0.0000 | Labour | 0 | 0.0000
527619 | C3001 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.030.001.001. | 0.0000 | Labour | 0 | 0.0000
527619 | C3001 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.030.001.001. | 0.0000 | Labour | 0 | 0.0000
527620 | C3002 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.030.002.001. | 0.0000 | Labour | 0 | 0.0000
527620 | C3002 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.030.002.001. | 0.0000 | Labour | 0 | 0.0000
527621 | C3003 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.030.003.001. | 0.0000 | Labour | 0 | 0.0000
527621 | C3003 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.030.003.001. | 0.0000 | Labour | 0 | 0.0000
527622 | C3004 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.030.004.001. | 0.0000 | Labour | 0 | 0.0000
527622 | C3004 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.030.004.001. | 0.0000 | Labour | 0 | 0.0000
527629 | C3101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 23 | 0.0000 | 34.005.004.005.003.004.031.001.001. | 0.0000 | Labour | 0 | 0.0000
527629 | C3101 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 12 | 0.0000 | 34.005.004.005.003.004.031.001.001. | 0.0000 | Labour | 0 | 0.0000
527630 | C3102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.031.002.001. | 0.0000 | Labour | 0 | 0.0000
527630 | C3102 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.031.002.001. | 0.0000 | Labour | 0 | 0.0000
527631 | C3103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 15.0000 | 0.0000 | 34.005.004.005.003.004.031.003.001. | 0.0000 | Labour | 0 | 0.0000
527631 | C3103 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 7.0000 | 0.0000 | 34.005.004.005.003.004.031.003.001. | 0.0000 | Labour | 0 | 0.0000
527632 | C3104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16578 | Vertical Core Cutting 125mm | No. | 17.0000 | 0.0000 | 34.005.004.005.003.004.031.004.001. | 0.0000 | Labour | 0 | 0.0000
527632 | C3104 Vertical Core Cut For Plumbing Work | No. | 1.0000 | 1.0000 | 16577 | Vertical Core Cutting 75mm | No. | 8.0000 | 0.0000 | 34.005.004.005.003.004.031.004.001. | 0.0000 | Labour | 0 | 0.0000