## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork | Selected Group :- G - Lift 1 AAC Blockwork
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 588071 | G - Lift 1 AAC Blockwork | NA | 0.0000 | 0.0000 | 0 | 588070 | 31 | 0 | [6 empty] | 0.0000
2 | 588072 | G GF Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
3 | 588073 | G 1st Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
4 | 588074 | G 2nd Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
5 | 588075 | G 3rd Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
6 | 588076 | G 4th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
7 | 588077 | G 5th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
8 | 588078 | G 6th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
9 | 588079 | G 7th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
10 | 588080 | G 8th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
11 | 588081 | G 9th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
12 | 588082 | G 10th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
13 | 588083 | G 11th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
14 | 588084 | G 12th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
15 | 588085 | G 13th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000
16 | 588086 | G 14th Floor Lift 1 AAC Blockwork | Sq.Ft | 22.9100 | 22.9100 | 1 | 588071 | 4 | 32573 | A Bldg Lift-2 AAC Bolckworkj | [5 empty] | 0.0000