## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork | Selected Group :- C - Lift 2 AAC Blockwork
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 588116 | C - Lift 2 AAC Blockwork | NA | 0.0000 | 0.0000 | 0 | 584123 | 31 | 0 | [6 empty] | 0.0000
2 | 588117 | C - GF Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
3 | 588118 | C - 1st Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
4 | 588119 | C - 2nd Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
5 | 588120 | C - 3rd Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
6 | 588121 | C - 4th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
7 | 588122 | C - 5th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
8 | 588123 | C - 6th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
9 | 588124 | C - 7th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
10 | 588125 | C - 8th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
11 | 588126 | C - 9th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
12 | 588127 | C - 10th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
13 | 588128 | C - 11th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
14 | 588129 | C - 12th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
15 | 588130 | C - 13th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 588116 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000