## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster | Selected Group :- C Lift 1 Plaster
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 588318 | C Lift 1 Plaster | NA | 0.0000 | 0.0000 | 0 | 584131 | 31 | 0 | [6 empty] | 0.0000
2 | 588319 | C - Gf Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
3 | 588320 | C - 1st Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
4 | 588321 | C - 2nd Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
5 | 588322 | C - 3rd Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
6 | 588323 | C - 4th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
7 | 588324 | C - 5th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
8 | 588325 | C - 6th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
9 | 588326 | C - 7th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
10 | 588327 | C - 8th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
11 | 588328 | C - 9th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
12 | 588329 | C - 10th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
13 | 588330 | C - 11th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
14 | 588331 | C - 12th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
15 | 588332 | C - 13th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
16 | 588333 | C - 14th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 588318 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000