## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work | Selected Group :- F- Brickwork/Plaster Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 601573 | F- Brickwork/Plaster Work | NA | 0.0000 | 0.0000 | 0 | 480658 | 31 | 0 | [6 empty] | 0.0000
2 | 601574 | F Brickwork | NA | 0.0000 | 0.0000 | 1 | 601573 | 31 | 0 | [6 empty] | 0.0000
3 | 601576 | F - Lift 1 AAC Blockwork | NA | 0.0000 | 0.0000 | 2 | 601574 | 31 | 0 | [6 empty] | 0.0000
4 | 601577 | F - GF Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
5 | 601578 | F - 1st Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
6 | 601579 | F - 2nd Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
7 | 601580 | F - 3rd Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
8 | 601581 | F - 4th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
9 | 601582 | F - 5th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
10 | 601583 | F - 6th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
11 | 601584 | F - 7th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
12 | 601585 | F - 8th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
13 | 601586 | F - 9th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
14 | 601587 | F - 10th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
15 | 601588 | F - 11th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
16 | 601589 | F - 12th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
17 | 601590 | F - 13th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
18 | 601591 | F - 14th Floor Lift 1 AAC Blockwork | No. | 1.0000 | 1.0000 | 3 | 601576 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
19 | 601592 | F - Lift 2 AAC Blockwork | NA | 0.0000 | 0.0000 | 2 | 601574 | 31 | 0 | [6 empty] | 0.0000
20 | 601593 | F - GF Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
21 | 601594 | F - 1st Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
22 | 601595 | F - 2nd Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
23 | 601596 | F - 3rd Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
24 | 601597 | F - 4th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
25 | 601598 | F - 5th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
26 | 601599 | F - 6th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
27 | 601600 | F - 7th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
28 | 601601 | F - 8th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
29 | 601602 | F - 9th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
30 | 601603 | F - 10th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
31 | 601604 | F - 11th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
32 | 601605 | F - 12th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
33 | 601606 | F - 13th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
34 | 601607 | F - 14th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 19 | 601592 | 4 | 34072 | G Lift 1 AAC Blockwork | [5 empty] | 0.0000
35 | 601575 | F Plaster | NA | 0.0000 | 0.0000 | 1 | 601573 | 31 | 0 | [6 empty] | 0.0000
36 | 601608 | F Lift 1 Plaster | NA | 0.0000 | 0.0000 | 35 | 601575 | 31 | 0 | [6 empty] | 0.0000
37 | 601609 | F - Gf Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
38 | 601610 | F - 1st Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
39 | 601611 | F - 2nd Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
40 | 601612 | F - 3rd Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
41 | 601613 | F - 4th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
42 | 601614 | F - 5th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
43 | 601615 | F - 6th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
44 | 601616 | F - 7th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
45 | 601617 | F - 8th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
46 | 601618 | F - 9th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
47 | 601619 | F - 10th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
48 | 601620 | F - 11th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
49 | 601621 | F - 12th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
50 | 601622 | F - 13th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
51 | 601623 | F - 14th Floor Lift 1 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 601608 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
52 | 601624 | F Lift 2 Plaster | NA | 0.0000 | 0.0000 | 35 | 601575 | 31 | 0 | [6 empty] | 0.0000
53 | 601625 | F - Gf Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
54 | 601626 | F - 1st Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
55 | 601627 | F - 2nd Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
56 | 601628 | F - 3rd Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
57 | 601629 | F - 4th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
58 | 601630 | F - 5th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
59 | 601631 | F - 6th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
60 | 601632 | F - 7th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
61 | 601633 | F - 8th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
62 | 601634 | F - 9th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
63 | 601635 | F - 10th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
64 | 601636 | F - 11th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
65 | 601637 | F - 12th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
66 | 601638 | F - 13th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000
67 | 601639 | F - 14th Floor Lift 2 Plaster Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 601624 | 4 | 34073 | G Lift 1 Sand Face Plaster | [5 empty] | 0.0000