## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 638213 | E - Umra Patti Work | NA | 0.0000 | 0.0000 | 0 | 636400 | 31 | 0 | [6 empty] | 0.0000
2 | 638214 | E - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
3 | 638215 | E - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
4 | 638216 | E -301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 3 | 638215 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
5 | 638217 | E - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
6 | 638218 | E -302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 5 | 638217 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
7 | 638219 | E - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
8 | 638220 | E -303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 7 | 638219 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
9 | 638221 | E - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
10 | 638222 | E -304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 9 | 638221 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
11 | 638223 | E - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
12 | 638224 | E -305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 11 | 638223 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
13 | 638225 | E - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
14 | 638226 | E -306 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 13 | 638225 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
15 | 638227 | E - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
16 | 638228 | E -307 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 15 | 638227 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
17 | 638229 | E - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
18 | 638230 | E -308 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 17 | 638229 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
19 | 638231 | E - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
20 | 638232 | E -309 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 19 | 638231 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
21 | 638233 | E - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
22 | 638234 | E -310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 21 | 638233 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
23 | 638235 | E - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
24 | 638236 | E -311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 23 | 638235 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
25 | 638237 | E - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
26 | 638238 | E -312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 25 | 638237 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
27 | 638239 | E - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
28 | 638240 | E -313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 27 | 638239 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
29 | 638241 | E - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 638214 | 31 | 0 | [6 empty] | 0.0000
30 | 638242 | E -314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 29 | 638241 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
31 | 638243 | E - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
32 | 638244 | E - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
33 | 638245 | E -401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 32 | 638244 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
34 | 638246 | E - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
35 | 638247 | E -402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 34 | 638246 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
36 | 638248 | E - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
37 | 638249 | E -403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 36 | 638248 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
38 | 638250 | E - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
39 | 638251 | E -404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 38 | 638250 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
40 | 638252 | E - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
41 | 638253 | E -405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 40 | 638252 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
42 | 638254 | E - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
43 | 638255 | E -406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 42 | 638254 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
44 | 638256 | E - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
45 | 638257 | E -407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 44 | 638256 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
46 | 638258 | E - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
47 | 638259 | E -408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 46 | 638258 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
48 | 638260 | E - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
49 | 638261 | E -409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 48 | 638260 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
50 | 638262 | E - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
51 | 638263 | E -410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 50 | 638262 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
52 | 638264 | E - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
53 | 638265 | E -411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 52 | 638264 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
54 | 638266 | E - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
55 | 638267 | E -412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 54 | 638266 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
56 | 638268 | E - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
57 | 638269 | E -413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 56 | 638268 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
58 | 638270 | E - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 638243 | 31 | 0 | [6 empty] | 0.0000
59 | 638271 | E -414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 58 | 638270 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
60 | 638272 | E - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
61 | 638273 | E - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
62 | 638274 | E -501 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 61 | 638273 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
63 | 638275 | E - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
64 | 638276 | E -502 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 63 | 638275 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
65 | 638277 | E - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
66 | 638278 | E -503 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 65 | 638277 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
67 | 638279 | E - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
68 | 638280 | E -504 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 67 | 638279 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
69 | 638281 | E - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
70 | 638282 | E -505 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 69 | 638281 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
71 | 638283 | E - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
72 | 638284 | E -506 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 71 | 638283 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
73 | 638285 | E - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
74 | 638286 | E -507 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 73 | 638285 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
75 | 638287 | E - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
76 | 638288 | E -508 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 75 | 638287 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
77 | 638289 | E - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
78 | 638290 | E -509 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 77 | 638289 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
79 | 638291 | E - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
80 | 638292 | E -510 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 79 | 638291 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
81 | 638293 | E - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
82 | 638294 | E -511 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 81 | 638293 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
83 | 638295 | E - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
84 | 638296 | E -512 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 83 | 638295 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
85 | 638297 | E - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
86 | 638298 | E -513 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 85 | 638297 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
87 | 638299 | E - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 638272 | 31 | 0 | [6 empty] | 0.0000
88 | 638300 | E -514 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 87 | 638299 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
89 | 638301 | E - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
90 | 638302 | E - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
91 | 638303 | E -601 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 90 | 638302 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
92 | 638304 | E - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
93 | 638305 | E -602 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 92 | 638304 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
94 | 638306 | E - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
95 | 638307 | E -603 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 94 | 638306 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
96 | 638308 | E - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
97 | 638309 | E -604 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 96 | 638308 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
98 | 638310 | E - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
99 | 638311 | E -605 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 98 | 638310 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
100 | 638312 | E - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
101 | 638313 | E -606 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 100 | 638312 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
102 | 638314 | E - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
103 | 638315 | E -607 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 102 | 638314 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
104 | 638316 | E - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
105 | 638317 | E -608 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 104 | 638316 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
106 | 638318 | E - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
107 | 638319 | E -609 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 106 | 638318 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
108 | 638320 | E - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
109 | 638321 | E -610 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 108 | 638320 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
110 | 638322 | E - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
111 | 638323 | E -611 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 110 | 638322 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
112 | 638324 | E - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
113 | 638325 | E -612 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 112 | 638324 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
114 | 638326 | E - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
115 | 638327 | E -613 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 114 | 638326 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
116 | 638328 | E - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 638301 | 31 | 0 | [6 empty] | 0.0000
117 | 638329 | E -614 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 116 | 638328 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
118 | 638330 | E - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
119 | 638331 | E - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
120 | 638332 | E -701 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 119 | 638331 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
121 | 638333 | E - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
122 | 638334 | E -702 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 121 | 638333 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
123 | 638335 | E - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
124 | 638336 | E -703 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 123 | 638335 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
125 | 638337 | E - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
126 | 638338 | E -704 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 125 | 638337 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
127 | 638339 | E - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
128 | 638340 | E -705 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 127 | 638339 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
129 | 638341 | E - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
130 | 638342 | E -706 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 129 | 638341 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
131 | 638343 | E - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
132 | 638344 | E -707 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 131 | 638343 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
133 | 638345 | E - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
134 | 638346 | E -708 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 133 | 638345 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
135 | 638347 | E - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
136 | 638348 | E -709 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 135 | 638347 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
137 | 638349 | E - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
138 | 638350 | E -710 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 137 | 638349 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
139 | 638351 | E - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
140 | 638352 | E -711 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 139 | 638351 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
141 | 638353 | E - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
142 | 638354 | E -712 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 141 | 638353 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
143 | 638355 | E - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
144 | 638356 | E -713 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 143 | 638355 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
145 | 638357 | E - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 638330 | 31 | 0 | [6 empty] | 0.0000
146 | 638358 | E -714 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 145 | 638357 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
147 | 638359 | E - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
148 | 638360 | E - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
149 | 638361 | E -801 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 148 | 638360 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
150 | 638362 | E - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
151 | 638363 | E -802 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 150 | 638362 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
152 | 638364 | E - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
153 | 638365 | E -803 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 152 | 638364 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
154 | 638366 | E - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
155 | 638367 | E -804 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 154 | 638366 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
156 | 638368 | E - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
157 | 638369 | E -805 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 156 | 638368 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
158 | 638370 | E - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
159 | 638371 | E -806 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 158 | 638370 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
160 | 638372 | E - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
161 | 638373 | E -807 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 160 | 638372 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
162 | 638374 | E - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
163 | 638375 | E -808 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 162 | 638374 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
164 | 638376 | E - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
165 | 638377 | E -809 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 164 | 638376 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
166 | 638378 | E - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
167 | 638379 | E -810 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 166 | 638378 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
168 | 638380 | E - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
169 | 638381 | E -811 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 168 | 638380 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
170 | 638382 | E - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
171 | 638383 | E -812 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 170 | 638382 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
172 | 638384 | E - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
173 | 638385 | E -813 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 172 | 638384 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
174 | 638386 | E - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 638359 | 31 | 0 | [6 empty] | 0.0000
175 | 638387 | E -814 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 174 | 638386 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
176 | 638388 | E - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
177 | 638389 | E - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
178 | 638390 | E -901 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 177 | 638389 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
179 | 638391 | E - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
180 | 638392 | E -902 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 179 | 638391 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
181 | 638393 | E - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
182 | 638394 | E -903 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 181 | 638393 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
183 | 638395 | E - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
184 | 638396 | E -904 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 183 | 638395 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
185 | 638397 | E - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
186 | 638398 | E -905 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 185 | 638397 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
187 | 638399 | E - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
188 | 638400 | E -906 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 187 | 638399 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
189 | 638401 | E - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
190 | 638402 | E -907 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 189 | 638401 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
191 | 638403 | E - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
192 | 638404 | E -908 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 191 | 638403 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
193 | 638405 | E - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
194 | 638406 | E -909 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 193 | 638405 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
195 | 638407 | E - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
196 | 638408 | E -910 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 195 | 638407 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
197 | 638409 | E - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
198 | 638410 | E -911 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 197 | 638409 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
199 | 638411 | E - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
200 | 638412 | E -912 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 199 | 638411 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
201 | 638413 | E - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
202 | 638414 | E -913 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 201 | 638413 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
203 | 638415 | E - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 638388 | 31 | 0 | [6 empty] | 0.0000
204 | 638416 | E -914 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 203 | 638415 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
205 | 638417 | E - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
206 | 638418 | E - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
207 | 638419 | E -1001 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 206 | 638418 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
208 | 638420 | E - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
209 | 638421 | E -1002 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 208 | 638420 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
210 | 638422 | E - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
211 | 638423 | E -1003 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 210 | 638422 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
212 | 638424 | E - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
213 | 638425 | E -1004 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 212 | 638424 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
214 | 638426 | E - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
215 | 638427 | E -1005 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 214 | 638426 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
216 | 638428 | E - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
217 | 638429 | E -1006 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 216 | 638428 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
218 | 638430 | E - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
219 | 638431 | E -1007 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 218 | 638430 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
220 | 638432 | E - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
221 | 638433 | E -1008 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 220 | 638432 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
222 | 638434 | E - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
223 | 638435 | E -1009 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 222 | 638434 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
224 | 638436 | E - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
225 | 638437 | E -1010 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 224 | 638436 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
226 | 638438 | E - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
227 | 638439 | E -1011 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 226 | 638438 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
228 | 638440 | E - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
229 | 638441 | E -1012 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 228 | 638440 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
230 | 638442 | E - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
231 | 638443 | E -1013 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 230 | 638442 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
232 | 638444 | E - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 638417 | 31 | 0 | [6 empty] | 0.0000
233 | 638445 | E -1014 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 232 | 638444 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
234 | 638446 | E - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
235 | 638447 | E - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
236 | 638448 | E -1101 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 235 | 638447 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
237 | 638449 | E - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
238 | 638450 | E -1102 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 237 | 638449 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
239 | 638451 | E - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
240 | 638452 | E -1103 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 239 | 638451 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
241 | 638453 | E - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
242 | 638454 | E -1104 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 241 | 638453 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
243 | 638455 | E - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
244 | 638456 | E -1105 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 243 | 638455 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
245 | 638457 | E - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
246 | 638458 | E -1106 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 245 | 638457 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
247 | 638459 | E - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
248 | 638460 | E -1107 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 247 | 638459 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
249 | 638461 | E - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
250 | 638462 | E -1108 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 249 | 638461 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
251 | 638463 | E - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
252 | 638464 | E -1109 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 251 | 638463 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
253 | 638465 | E - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
254 | 638466 | E -1110 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 253 | 638465 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
255 | 638467 | E - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
256 | 638468 | E -1111 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 255 | 638467 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
257 | 638469 | E - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
258 | 638470 | E -1112 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 257 | 638469 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
259 | 638471 | E - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
260 | 638472 | E -1113 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 259 | 638471 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
261 | 638473 | E - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 638446 | 31 | 0 | [6 empty] | 0.0000
262 | 638474 | E -1114 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 261 | 638473 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
263 | 638475 | E - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
264 | 638476 | E - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
265 | 638477 | E -1201 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 264 | 638476 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
266 | 638478 | E - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
267 | 638479 | E -1202 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 266 | 638478 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
268 | 638480 | E - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
269 | 638481 | E -1203 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 268 | 638480 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
270 | 638482 | E - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
271 | 638483 | E -1204 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 270 | 638482 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
272 | 638484 | E - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
273 | 638485 | E -1205 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 272 | 638484 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
274 | 638486 | E - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
275 | 638487 | E -1206 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 274 | 638486 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
276 | 638488 | E - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
277 | 638489 | E -1207 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 276 | 638488 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
278 | 638490 | E - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
279 | 638491 | E -1208 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 278 | 638490 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
280 | 638492 | E - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
281 | 638493 | E -1209 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 280 | 638492 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
282 | 638494 | E - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
283 | 638495 | E -1210 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 282 | 638494 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
284 | 638496 | E - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
285 | 638497 | E -1211 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 284 | 638496 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
286 | 638498 | E - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
287 | 638499 | E -1212 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 286 | 638498 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
288 | 638500 | E - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
289 | 638501 | E -1213 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 288 | 638500 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
290 | 638502 | E - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 638475 | 31 | 0 | [6 empty] | 0.0000
291 | 638503 | E -1214 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 290 | 638502 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
292 | 638504 | E - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
293 | 638505 | E - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
294 | 638506 | E -1301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 293 | 638505 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
295 | 638507 | E - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
296 | 638508 | E -1302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 295 | 638507 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
297 | 638509 | E - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
298 | 638510 | E -1303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 297 | 638509 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
299 | 638511 | E - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
300 | 638512 | E -1304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 299 | 638511 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
301 | 638513 | E - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
302 | 638514 | E -1305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 301 | 638513 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
303 | 638515 | E - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
304 | 638516 | E -1306 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 303 | 638515 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
305 | 638517 | E - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
306 | 638518 | E -1307 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 305 | 638517 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
307 | 638519 | E - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
308 | 638520 | E -1308 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 307 | 638519 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
309 | 638521 | E - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
310 | 638522 | E -1309 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 309 | 638521 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
311 | 638523 | E - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
312 | 638524 | E -1310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 311 | 638523 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
313 | 638525 | E - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
314 | 638526 | E -1311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 313 | 638525 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
315 | 638527 | E - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
316 | 638528 | E -1312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 315 | 638527 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
317 | 638529 | E - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
318 | 638530 | E -1313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 317 | 638529 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
319 | 638531 | E - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 638504 | 31 | 0 | [6 empty] | 0.0000
320 | 638532 | E -1314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 319 | 638531 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
321 | 638533 | E - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 638213 | 31 | 0 | [6 empty] | 0.0000
322 | 638534 | E - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
323 | 638535 | E -1401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 322 | 638534 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
324 | 638536 | E - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
325 | 638537 | E -1402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 324 | 638536 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
326 | 638538 | E - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
327 | 638539 | E -1403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 326 | 638538 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
328 | 638540 | E - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
329 | 638541 | E -1404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 328 | 638540 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
330 | 638542 | E - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
331 | 638543 | E -1405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 330 | 638542 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
332 | 638544 | E - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
333 | 638545 | E -1406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 332 | 638544 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
334 | 638546 | E - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
335 | 638547 | E -1407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 334 | 638546 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
336 | 638548 | E - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
337 | 638549 | E -1408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 336 | 638548 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
338 | 638550 | E - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
339 | 638551 | E -1409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 338 | 638550 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
340 | 638552 | E - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
341 | 638553 | E -1410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 340 | 638552 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
342 | 638554 | E - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
343 | 638555 | E -1411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 342 | 638554 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
344 | 638556 | E - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
345 | 638557 | E -1412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 344 | 638556 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
346 | 638558 | E - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
347 | 638559 | E -1413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 346 | 638558 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
348 | 638560 | E - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 638533 | 31 | 0 | [6 empty] | 0.0000
349 | 638561 | E -1414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 348 | 638560 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000