## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 638911 | E - Kitchen Otta | NA | 0.0000 | 0.0000 | 0 | 636400 | 31 | 0 | [6 empty] | 0.0000
2 | 638912 | E - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
3 | 638913 | E - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
4 | 638914 | E -301 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 3 | 638913 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
5 | 638915 | E - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
6 | 638916 | E -302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 5 | 638915 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
7 | 638917 | E - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
8 | 638918 | E -303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 7 | 638917 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
9 | 638919 | E - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
10 | 638920 | E -304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 9 | 638919 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
11 | 638921 | E - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
12 | 638922 | E -305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 11 | 638921 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
13 | 638923 | E - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
14 | 638924 | E -306 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 13 | 638923 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
15 | 638925 | E - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
16 | 638926 | E -307 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 15 | 638925 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
17 | 638927 | E - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
18 | 638928 | E -308 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 17 | 638927 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
19 | 638929 | E - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
20 | 638930 | E -309 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 19 | 638929 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
21 | 638931 | E - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
22 | 638932 | E -310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 21 | 638931 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
23 | 638933 | E - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
24 | 638934 | E -311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 23 | 638933 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
25 | 638935 | E - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
26 | 638936 | E -312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 25 | 638935 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
27 | 638937 | E - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
28 | 638938 | E -313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 27 | 638937 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
29 | 638939 | E - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 638912 | 31 | 0 | [6 empty] | 0.0000
30 | 638940 | E -314 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 29 | 638939 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
31 | 638941 | E - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
32 | 638942 | E - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
33 | 638943 | E -401 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 32 | 638942 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
34 | 638944 | E - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
35 | 638945 | E -402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 34 | 638944 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
36 | 638946 | E - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
37 | 638947 | E -403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 36 | 638946 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
38 | 638948 | E - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
39 | 638949 | E -404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 38 | 638948 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
40 | 638950 | E - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
41 | 638951 | E -405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 40 | 638950 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
42 | 638952 | E - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
43 | 638953 | E -406 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 42 | 638952 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
44 | 638954 | E - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
45 | 638955 | E -407 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 44 | 638954 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
46 | 638956 | E - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
47 | 638957 | E -408 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 46 | 638956 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
48 | 638958 | E - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
49 | 638959 | E -409 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 48 | 638958 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
50 | 638960 | E - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
51 | 638961 | E -410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 50 | 638960 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
52 | 638962 | E - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
53 | 638963 | E -411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 52 | 638962 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
54 | 638964 | E - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
55 | 638965 | E -412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 54 | 638964 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
56 | 638966 | E - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
57 | 638967 | E -413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 56 | 638966 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
58 | 638968 | E - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 638941 | 31 | 0 | [6 empty] | 0.0000
59 | 638969 | E -414 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 58 | 638968 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
60 | 638970 | E - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
61 | 638971 | E - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
62 | 638972 | E -501 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 61 | 638971 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
63 | 638973 | E - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
64 | 638974 | E -502 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 63 | 638973 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
65 | 638975 | E - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
66 | 638976 | E -503 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 65 | 638975 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
67 | 638977 | E - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
68 | 638978 | E -504 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 67 | 638977 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
69 | 638979 | E - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
70 | 638980 | E -505 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 69 | 638979 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
71 | 638981 | E - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
72 | 638982 | E -506 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 71 | 638981 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
73 | 638983 | E - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
74 | 638984 | E -507 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 73 | 638983 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
75 | 638985 | E - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
76 | 638986 | E -508 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 75 | 638985 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
77 | 638987 | E - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
78 | 638988 | E -509 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 77 | 638987 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
79 | 638989 | E - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
80 | 638990 | E -510 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 79 | 638989 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
81 | 638991 | E - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
82 | 638992 | E -511 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 81 | 638991 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
83 | 638993 | E - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
84 | 638994 | E -512 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 83 | 638993 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
85 | 638995 | E - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
86 | 638996 | E -513 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 85 | 638995 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
87 | 638997 | E - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 638970 | 31 | 0 | [6 empty] | 0.0000
88 | 638998 | E -514 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 87 | 638997 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
89 | 638999 | E - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
90 | 639000 | E - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
91 | 639001 | E -601 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 90 | 639000 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
92 | 639002 | E - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
93 | 639003 | E -602 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 92 | 639002 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
94 | 639004 | E - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
95 | 639005 | E -603 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 94 | 639004 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
96 | 639006 | E - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
97 | 639007 | E -604 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 96 | 639006 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
98 | 639008 | E - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
99 | 639009 | E -605 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 98 | 639008 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
100 | 639010 | E - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
101 | 639011 | E -606 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 100 | 639010 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
102 | 639012 | E - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
103 | 639013 | E -607 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 102 | 639012 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
104 | 639014 | E - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
105 | 639015 | E -608 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 104 | 639014 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
106 | 639016 | E - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
107 | 639017 | E -609 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 106 | 639016 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
108 | 639018 | E - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
109 | 639019 | E -610 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 108 | 639018 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
110 | 639020 | E - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
111 | 639021 | E -611 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 110 | 639020 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
112 | 639022 | E - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
113 | 639023 | E -612 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 112 | 639022 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
114 | 639024 | E - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
115 | 639025 | E -613 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 114 | 639024 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
116 | 639026 | E - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 638999 | 31 | 0 | [6 empty] | 0.0000
117 | 639027 | E -614 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 116 | 639026 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
118 | 639028 | E - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
119 | 639029 | E - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
120 | 639030 | E -701 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 119 | 639029 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
121 | 639031 | E - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
122 | 639032 | E -702 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 121 | 639031 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
123 | 639033 | E - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
124 | 639034 | E -703 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 123 | 639033 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
125 | 639035 | E - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
126 | 639036 | E -704 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 125 | 639035 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
127 | 639037 | E - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
128 | 639038 | E -705 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 127 | 639037 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
129 | 639039 | E - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
130 | 639040 | E -706 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 129 | 639039 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
131 | 639041 | E - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
132 | 639042 | E -707 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 131 | 639041 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
133 | 639043 | E - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
134 | 639044 | E -708 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 133 | 639043 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
135 | 639045 | E - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
136 | 639046 | E -709 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 135 | 639045 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
137 | 639047 | E - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
138 | 639048 | E -710 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 137 | 639047 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
139 | 639049 | E - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
140 | 639050 | E -711 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 139 | 639049 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
141 | 639051 | E - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
142 | 639052 | E -712 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 141 | 639051 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
143 | 639053 | E - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
144 | 639054 | E -713 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 143 | 639053 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
145 | 639055 | E - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 639028 | 31 | 0 | [6 empty] | 0.0000
146 | 639056 | E -714 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 145 | 639055 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
147 | 639057 | E - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
148 | 639058 | E - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
149 | 639059 | E -801 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 148 | 639058 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
150 | 639060 | E - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
151 | 639061 | E -802 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 150 | 639060 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
152 | 639062 | E - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
153 | 639063 | E -803 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 152 | 639062 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
154 | 639064 | E - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
155 | 639065 | E -804 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 154 | 639064 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
156 | 639066 | E - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
157 | 639067 | E -805 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 156 | 639066 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
158 | 639068 | E - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
159 | 639069 | E -806 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 158 | 639068 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
160 | 639070 | E - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
161 | 639071 | E -807 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 160 | 639070 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
162 | 639072 | E - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
163 | 639073 | E -808 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 162 | 639072 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
164 | 639074 | E - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
165 | 639075 | E -809 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 164 | 639074 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
166 | 639076 | E - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
167 | 639077 | E -810 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 166 | 639076 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
168 | 639078 | E - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
169 | 639079 | E -811 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 168 | 639078 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
170 | 639080 | E - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
171 | 639081 | E -812 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 170 | 639080 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
172 | 639082 | E - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
173 | 639083 | E -813 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 172 | 639082 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
174 | 639084 | E - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 639057 | 31 | 0 | [6 empty] | 0.0000
175 | 639085 | E -814 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 174 | 639084 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
176 | 639086 | E - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
177 | 639087 | E - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
178 | 639088 | E -901 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 177 | 639087 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
179 | 639089 | E - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
180 | 639090 | E -902 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 179 | 639089 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
181 | 639091 | E - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
182 | 639092 | E -903 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 181 | 639091 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
183 | 639093 | E - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
184 | 639094 | E -904 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 183 | 639093 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
185 | 639095 | E - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
186 | 639096 | E -905 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 185 | 639095 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
187 | 639097 | E - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
188 | 639098 | E -906 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 187 | 639097 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
189 | 639099 | E - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
190 | 639100 | E -907 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 189 | 639099 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
191 | 639101 | E - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
192 | 639102 | E -908 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 191 | 639101 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
193 | 639103 | E - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
194 | 639104 | E -909 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 193 | 639103 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
195 | 639105 | E - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
196 | 639106 | E -910 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 195 | 639105 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
197 | 639107 | E - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
198 | 639108 | E -911 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 197 | 639107 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
199 | 639109 | E - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
200 | 639110 | E -912 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 199 | 639109 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
201 | 639111 | E - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
202 | 639112 | E -913 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 201 | 639111 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
203 | 639113 | E - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 639086 | 31 | 0 | [6 empty] | 0.0000
204 | 639114 | E -914 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 203 | 639113 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
205 | 639115 | E - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
206 | 639116 | E - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
207 | 639117 | E -1001 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 206 | 639116 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
208 | 639118 | E - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
209 | 639119 | E -1002 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 208 | 639118 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
210 | 639120 | E - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
211 | 639121 | E -1003 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 210 | 639120 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
212 | 639122 | E - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
213 | 639123 | E -1004 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 212 | 639122 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
214 | 639124 | E - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
215 | 639125 | E -1005 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 214 | 639124 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
216 | 639126 | E - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
217 | 639127 | E -1006 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 216 | 639126 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
218 | 639128 | E - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
219 | 639129 | E -1007 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 218 | 639128 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
220 | 639130 | E - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
221 | 639131 | E -1008 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 220 | 639130 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
222 | 639132 | E - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
223 | 639133 | E -1009 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 222 | 639132 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
224 | 639134 | E - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
225 | 639135 | E -1010 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 224 | 639134 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
226 | 639136 | E - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
227 | 639137 | E -1011 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 226 | 639136 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
228 | 639138 | E - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
229 | 639139 | E -1012 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 228 | 639138 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
230 | 639140 | E - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
231 | 639141 | E -1013 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 230 | 639140 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
232 | 639142 | E - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 639115 | 31 | 0 | [6 empty] | 0.0000
233 | 639143 | E -1014 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 232 | 639142 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
234 | 639144 | E - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
235 | 639145 | E - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
236 | 639146 | E -1101 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 235 | 639145 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
237 | 639147 | E - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
238 | 639148 | E -1102 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 237 | 639147 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
239 | 639149 | E - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
240 | 639150 | E -1103 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 239 | 639149 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
241 | 639151 | E - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
242 | 639152 | E -1104 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 241 | 639151 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
243 | 639153 | E - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
244 | 639154 | E -1105 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 243 | 639153 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
245 | 639155 | E - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
246 | 639156 | E -1106 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 245 | 639155 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
247 | 639157 | E - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
248 | 639158 | E -1107 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 247 | 639157 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
249 | 639159 | E - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
250 | 639160 | E -1108 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 249 | 639159 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
251 | 639161 | E - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
252 | 639162 | E -1109 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 251 | 639161 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
253 | 639163 | E - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
254 | 639164 | E -1110 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 253 | 639163 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
255 | 639165 | E - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
256 | 639166 | E -1111 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 255 | 639165 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
257 | 639167 | E - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
258 | 639168 | E -1112 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 257 | 639167 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
259 | 639169 | E - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
260 | 639170 | E -1113 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 259 | 639169 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
261 | 639171 | E - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 639144 | 31 | 0 | [6 empty] | 0.0000
262 | 639172 | E -1114 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 261 | 639171 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
263 | 639173 | E - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
264 | 639174 | E - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
265 | 639175 | E -1201 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 264 | 639174 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
266 | 639176 | E - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
267 | 639177 | E -1202 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 266 | 639176 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
268 | 639178 | E - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
269 | 639179 | E -1203 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 268 | 639178 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
270 | 639180 | E - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
271 | 639181 | E -1204 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 270 | 639180 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
272 | 639182 | E - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
273 | 639183 | E -1205 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 272 | 639182 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
274 | 639184 | E - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
275 | 639185 | E -1206 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 274 | 639184 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
276 | 639186 | E - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
277 | 639187 | E -1207 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 276 | 639186 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
278 | 639188 | E - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
279 | 639189 | E -1208 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 278 | 639188 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
280 | 639190 | E - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
281 | 639191 | E -1209 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 280 | 639190 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
282 | 639192 | E - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
283 | 639193 | E -1210 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 282 | 639192 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
284 | 639194 | E - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
285 | 639195 | E -1211 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 284 | 639194 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
286 | 639196 | E - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
287 | 639197 | E -1212 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 286 | 639196 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
288 | 639198 | E - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
289 | 639199 | E -1213 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 288 | 639198 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
290 | 639200 | E - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 639173 | 31 | 0 | [6 empty] | 0.0000
291 | 639201 | E -1214 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 290 | 639200 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
292 | 639202 | E - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
293 | 639203 | E - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
294 | 639204 | E -1301 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 293 | 639203 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
295 | 639205 | E - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
296 | 639206 | E -1302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 295 | 639205 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
297 | 639207 | E - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
298 | 639208 | E -1303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 297 | 639207 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
299 | 639209 | E - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
300 | 639210 | E -1304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 299 | 639209 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
301 | 639211 | E - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
302 | 639212 | E -1305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 301 | 639211 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
303 | 639213 | E - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
304 | 639214 | E -1306 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 303 | 639213 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
305 | 639215 | E - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
306 | 639216 | E -1307 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 305 | 639215 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
307 | 639217 | E - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
308 | 639218 | E -1308 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 307 | 639217 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
309 | 639219 | E - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
310 | 639220 | E -1309 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 309 | 639219 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
311 | 639221 | E - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
312 | 639222 | E -1310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 311 | 639221 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
313 | 639223 | E - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
314 | 639224 | E -1311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 313 | 639223 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
315 | 639225 | E - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
316 | 639226 | E -1312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 315 | 639225 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
317 | 639227 | E - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
318 | 639228 | E -1313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 317 | 639227 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
319 | 639229 | E - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 639202 | 31 | 0 | [6 empty] | 0.0000
320 | 639230 | E -1314 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 319 | 639229 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
321 | 639231 | E - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 638911 | 31 | 0 | [6 empty] | 0.0000
322 | 639232 | E - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
323 | 639233 | E -1401 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 322 | 639232 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
324 | 639234 | E - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
325 | 639235 | E -1402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 324 | 639234 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
326 | 639236 | E - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
327 | 639237 | E -1403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 326 | 639236 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
328 | 639238 | E - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
329 | 639239 | E -1404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 328 | 639238 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
330 | 639240 | E - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
331 | 639241 | E -1405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 330 | 639240 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
332 | 639242 | E - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
333 | 639243 | E -1406 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 332 | 639242 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
334 | 639244 | E - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
335 | 639245 | E -1407 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 334 | 639244 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
336 | 639246 | E - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
337 | 639247 | E -1408 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 336 | 639246 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
338 | 639248 | E - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
339 | 639249 | E -1409 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 338 | 639248 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
340 | 639250 | E - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
341 | 639251 | E -1410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 340 | 639250 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
342 | 639252 | E - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
343 | 639253 | E -1411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 342 | 639252 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
344 | 639254 | E - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
345 | 639255 | E -1412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 344 | 639254 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
346 | 639256 | E - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
347 | 639257 | E -1413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 346 | 639256 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
348 | 639258 | E - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 639231 | 31 | 0 | [6 empty] | 0.0000
349 | 639259 | E -1414 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 348 | 639258 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000