## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L)
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 660745 | D - Staircase Riser Plaster (L) | NA | 0.0000 | 0.0000 | 0 | 601434 | 31 | 0 | [6 empty] | 0.0000
2 | 660746 | D -Staircase 1 | NA | 0.0000 | 0.0000 | 1 | 660745 | 31 | 0 | [6 empty] | 0.0000
3 | 660747 | D - G.F. Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
4 | 660748 | D - 1st Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
5 | 660749 | D - 2nd Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
6 | 660750 | D - 3rd Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
7 | 660751 | D - 4th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
8 | 660752 | D - 5th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
9 | 660753 | D - 6th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
10 | 660754 | D - 7th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
11 | 660755 | D - 8th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
12 | 660756 | D - 9th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
13 | 660757 | D - 10th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
14 | 660758 | D - 11th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
15 | 660772 | D - 12th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
16 | 660773 | D - 13th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
17 | 660774 | D - 14th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 660746 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
18 | 660759 | D -Staircase 2 | NA | 0.0000 | 0.0000 | 1 | 660745 | 31 | 0 | [6 empty] | 0.0000
19 | 660760 | D - G.F. Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
20 | 660761 | D - 1st Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
21 | 660762 | D - 2nd Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
22 | 660763 | D - 3rd Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
23 | 660764 | D - 4th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
24 | 660765 | D - 5th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
25 | 660766 | D - 6th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
26 | 660767 | D - 7th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
27 | 660768 | D - 8th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
28 | 660769 | D - 9th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
29 | 660770 | D - 10th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
30 | 660771 | D - 11th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
31 | 660775 | D - 12th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
32 | 660776 | D - 13th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
33 | 660777 | D - 14th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 18 | 660759 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000