## Sheet1
Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS
Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster | Selected Group :- C Ledge wall plaster
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 438690 | C Ledge wall plaster | NA | 0.0000 | 0.0000 | 0 | 438532 | 31 | 0 | [6 empty] | 0.0000
2 | 438691 | C 1st Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
3 | 667330 | C101 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 2 | 438691 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
4 | 667331 | C102 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 2 | 438691 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
5 | 667332 | C103 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 2 | 438691 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
6 | 667333 | C104 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 2 | 438691 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
7 | 667334 | C 2nd Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
8 | 667335 | C201 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 7 | 667334 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
9 | 667336 | C202 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 7 | 667334 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
10 | 667337 | C203 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 7 | 667334 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
11 | 667338 | C204 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 7 | 667334 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
12 | 667339 | C 3rd Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
13 | 667340 | C301 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 12 | 667339 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
14 | 667341 | C302 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 12 | 667339 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
15 | 667342 | C303 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 12 | 667339 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
16 | 667343 | C304 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 12 | 667339 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
17 | 667344 | C 4th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
18 | 667345 | C401 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 17 | 667344 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
19 | 667346 | C402 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 17 | 667344 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
20 | 667347 | C403 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 17 | 667344 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
21 | 667348 | C404 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 17 | 667344 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
22 | 667349 | C 5th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
23 | 667350 | C501 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 22 | 667349 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
24 | 667351 | C502 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 22 | 667349 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
25 | 667352 | C503 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 22 | 667349 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
26 | 667353 | C504 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 22 | 667349 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
27 | 667354 | C 6th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
28 | 667355 | C601 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 27 | 667354 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
29 | 667356 | C602 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 27 | 667354 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
30 | 667357 | C603 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 27 | 667354 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
31 | 667358 | C604 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 27 | 667354 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
32 | 667359 | C 7th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
33 | 667360 | C701 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 32 | 667359 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
34 | 667361 | C702 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 32 | 667359 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
35 | 667362 | C703 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 32 | 667359 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
36 | 667363 | C704 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 32 | 667359 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
37 | 667364 | C 8th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
38 | 667365 | C801 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 37 | 667364 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
39 | 667366 | C802 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 37 | 667364 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
40 | 667367 | C803 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 37 | 667364 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
41 | 667368 | C804 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 37 | 667364 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
42 | 667369 | C 9th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
43 | 667370 | C901 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 42 | 667369 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
44 | 667371 | C902 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 42 | 667369 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
45 | 667372 | C903 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 42 | 667369 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
46 | 667373 | C904 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 42 | 667369 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
47 | 667374 | C 10th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
48 | 667375 | C1001 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 47 | 667374 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
49 | 667376 | C1002 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 47 | 667374 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
50 | 667377 | C1003 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 47 | 667374 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
51 | 667378 | C1004 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 47 | 667374 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
52 | 667379 | C 11th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
53 | 667380 | C1101 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 52 | 667379 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
54 | 667381 | C1102 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 52 | 667379 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
55 | 667382 | C1103 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 52 | 667379 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
56 | 667383 | C1104 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 52 | 667379 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
57 | 667384 | C 12th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
58 | 667385 | C1201 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 57 | 667384 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
59 | 667386 | C1202 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 57 | 667384 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
60 | 667387 | C1203 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 57 | 667384 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
61 | 667388 | C1204 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 57 | 667384 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
62 | 667389 | C 13th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
63 | 667390 | C1301 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 62 | 667389 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
64 | 667391 | C1302 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 62 | 667389 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
65 | 667392 | C1303 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 62 | 667389 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
66 | 667393 | C1304 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 62 | 667389 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
67 | 667394 | C 14th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
68 | 667395 | C1401 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 67 | 667394 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
69 | 667396 | C1402 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 67 | 667394 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
70 | 667397 | C1403 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 67 | 667394 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
71 | 667398 | C1404 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 67 | 667394 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
72 | 667399 | C 15th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
73 | 667400 | C1501 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 72 | 667399 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
74 | 667401 | C1502 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 72 | 667399 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
75 | 667402 | C1503 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 72 | 667399 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
76 | 667403 | C1504 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 72 | 667399 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
77 | 667404 | C 16th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
78 | 667405 | C1601 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 77 | 667404 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
79 | 667406 | C1602 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 77 | 667404 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
80 | 667407 | C1603 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 77 | 667404 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
81 | 667408 | C1604 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 77 | 667404 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
82 | 667409 | C 17th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
83 | 667410 | C1701 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 82 | 667409 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
84 | 667411 | C1702 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 82 | 667409 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
85 | 667412 | C1703 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 82 | 667409 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
86 | 667413 | C1704 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 82 | 667409 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
87 | 667414 | C 18th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
88 | 667415 | C1801 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 87 | 667414 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
89 | 667416 | C1802 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 87 | 667414 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
90 | 667417 | C1803 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 87 | 667414 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
91 | 667418 | C1804 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 87 | 667414 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
92 | 667419 | C 19th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
93 | 667420 | C1901 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 92 | 667419 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
94 | 667421 | C1902 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 92 | 667419 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
95 | 667422 | C1903 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 92 | 667419 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
96 | 667423 | C1904 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 92 | 667419 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
97 | 667424 | C 20th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
98 | 667425 | C2001 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 97 | 667424 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
99 | 667426 | C2002 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 97 | 667424 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
100 | 667427 | C2003 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 97 | 667424 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
101 | 667428 | C2004 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 97 | 667424 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
102 | 667429 | C 21st Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
103 | 667430 | C2101 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 102 | 667429 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
104 | 667431 | C2102 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 102 | 667429 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
105 | 667432 | C2103 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 102 | 667429 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
106 | 667433 | C2104 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 102 | 667429 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
107 | 667434 | C 22nd Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
108 | 667435 | C2201 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 107 | 667434 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
109 | 667436 | C2202 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 107 | 667434 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
110 | 667437 | C2203 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 107 | 667434 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
111 | 667438 | C2204 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 107 | 667434 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
112 | 667439 | C 23rd Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
113 | 667440 | C2301 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 112 | 667439 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
114 | 667441 | C2302 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 112 | 667439 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
115 | 667442 | C2303 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 112 | 667439 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
116 | 667443 | C2304 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 112 | 667439 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
117 | 667444 | C 24th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
118 | 667445 | C2401 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 117 | 667444 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
119 | 667446 | C2402 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 117 | 667444 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
120 | 667447 | C2403 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 117 | 667444 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
121 | 667448 | C2404 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 117 | 667444 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
122 | 667449 | C 25th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
123 | 667450 | C2501 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 122 | 667449 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
124 | 667451 | C2502 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 122 | 667449 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
125 | 667452 | C2503 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 122 | 667449 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
126 | 667453 | C2504 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 122 | 667449 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
127 | 667454 | C 26th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
128 | 667455 | C2601 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 127 | 667454 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
129 | 667456 | C2602 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 127 | 667454 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
130 | 667457 | C2603 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 127 | 667454 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
131 | 667458 | C2604 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 127 | 667454 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
132 | 667459 | C 27th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
133 | 667460 | C2701 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 132 | 667459 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
134 | 667461 | C2702 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 132 | 667459 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
135 | 667462 | C2703 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 132 | 667459 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
136 | 667463 | C2704 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 132 | 667459 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
137 | 667464 | C 28th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
138 | 667465 | C2801 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 137 | 667464 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
139 | 667466 | C2802 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 137 | 667464 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
140 | 667467 | C2803 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 137 | 667464 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
141 | 667468 | C2804 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 137 | 667464 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
142 | 667469 | C 29th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
143 | 667470 | C2901 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 142 | 667469 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
144 | 667471 | C2902 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 142 | 667469 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
145 | 667472 | C2903 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 142 | 667469 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
146 | 667473 | C2904 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 142 | 667469 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
147 | 667474 | C 30th Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
148 | 667475 | C3001 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 147 | 667474 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
149 | 667476 | C3002 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 147 | 667474 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
150 | 667477 | C3003 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 147 | 667474 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
151 | 667478 | C3004 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 147 | 667474 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
152 | 667479 | C 31st Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
153 | 667480 | C3101 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 152 | 667479 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
154 | 667481 | C3102 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 152 | 667479 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
155 | 667482 | C3103 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 152 | 667479 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
156 | 667483 | C3104 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 152 | 667479 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
157 | 667484 | C 32nd Floor Ledge wall plaster | NA | 0.0000 | 0.0000 | 1 | 438690 | 31 | 0 | [6 empty] | 0.0000
158 | 667485 | C3201 Ledge wall plaster Work | Sq.Ft | 96.9500 | 96.9500 | 157 | 667484 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
159 | 667486 | C3202 Ledge wall plaster Work | Sq.Ft | 57.3900 | 57.3900 | 157 | 667484 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
160 | 667487 | C3203 Ledge wall plaster Work | Sq.Ft | 58.3600 | 58.3600 | 157 | 667484 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000
161 | 667488 | C3204 Ledge wall plaster Work | Sq.Ft | 55.5900 | 55.5900 | 157 | 667484 | 4 | 34755 | C Ledge Wall Plaster Work | [5 empty] | 0.0000