## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work | Selected Group :- E Shop MS Shutter Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 670982 | E Shop MS Shutter Work | NA | 0.0000 | 0.0000 | 0 | 670920 | 31 | 0 | [6 empty] | 0.0000
2 | 670983 | E - R Shop 1 MS Shutter Work | Sq.Ft | 53.7300 | 53.7300 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
3 | 670984 | E - R Shop 2 MS Shutter Work | Sq.Ft | 63.5500 | 63.5500 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
4 | 670985 | E - C Shop 1 MS Shutter Work | Sq.Ft | 257.8200 | 257.8200 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
5 | 670986 | E - C Shop 2 MS Shutter Work | Sq.Ft | 176.1900 | 176.1900 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
6 | 670987 | E - C Shop 3 MS Shutter Work | Sq.Ft | 98.6800 | 98.6800 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
7 | 670988 | E - C Shop 4 MS Shutter Work | Sq.Ft | 257.8200 | 257.8200 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
8 | 670989 | E - C Shop 5 MS Shutter Work | Sq.Ft | 98.1700 | 98.1700 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
9 | 670990 | E - C Shop 6 MS Shutter Work | Sq.Ft | 176.1900 | 176.1900 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
10 | 670991 | E - C Shop 7 MS Shutter Work | Sq.Ft | 257.8200 | 257.8200 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
11 | 670992 | E - R Shop 3 MS Shutter Work | Sq.Ft | 343.3300 | 343.3300 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
12 | 670993 | E - C Shop 8 MS Shutter Work | Sq.Ft | 122.1900 | 122.1900 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
13 | 670994 | E - R Shop 4 MS Shutter Work | Sq.Ft | 63.5500 | 63.5500 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
14 | 670995 | E - R Shop 5 MS Shutter Work | Sq.Ft | 178.7700 | 178.7700 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
15 | 670996 | E - R Shop 6 MS Shutter Work | Sq.Ft | 128.9100 | 128.9100 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
16 | 670997 | E - Sale Shop 6 MS Shutter Work | Sq.Ft | 46.7600 | 46.7600 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
17 | 670998 | E - Sale Shop 5 MS Shutter Work | Sq.Ft | 128.9100 | 128.9100 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
18 | 670999 | E - Sale Shop 4 MS Shutter Work | Sq.Ft | 117.8000 | 117.8000 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
19 | 671000 | E - Sale Shop 3 MS Shutter Work | Sq.Ft | 106.6900 | 106.6900 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
20 | 671001 | E - Sale Shop 2 MS Shutter Work | Sq.Ft | 47.7900 | 47.7900 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
21 | 671002 | E - Sale Shop 1 MS Shutter Work | Sq.Ft | 128.9100 | 128.9100 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
22 | 671003 | E - R Shop 7 MS Shutter Work | Sq.Ft | 128.9100 | 128.9100 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
23 | 671004 | E - R Shop 8 MS Shutter Work | Sq.Ft | 310.2600 | 310.2600 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
24 | 671005 | E - R Shop 9 MS Shutter Work | Sq.Ft | 86.8000 | 86.8000 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
25 | 671006 | E - R Shop 10 MS Shutter Work | Sq.Ft | 128.9100 | 128.9100 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
26 | 671007 | E - R Shop 11 MS Shutter Work | Sq.Ft | 86.8000 | 86.8000 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
27 | 671008 | E - R Shop 12 MS Shutter Work | Sq.Ft | 86.8000 | 86.8000 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
28 | 671009 | E - R Shop 13 MS Shutter Work | Sq.Ft | 86.8000 | 86.8000 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000
29 | 671010 | E - R Shop 14 MS Shutter Work | Sq.Ft | 86.8000 | 86.8000 | 1 | 670982 | 4 | 33986 | C - Rolling Shutter Fixing Work | [5 empty] | 0.0000