## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work | Selected Group :- E Shop Internal Flooring Work
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 671014 | E Shop Internal Flooring Work | NA | 0.0000 | 0.0000 | 0 | 671013 | 31 | 0 | [6 empty] | 0.0000
2 | 671016 | E - R Shop 1 Internal Flooring Work | Sq.Ft | 108.1800 | 108.1800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
3 | 671017 | E - R Shop 2 Internal Flooring Work | Sq.Ft | 66.3100 | 66.3100 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
4 | 671018 | E - C Shop 1 Internal Flooring Work | Sq.Ft | 271.6800 | 271.6800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
5 | 671019 | E - C Shop 2 Internal Flooring Work | Sq.Ft | 182.1300 | 182.1300 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
6 | 671020 | E - C Shop 3 Internal Flooring Work | Sq.Ft | 103.3300 | 103.3300 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
7 | 671021 | E - C Shop 4 Internal Flooring Work | Sq.Ft | 271.6800 | 271.6800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
8 | 671022 | E - C Shop 5 Internal Flooring Work | Sq.Ft | 102.8000 | 102.8000 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
9 | 671023 | E - C Shop 6 Internal Flooring Work | Sq.Ft | 182.1300 | 182.1300 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
10 | 671024 | E - C Shop 7 Internal Flooring Work | Sq.Ft | 270.9300 | 270.9300 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
11 | 671025 | E - R Shop 3 Internal Flooring Work | Sq.Ft | 363.6100 | 363.6100 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
12 | 671026 | E - C Shop 8 Internal Flooring Work | Sq.Ft | 128.4100 | 128.4100 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
13 | 671027 | E - R Shop 4 Internal Flooring Work | Sq.Ft | 84.3900 | 84.3900 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
14 | 671028 | E - R Shop 5 Internal Flooring Work | Sq.Ft | 254.7800 | 254.7800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
15 | 671029 | E - R Shop 6 Internal Flooring Work | Sq.Ft | 191.7100 | 191.7100 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
16 | 671030 | E - Sale Shop 6 Internal Flooring Work | Sq.Ft | 114.4200 | 114.4200 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
17 | 671031 | E - Sale Shop 5 Internal Flooring Work | Sq.Ft | 115.2800 | 115.2800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
18 | 671032 | E - Sale Shop 4 Internal Flooring Work | Sq.Ft | 108.3900 | 108.3900 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
19 | 671033 | E - Sale Shop 3 Internal Flooring Work | Sq.Ft | 113.1300 | 113.1300 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
20 | 671034 | E - Sale Shop 2 Internal Flooring Work | Sq.Ft | 104.3000 | 104.3000 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
21 | 671035 | E - Sale Shop 1 Internal Flooring Work | Sq.Ft | 192.4600 | 192.4600 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
22 | 671036 | E - R Shop 7 Internal Flooring Work | Sq.Ft | 115.2800 | 115.2800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
23 | 671037 | E - R Shop 8 Internal Flooring Work | Sq.Ft | 393.7500 | 393.7500 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
24 | 671038 | E - R Shop 9 Internal Flooring Work | Sq.Ft | 107.6400 | 107.6400 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
25 | 671039 | E - R Shop 10 Internal Flooring Work | Sq.Ft | 115.2800 | 115.2800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
26 | 671040 | E - R Shop 11 Internal Flooring Work | Sq.Ft | 106.7800 | 106.7800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
27 | 671068 | E - R Shop 12 Internal Flooring Work | Sq.Ft | 106.7800 | 106.7800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
28 | 671069 | E - R Shop 13 Internal Flooring Work | Sq.Ft | 106.7800 | 106.7800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000
29 | 671070 | E - R Shop 14 Internal Flooring Work | Sq.Ft | 106.7800 | 106.7800 | 1 | 671014 | 4 | 34699 | C Shop Internal Flooring Work | [5 empty] | 0.0000