## Sheet1
Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS
Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting | Selected Group :- C Internal Painting
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 465989 | C Internal Painting | NA | 0.0000 | 0.0000 | 0 | 313138 | 31 | 0 | [6 empty] | 0.0000
2 | 465990 | C 1st Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
3 | 465991 | C Flat No.101 Internal Painting | NA | 0.0000 | 0.0000 | 2 | 465990 | 31 | 0 | [6 empty] | 0.0000
4 | 465992 | C 101 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 3 | 465991 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
5 | 465993 | C 101 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 3 | 465991 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
6 | 465994 | C 101 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 3 | 465991 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
7 | 465996 | C Flat No.102 Internal Painting | NA | 0.0000 | 0.0000 | 2 | 465990 | 31 | 0 | [6 empty] | 0.0000
8 | 465997 | C 102 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 7 | 465996 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
9 | 465998 | C 102 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 7 | 465996 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
10 | 465999 | C 102 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 7 | 465996 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
11 | 466002 | C Flat No.103 Internal Painting | NA | 0.0000 | 0.0000 | 2 | 465990 | 31 | 0 | [6 empty] | 0.0000
12 | 466003 | C 103 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 11 | 466002 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
13 | 466004 | C 103 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 11 | 466002 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
14 | 466005 | C 103 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 11 | 466002 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
15 | 466008 | C Flat No.104 Internal Painting | NA | 0.0000 | 0.0000 | 2 | 465990 | 31 | 0 | [6 empty] | 0.0000
16 | 466009 | C 104 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 15 | 466008 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
17 | 466010 | C 104 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 15 | 466008 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
18 | 466011 | C 104 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 15 | 466008 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
19 | 466012 | C 2nd Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
20 | 466013 | C Flat No. 201 Internal Painting | NA | 0.0000 | 0.0000 | 19 | 466012 | 31 | 0 | [6 empty] | 0.0000
21 | 466014 | C 201 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 20 | 466013 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
22 | 466015 | C 201 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 20 | 466013 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
23 | 466016 | C 201 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 20 | 466013 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
24 | 466017 | C Flat No.202 Internal Painting | NA | 0.0000 | 0.0000 | 19 | 466012 | 31 | 0 | [6 empty] | 0.0000
25 | 466018 | C 202 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 24 | 466017 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
26 | 466019 | C 202 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 24 | 466017 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
27 | 466020 | C 202 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 24 | 466017 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
28 | 466021 | C Flat No.203 Internal Painting | NA | 0.0000 | 0.0000 | 19 | 466012 | 31 | 0 | [6 empty] | 0.0000
29 | 466022 | C 203 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 28 | 466021 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
30 | 466023 | C 203 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 28 | 466021 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
31 | 466024 | C 203 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 28 | 466021 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
32 | 466025 | C Flat No. 204 Internal Painting | NA | 0.0000 | 0.0000 | 19 | 466012 | 31 | 0 | [6 empty] | 0.0000
33 | 466026 | C 204 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 32 | 466025 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
34 | 466027 | C 204 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 32 | 466025 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
35 | 466028 | C 204 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 32 | 466025 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
36 | 466029 | C 3rd Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
37 | 466030 | C Flat No. 301 Internal Painting | NA | 0.0000 | 0.0000 | 36 | 466029 | 31 | 0 | [6 empty] | 0.0000
38 | 466031 | C 301 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 37 | 466030 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
39 | 466032 | C 301 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 37 | 466030 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
40 | 466033 | C 301 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 37 | 466030 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
41 | 466034 | C Flat No. 302 Internal Painting | NA | 0.0000 | 0.0000 | 36 | 466029 | 31 | 0 | [6 empty] | 0.0000
42 | 466035 | C 302 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 41 | 466034 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
43 | 466036 | C 302 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 41 | 466034 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
44 | 466037 | C 302 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 41 | 466034 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
45 | 466038 | C Flat No. 303 Internal Painting | NA | 0.0000 | 0.0000 | 36 | 466029 | 31 | 0 | [6 empty] | 0.0000
46 | 466039 | C 303 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 45 | 466038 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
47 | 466040 | C 303 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 45 | 466038 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
48 | 466041 | C 303 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 45 | 466038 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
49 | 466042 | C Flat No. 304 Internal Painting | NA | 0.0000 | 0.0000 | 36 | 466029 | 31 | 0 | [6 empty] | 0.0000
50 | 466043 | C 304 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 49 | 466042 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
51 | 466044 | C 304 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 49 | 466042 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
52 | 466045 | C 304 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 49 | 466042 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
53 | 466046 | C 4th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
54 | 466047 | C Flat No. 401 Internal Painting | NA | 0.0000 | 0.0000 | 53 | 466046 | 31 | 0 | [6 empty] | 0.0000
55 | 466048 | C 401 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 54 | 466047 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
56 | 466049 | C 401 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 54 | 466047 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
57 | 466050 | C 401 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 54 | 466047 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
58 | 466051 | C Flat No. 402 Internal Painting | NA | 0.0000 | 0.0000 | 53 | 466046 | 31 | 0 | [6 empty] | 0.0000
59 | 466052 | C 402 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 58 | 466051 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
60 | 466053 | C 402 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 58 | 466051 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
61 | 466054 | C 402 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 58 | 466051 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
62 | 466055 | C Flat No. 403 Internal Painting | NA | 0.0000 | 0.0000 | 53 | 466046 | 31 | 0 | [6 empty] | 0.0000
63 | 466056 | C 403 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 62 | 466055 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
64 | 466057 | C 403 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 62 | 466055 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
65 | 466058 | C 403 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 62 | 466055 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
66 | 466059 | C Flat No. 404 Internal Painting | NA | 0.0000 | 0.0000 | 53 | 466046 | 31 | 0 | [6 empty] | 0.0000
67 | 466060 | C 404 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 66 | 466059 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
68 | 466061 | C 404 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 66 | 466059 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
69 | 466062 | C 404 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 66 | 466059 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
70 | 466063 | C 5th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
71 | 466064 | C Flat No. 501 Internal Painting | NA | 0.0000 | 0.0000 | 70 | 466063 | 31 | 0 | [6 empty] | 0.0000
72 | 466065 | C 501 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 71 | 466064 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
73 | 466066 | C 501 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 71 | 466064 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
74 | 466067 | C 501 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 71 | 466064 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
75 | 466068 | C Flat No. 502 Internal Painting | NA | 0.0000 | 0.0000 | 70 | 466063 | 31 | 0 | [6 empty] | 0.0000
76 | 466069 | C 502 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 75 | 466068 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
77 | 466070 | C 502 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 75 | 466068 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
78 | 466071 | C 502 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 75 | 466068 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
79 | 466072 | C Flat No. 503 Internal Painting | NA | 0.0000 | 0.0000 | 70 | 466063 | 31 | 0 | [6 empty] | 0.0000
80 | 466073 | C 503 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 79 | 466072 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
81 | 466074 | C 503 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 79 | 466072 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
82 | 466075 | C 503 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 79 | 466072 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
83 | 466076 | C Flat No. 504 Internal Painting | NA | 0.0000 | 0.0000 | 70 | 466063 | 31 | 0 | [6 empty] | 0.0000
84 | 466077 | C 504 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 83 | 466076 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
85 | 466078 | C 504 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 83 | 466076 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
86 | 466079 | C 504 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 83 | 466076 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
87 | 466080 | C 6th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
88 | 466081 | C Flat No. 601 Internal Painting | NA | 0.0000 | 0.0000 | 87 | 466080 | 31 | 0 | [6 empty] | 0.0000
89 | 466082 | C 601 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 88 | 466081 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
90 | 466083 | C 601 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 88 | 466081 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
91 | 466084 | C 601 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 88 | 466081 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
92 | 466085 | C Flat No. 602 Internal Painting | NA | 0.0000 | 0.0000 | 87 | 466080 | 31 | 0 | [6 empty] | 0.0000
93 | 466086 | C 602 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 92 | 466085 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
94 | 466087 | C 602 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 92 | 466085 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
95 | 466088 | C 602 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 92 | 466085 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
96 | 466089 | C Flat No. 603 Internal Painting | NA | 0.0000 | 0.0000 | 87 | 466080 | 31 | 0 | [6 empty] | 0.0000
97 | 466090 | C 603 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 96 | 466089 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
98 | 466091 | C 603 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 96 | 466089 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
99 | 466092 | C 603 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 96 | 466089 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
100 | 466093 | C Flat No. 604 Internal Painting | NA | 0.0000 | 0.0000 | 87 | 466080 | 31 | 0 | [6 empty] | 0.0000
101 | 466094 | C 604 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 100 | 466093 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
102 | 466095 | C 604 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 100 | 466093 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
103 | 466096 | C 604 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 100 | 466093 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
104 | 466097 | C 7th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
105 | 466098 | C Flat No. 701 Internal Painting | NA | 0.0000 | 0.0000 | 104 | 466097 | 31 | 0 | [6 empty] | 0.0000
106 | 466099 | C 701 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 105 | 466098 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
107 | 466100 | C 701 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 105 | 466098 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
108 | 466101 | C 701 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 105 | 466098 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
109 | 466102 | C Flat No. 702 Internal Painting | NA | 0.0000 | 0.0000 | 104 | 466097 | 31 | 0 | [6 empty] | 0.0000
110 | 466103 | C 702 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 109 | 466102 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
111 | 466104 | C 702 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 109 | 466102 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
112 | 466105 | C 702 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 109 | 466102 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
113 | 466106 | C Flat No. 703 Internal Painting | NA | 0.0000 | 0.0000 | 104 | 466097 | 31 | 0 | [6 empty] | 0.0000
114 | 466107 | C 703 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 113 | 466106 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
115 | 466108 | C 703 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 113 | 466106 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
116 | 466109 | C 703 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 113 | 466106 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
117 | 466110 | C Flat No. 704 Internal Painting | NA | 0.0000 | 0.0000 | 104 | 466097 | 31 | 0 | [6 empty] | 0.0000
118 | 466111 | C 704 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 117 | 466110 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
119 | 466112 | C 704 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 117 | 466110 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
120 | 466113 | C 704 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 117 | 466110 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
121 | 466114 | C 8th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
122 | 466115 | C Flat No. 801 Internal Painting | NA | 0.0000 | 0.0000 | 121 | 466114 | 31 | 0 | [6 empty] | 0.0000
123 | 466116 | C 801 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 122 | 466115 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
124 | 466117 | C 801 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 122 | 466115 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
125 | 466118 | C 801 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 122 | 466115 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
126 | 466119 | C Flat No. 802 Internal Painting | NA | 0.0000 | 0.0000 | 121 | 466114 | 31 | 0 | [6 empty] | 0.0000
127 | 466120 | C 802 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 126 | 466119 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
128 | 466121 | C 802 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 126 | 466119 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
129 | 466122 | C 802 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 126 | 466119 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
130 | 466123 | C Flat No. 803 Internal Painting | NA | 0.0000 | 0.0000 | 121 | 466114 | 31 | 0 | [6 empty] | 0.0000
131 | 466124 | C 803 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 130 | 466123 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
132 | 466125 | C 803 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 130 | 466123 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
133 | 466126 | C 803 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 130 | 466123 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
134 | 466127 | C Flat No. 804 Internal Painting | NA | 0.0000 | 0.0000 | 121 | 466114 | 31 | 0 | [6 empty] | 0.0000
135 | 466128 | C 804 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 134 | 466127 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
136 | 466129 | C 804 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 134 | 466127 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
137 | 466130 | C 804 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 134 | 466127 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
138 | 466131 | C 9th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
139 | 466132 | C Flat No. 901 Internal Painting | NA | 0.0000 | 0.0000 | 138 | 466131 | 31 | 0 | [6 empty] | 0.0000
140 | 466133 | C 901 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 139 | 466132 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
141 | 466134 | C 901 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 139 | 466132 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
142 | 466135 | C 901 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 139 | 466132 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
143 | 466136 | C Flat No. 902 Internal Painting | NA | 0.0000 | 0.0000 | 138 | 466131 | 31 | 0 | [6 empty] | 0.0000
144 | 466137 | C 902 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 143 | 466136 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
145 | 466138 | C 902 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 143 | 466136 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
146 | 466139 | C 902 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 143 | 466136 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
147 | 466140 | C Flat No. 903 Internal Painting | NA | 0.0000 | 0.0000 | 138 | 466131 | 31 | 0 | [6 empty] | 0.0000
148 | 466141 | C 903 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 147 | 466140 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
149 | 466142 | C 903 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 147 | 466140 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
150 | 466143 | C 903 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 147 | 466140 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
151 | 466144 | C Flat No. 904 Internal Painting | NA | 0.0000 | 0.0000 | 138 | 466131 | 31 | 0 | [6 empty] | 0.0000
152 | 466145 | C 904 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 151 | 466144 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
153 | 466146 | C 904 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 151 | 466144 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
154 | 466147 | C 904 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 151 | 466144 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
155 | 466148 | C 10th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
156 | 466149 | C Flat No. 1001 Internal Painting | NA | 0.0000 | 0.0000 | 155 | 466148 | 31 | 0 | [6 empty] | 0.0000
157 | 466150 | C 1001 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 156 | 466149 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
158 | 466151 | C 1001 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 156 | 466149 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
159 | 466152 | C 1001 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 156 | 466149 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
160 | 466153 | C Flat No. 1002 Internal Painting | NA | 0.0000 | 0.0000 | 155 | 466148 | 31 | 0 | [6 empty] | 0.0000
161 | 466154 | C 1002 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 160 | 466153 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
162 | 466155 | C 1002 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 160 | 466153 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
163 | 466156 | C 1002 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 160 | 466153 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
164 | 466157 | C Flat No. 1003 Internal Painting | NA | 0.0000 | 0.0000 | 155 | 466148 | 31 | 0 | [6 empty] | 0.0000
165 | 466158 | C 1003 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 164 | 466157 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
166 | 466159 | C 1003 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 164 | 466157 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
167 | 466160 | C 1003 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 164 | 466157 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
168 | 466161 | C Flat No. 1004 Internal Painting | NA | 0.0000 | 0.0000 | 155 | 466148 | 31 | 0 | [6 empty] | 0.0000
169 | 466162 | C 1004 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 168 | 466161 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
170 | 466163 | C 1004 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 168 | 466161 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
171 | 466164 | C 1004 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 168 | 466161 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
172 | 466165 | C 11th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
173 | 466166 | C Flat No.1101 Internal Painting | NA | 0.0000 | 0.0000 | 172 | 466165 | 31 | 0 | [6 empty] | 0.0000
174 | 466167 | C 1101 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 173 | 466166 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
175 | 466168 | C 1101 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 173 | 466166 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
176 | 466169 | C 1101 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 173 | 466166 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
177 | 466170 | C Flat No.1102 Internal Painting | NA | 0.0000 | 0.0000 | 172 | 466165 | 31 | 0 | [6 empty] | 0.0000
178 | 466171 | C 1102 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 177 | 466170 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
179 | 466172 | C 1102 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 177 | 466170 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
180 | 466173 | C 1102 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 177 | 466170 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
181 | 466174 | C Flat No.1103 Internal Painting | NA | 0.0000 | 0.0000 | 172 | 466165 | 31 | 0 | [6 empty] | 0.0000
182 | 466175 | C 1103 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 181 | 466174 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
183 | 466176 | C 1103 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 181 | 466174 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
184 | 466177 | C 1103 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 181 | 466174 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
185 | 466178 | C Flat No.1104 Internal Painting | NA | 0.0000 | 0.0000 | 172 | 466165 | 31 | 0 | [6 empty] | 0.0000
186 | 466179 | C 1104 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 185 | 466178 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
187 | 466180 | C 1104 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 185 | 466178 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
188 | 466181 | C 1104 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 185 | 466178 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
189 | 466182 | C 12th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
190 | 466183 | C Flat No. 1201 Internal Painting | NA | 0.0000 | 0.0000 | 189 | 466182 | 31 | 0 | [6 empty] | 0.0000
191 | 466184 | C 1201 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 190 | 466183 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
192 | 466185 | C 1201 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 190 | 466183 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
193 | 466186 | C 1201 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 190 | 466183 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
194 | 466187 | C Flat No. 1202 Internal Painting | NA | 0.0000 | 0.0000 | 189 | 466182 | 31 | 0 | [6 empty] | 0.0000
195 | 466188 | C 1202 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 194 | 466187 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
196 | 466189 | C 1202 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 194 | 466187 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
197 | 466190 | C 1202 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 194 | 466187 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
198 | 466191 | C Flat No. 1203 Internal Painting | NA | 0.0000 | 0.0000 | 189 | 466182 | 31 | 0 | [6 empty] | 0.0000
199 | 466192 | C 1203 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 198 | 466191 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
200 | 466193 | C 1203 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 198 | 466191 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
201 | 466194 | C 1203 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 198 | 466191 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
202 | 466195 | C Flat No. 1204 Internal Painting | NA | 0.0000 | 0.0000 | 189 | 466182 | 31 | 0 | [6 empty] | 0.0000
203 | 466196 | C 1204 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 202 | 466195 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
204 | 466197 | C 1204 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 202 | 466195 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
205 | 466198 | C 1204 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 202 | 466195 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
206 | 466199 | C 13th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
207 | 466200 | C Flat No. 1301 Internal Painting | NA | 0.0000 | 0.0000 | 206 | 466199 | 31 | 0 | [6 empty] | 0.0000
208 | 466201 | C 1301 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 207 | 466200 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
209 | 466202 | C 1301 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 207 | 466200 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
210 | 466203 | C 1301 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 207 | 466200 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
211 | 466204 | C Flat No. 1302 Internal Painting | NA | 0.0000 | 0.0000 | 206 | 466199 | 31 | 0 | [6 empty] | 0.0000
212 | 466205 | C 1302 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 211 | 466204 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
213 | 466206 | C 1302 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 211 | 466204 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
214 | 466207 | C 1302 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 211 | 466204 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
215 | 466208 | C Flat No. 1303 Internal Painting | NA | 0.0000 | 0.0000 | 206 | 466199 | 31 | 0 | [6 empty] | 0.0000
216 | 466209 | C 1303 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 215 | 466208 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
217 | 466210 | C 1303 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 215 | 466208 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
218 | 466211 | C 1303 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 215 | 466208 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
219 | 466212 | C Flat No. 1304 Internal Painting | NA | 0.0000 | 0.0000 | 206 | 466199 | 31 | 0 | [6 empty] | 0.0000
220 | 466213 | C 1304 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 219 | 466212 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
221 | 466214 | C 1304 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 219 | 466212 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
222 | 466215 | C 1304 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 219 | 466212 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
223 | 466216 | C 14th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
224 | 466217 | C Flat No. 1401 Internal Painting | NA | 0.0000 | 0.0000 | 223 | 466216 | 31 | 0 | [6 empty] | 0.0000
225 | 466218 | C 1401 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 224 | 466217 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
226 | 466219 | C 1401 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 224 | 466217 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
227 | 466220 | C 1401 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 224 | 466217 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
228 | 466221 | C Flat No. 1402 Internal Painting | NA | 0.0000 | 0.0000 | 223 | 466216 | 31 | 0 | [6 empty] | 0.0000
229 | 466222 | C 1402 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 228 | 466221 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
230 | 466223 | C 1402 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 228 | 466221 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
231 | 466224 | C 1402 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 228 | 466221 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
232 | 466225 | C Flat No. 1403 Internal Painting | NA | 0.0000 | 0.0000 | 223 | 466216 | 31 | 0 | [6 empty] | 0.0000
233 | 466226 | C 1403 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 232 | 466225 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
234 | 466227 | C 1403 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 232 | 466225 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
235 | 466228 | C 1403 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 232 | 466225 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
236 | 466229 | C Flat No. 1404 Internal Painting | NA | 0.0000 | 0.0000 | 223 | 466216 | 31 | 0 | [6 empty] | 0.0000
237 | 466230 | C 1404 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 236 | 466229 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
238 | 466231 | C 1404 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 236 | 466229 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
239 | 466232 | C 1404 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 236 | 466229 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
240 | 466233 | C 15th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
241 | 466234 | C Flat No. 1501 Internal Painting | NA | 0.0000 | 0.0000 | 240 | 466233 | 31 | 0 | [6 empty] | 0.0000
242 | 466235 | C 1501 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 241 | 466234 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
243 | 466236 | C 1501 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 241 | 466234 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
244 | 466237 | C 1501 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 241 | 466234 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
245 | 466238 | C Flat No. 1502 Internal Painting | NA | 0.0000 | 0.0000 | 240 | 466233 | 31 | 0 | [6 empty] | 0.0000
246 | 466239 | C 1502 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 245 | 466238 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
247 | 466240 | C 1502 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 245 | 466238 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
248 | 466241 | C 1502 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 245 | 466238 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
249 | 466242 | C Flat No. 1503 Internal Painting | NA | 0.0000 | 0.0000 | 240 | 466233 | 31 | 0 | [6 empty] | 0.0000
250 | 466243 | C 1503 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 249 | 466242 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
251 | 466244 | C 1503 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 249 | 466242 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
252 | 466245 | C 1503 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 249 | 466242 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
253 | 466246 | C Flat No. 1504 Internal Painting | NA | 0.0000 | 0.0000 | 240 | 466233 | 31 | 0 | [6 empty] | 0.0000
254 | 466247 | C 1504 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 253 | 466246 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
255 | 466248 | C 1504 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 253 | 466246 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
256 | 466249 | C 1504 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 253 | 466246 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
257 | 466250 | C 16th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
258 | 466251 | C Flat No. 1601 Internal Painting | NA | 0.0000 | 0.0000 | 257 | 466250 | 31 | 0 | [6 empty] | 0.0000
259 | 466252 | C 1601 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 258 | 466251 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
260 | 466253 | C 1601 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 258 | 466251 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
261 | 466254 | C 1601 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 258 | 466251 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
262 | 466255 | C Flat No. 1602 Internal Painting | NA | 0.0000 | 0.0000 | 257 | 466250 | 31 | 0 | [6 empty] | 0.0000
263 | 466256 | C 1602 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 262 | 466255 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
264 | 466257 | C 1602 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 262 | 466255 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
265 | 466258 | C 1602 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 262 | 466255 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
266 | 466259 | C Flat No. 1603 Internal Painting | NA | 0.0000 | 0.0000 | 257 | 466250 | 31 | 0 | [6 empty] | 0.0000
267 | 466260 | C 1603 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 266 | 466259 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
268 | 466261 | C 1603 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 266 | 466259 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
269 | 466262 | C 1603 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 266 | 466259 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
270 | 466263 | C Flat No. 1604 Internal Painting | NA | 0.0000 | 0.0000 | 257 | 466250 | 31 | 0 | [6 empty] | 0.0000
271 | 466264 | C 1604 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 270 | 466263 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
272 | 466265 | C 1604 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 270 | 466263 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
273 | 466266 | C 1604 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 270 | 466263 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
274 | 466267 | C 17th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
275 | 466268 | C Flat No. 1701 Internal Painting | NA | 0.0000 | 0.0000 | 274 | 466267 | 31 | 0 | [6 empty] | 0.0000
276 | 466269 | C 1701 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 275 | 466268 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
277 | 466270 | C 1701 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 275 | 466268 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
278 | 466271 | C 1701 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 275 | 466268 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
279 | 466272 | C Flat No. 1702 Internal Painting | NA | 0.0000 | 0.0000 | 274 | 466267 | 31 | 0 | [6 empty] | 0.0000
280 | 466273 | C 1702 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 279 | 466272 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
281 | 466274 | C 1702 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 279 | 466272 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
282 | 466275 | C 1702 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 279 | 466272 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
283 | 466276 | C Flat No. 1703 Internal Painting | NA | 0.0000 | 0.0000 | 274 | 466267 | 31 | 0 | [6 empty] | 0.0000
284 | 466277 | C 1703 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 283 | 466276 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
285 | 466278 | C 1703 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 283 | 466276 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
286 | 466279 | C 1703 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 283 | 466276 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
287 | 466280 | C Flat No. 1704 Internal Painting | NA | 0.0000 | 0.0000 | 274 | 466267 | 31 | 0 | [6 empty] | 0.0000
288 | 466281 | C 1704 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 287 | 466280 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
289 | 466282 | C 1704 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 287 | 466280 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
290 | 466283 | C 1704 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 287 | 466280 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
291 | 466284 | C 18th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
292 | 466285 | C Flat No. 1801 Internal Painting | NA | 0.0000 | 0.0000 | 291 | 466284 | 31 | 0 | [6 empty] | 0.0000
293 | 466286 | C 1801 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 292 | 466285 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
294 | 466287 | C 1801 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 292 | 466285 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
295 | 466288 | C 1801 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 292 | 466285 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
296 | 466289 | C Flat No. 1802 Internal Painting | NA | 0.0000 | 0.0000 | 291 | 466284 | 31 | 0 | [6 empty] | 0.0000
297 | 466290 | C 1802 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 296 | 466289 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
298 | 466291 | C 1802 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 296 | 466289 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
299 | 466292 | C 1802 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 296 | 466289 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
300 | 466293 | C Flat No. 1803 Internal Painting | NA | 0.0000 | 0.0000 | 291 | 466284 | 31 | 0 | [6 empty] | 0.0000
301 | 466294 | C 1803 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 300 | 466293 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
302 | 466295 | C 1803 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 300 | 466293 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
303 | 466296 | C 1803 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 300 | 466293 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
304 | 466297 | C Flat No. 1804 Internal Painting | NA | 0.0000 | 0.0000 | 291 | 466284 | 31 | 0 | [6 empty] | 0.0000
305 | 466298 | C 1804 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 304 | 466297 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
306 | 466299 | C 1804 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 304 | 466297 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
307 | 466300 | C 1804 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 304 | 466297 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
308 | 466301 | C 19th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
309 | 466302 | C Flat No. 1901 Internal Painting | NA | 0.0000 | 0.0000 | 308 | 466301 | 31 | 0 | [6 empty] | 0.0000
310 | 466303 | C 1901 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 309 | 466302 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
311 | 466304 | C 1901 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 309 | 466302 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
312 | 466305 | C 1901 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 309 | 466302 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
313 | 466306 | C Flat No. 1902 Internal Painting | NA | 0.0000 | 0.0000 | 308 | 466301 | 31 | 0 | [6 empty] | 0.0000
314 | 466307 | C 1902 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 313 | 466306 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
315 | 466308 | C 1902 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 313 | 466306 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
316 | 466309 | C 1902 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 313 | 466306 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
317 | 466310 | C Flat No. 1903 Internal Painting | NA | 0.0000 | 0.0000 | 308 | 466301 | 31 | 0 | [6 empty] | 0.0000
318 | 466311 | C 1903 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 317 | 466310 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
319 | 466312 | C 1903 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 317 | 466310 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
320 | 466313 | C 1903 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 317 | 466310 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
321 | 466314 | C Flat No. 1904 Internal Painting | NA | 0.0000 | 0.0000 | 308 | 466301 | 31 | 0 | [6 empty] | 0.0000
322 | 466315 | C 1904 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 321 | 466314 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
323 | 466316 | C 1904 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 321 | 466314 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
324 | 466317 | C 1904 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 321 | 466314 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
325 | 466318 | C 20th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
326 | 466319 | C Flat No. 2001 Internal Painting | NA | 0.0000 | 0.0000 | 325 | 466318 | 31 | 0 | [6 empty] | 0.0000
327 | 466320 | C 2001 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 326 | 466319 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
328 | 466321 | C 2001 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 326 | 466319 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
329 | 466322 | C 2001 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 326 | 466319 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
330 | 466323 | C Flat No. 2002 Internal Painting | NA | 0.0000 | 0.0000 | 325 | 466318 | 31 | 0 | [6 empty] | 0.0000
331 | 466324 | C 2002 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 330 | 466323 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
332 | 466325 | C 2002 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 330 | 466323 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
333 | 466326 | C 2002 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 330 | 466323 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
334 | 466327 | C Flat No. 2003 Internal Painting | NA | 0.0000 | 0.0000 | 325 | 466318 | 31 | 0 | [6 empty] | 0.0000
335 | 466328 | C 2003 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 334 | 466327 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
336 | 466329 | C 2003 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 334 | 466327 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
337 | 466330 | C 2003 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 334 | 466327 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
338 | 466331 | C Flat No. 2004 Internal Painting | NA | 0.0000 | 0.0000 | 325 | 466318 | 31 | 0 | [6 empty] | 0.0000
339 | 466332 | C 2004 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 338 | 466331 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
340 | 466333 | C 2004 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 338 | 466331 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
341 | 466334 | C 2004 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 338 | 466331 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
342 | 466335 | C 21st Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
343 | 466336 | C Flat No. 2101 Internal Painting | NA | 0.0000 | 0.0000 | 342 | 466335 | 31 | 0 | [6 empty] | 0.0000
344 | 466337 | C 2101 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 343 | 466336 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
345 | 466338 | C 2101 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 343 | 466336 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
346 | 466339 | C 2101 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 343 | 466336 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
347 | 466340 | C Flat No. 2102 Internal Painting | NA | 0.0000 | 0.0000 | 342 | 466335 | 31 | 0 | [6 empty] | 0.0000
348 | 466341 | C 2102 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 347 | 466340 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
349 | 466342 | C 2102 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 347 | 466340 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
350 | 466343 | C 2102 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 347 | 466340 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
351 | 466344 | C Flat No. 2103 Internal Painting | NA | 0.0000 | 0.0000 | 342 | 466335 | 31 | 0 | [6 empty] | 0.0000
352 | 466345 | C 2103 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 351 | 466344 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
353 | 466346 | C 2103 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 351 | 466344 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
354 | 466347 | C 2103 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 351 | 466344 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
355 | 466348 | C Flat No. 2104 Internal Painting | NA | 0.0000 | 0.0000 | 342 | 466335 | 31 | 0 | [6 empty] | 0.0000
356 | 466349 | C 2104 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 355 | 466348 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
357 | 466350 | C 2104 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 355 | 466348 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
358 | 466351 | C 2104 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 355 | 466348 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
359 | 466352 | C 22nd Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
360 | 466353 | C Flat No. 2201 Internal Painting | NA | 0.0000 | 0.0000 | 359 | 466352 | 31 | 0 | [6 empty] | 0.0000
361 | 466354 | C 2201 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 360 | 466353 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
362 | 466355 | C 2201 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 360 | 466353 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
363 | 466356 | C 2201 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 360 | 466353 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
364 | 466357 | C Flat No. 2202 Internal Painting | NA | 0.0000 | 0.0000 | 359 | 466352 | 31 | 0 | [6 empty] | 0.0000
365 | 466358 | C 2202 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 364 | 466357 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
366 | 466359 | C 2202 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 364 | 466357 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
367 | 466360 | C 2202 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 364 | 466357 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
368 | 466361 | C Flat No. 2203 Internal Painting | NA | 0.0000 | 0.0000 | 359 | 466352 | 31 | 0 | [6 empty] | 0.0000
369 | 466362 | C 2203 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 368 | 466361 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
370 | 466363 | C 2203 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 368 | 466361 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
371 | 466364 | C 2203 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 368 | 466361 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
372 | 466365 | C Flat No. 2204 Internal Painting | NA | 0.0000 | 0.0000 | 359 | 466352 | 31 | 0 | [6 empty] | 0.0000
373 | 466366 | C 2204 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 372 | 466365 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
374 | 466367 | C 2204 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 372 | 466365 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
375 | 466368 | C 2204 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 372 | 466365 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
376 | 466369 | C 23rd Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
377 | 466370 | C Flat No. 2301 Internal Painting | NA | 0.0000 | 0.0000 | 376 | 466369 | 31 | 0 | [6 empty] | 0.0000
378 | 466371 | C 2301 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 377 | 466370 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
379 | 466372 | C 2301 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 377 | 466370 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
380 | 466373 | C 2301 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 377 | 466370 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
381 | 466374 | C Flat No. 2302 Internal Painting | NA | 0.0000 | 0.0000 | 376 | 466369 | 31 | 0 | [6 empty] | 0.0000
382 | 466375 | C 2302 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 381 | 466374 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
383 | 466376 | C 2302 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 381 | 466374 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
384 | 466377 | C 2302 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 381 | 466374 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
385 | 466378 | C Flat No. 2303 Internal Painting | NA | 0.0000 | 0.0000 | 376 | 466369 | 31 | 0 | [6 empty] | 0.0000
386 | 466379 | C 2303 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 385 | 466378 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
387 | 466380 | C 2303 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 385 | 466378 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
388 | 466381 | C 2303 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 385 | 466378 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
389 | 466382 | C Flat No. 2304 Internal Painting | NA | 0.0000 | 0.0000 | 376 | 466369 | 31 | 0 | [6 empty] | 0.0000
390 | 466383 | C 2304 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 389 | 466382 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
391 | 466384 | C 2304 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 389 | 466382 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
392 | 466385 | C 2304 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 389 | 466382 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
393 | 466386 | C 24th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
394 | 466387 | C Flat No. 2401 Internal Painting | NA | 0.0000 | 0.0000 | 393 | 466386 | 31 | 0 | [6 empty] | 0.0000
395 | 466388 | C 2401 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 394 | 466387 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
396 | 466389 | C 2401 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 394 | 466387 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
397 | 466390 | C 2401 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 394 | 466387 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
398 | 466391 | C Flat No. 2402 Internal Painting | NA | 0.0000 | 0.0000 | 393 | 466386 | 31 | 0 | [6 empty] | 0.0000
399 | 466392 | C 2402 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 398 | 466391 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
400 | 466393 | C 2402 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 398 | 466391 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
401 | 466394 | C 2402 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 398 | 466391 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
402 | 466395 | C Flat No. 2403 Internal Painting | NA | 0.0000 | 0.0000 | 393 | 466386 | 31 | 0 | [6 empty] | 0.0000
403 | 466396 | C 2403 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 402 | 466395 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
404 | 466397 | C 2403 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 402 | 466395 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
405 | 466398 | C 2403 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 402 | 466395 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
406 | 466399 | C Flat No. 2404 Internal Painting | NA | 0.0000 | 0.0000 | 393 | 466386 | 31 | 0 | [6 empty] | 0.0000
407 | 466400 | C 2404 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 406 | 466399 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
408 | 466401 | C 2404 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 406 | 466399 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
409 | 466402 | C 2404 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 406 | 466399 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
410 | 466403 | C 25th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
411 | 466404 | C Flat No. 2501 Internal Painting | NA | 0.0000 | 0.0000 | 410 | 466403 | 31 | 0 | [6 empty] | 0.0000
412 | 466405 | C 2501 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 411 | 466404 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
413 | 466406 | C 2501 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 411 | 466404 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
414 | 466407 | C 2501 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 411 | 466404 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
415 | 466408 | C Flat No. 2502 Internal Painting | NA | 0.0000 | 0.0000 | 410 | 466403 | 31 | 0 | [6 empty] | 0.0000
416 | 466409 | C 2502 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 415 | 466408 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
417 | 466410 | C 2502 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 415 | 466408 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
418 | 466411 | C 2502 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 415 | 466408 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
419 | 466412 | C Flat No. 2503 Internal Painting | NA | 0.0000 | 0.0000 | 410 | 466403 | 31 | 0 | [6 empty] | 0.0000
420 | 466413 | C 2503 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 419 | 466412 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
421 | 466414 | C 2503 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 419 | 466412 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
422 | 466415 | C 2503 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 419 | 466412 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
423 | 466416 | C Flat No. 2504 Internal Painting | NA | 0.0000 | 0.0000 | 410 | 466403 | 31 | 0 | [6 empty] | 0.0000
424 | 466417 | C 2504 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 423 | 466416 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
425 | 466418 | C 2504 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 423 | 466416 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
426 | 466419 | C 2504 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 423 | 466416 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
427 | 466420 | C 26th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
428 | 466421 | C Flat No. 2601 Internal Painting | NA | 0.0000 | 0.0000 | 427 | 466420 | 31 | 0 | [6 empty] | 0.0000
429 | 466422 | C 2601 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 428 | 466421 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
430 | 466423 | C 2601 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 428 | 466421 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
431 | 466424 | C 2601 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 428 | 466421 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
432 | 466425 | C Flat No. 2602 Internal Painting | NA | 0.0000 | 0.0000 | 427 | 466420 | 31 | 0 | [6 empty] | 0.0000
433 | 466426 | C 2602 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 432 | 466425 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
434 | 466427 | C 2602 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 432 | 466425 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
435 | 466428 | C 2602 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 432 | 466425 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
436 | 466429 | C Flat No. 2603 Internal Painting | NA | 0.0000 | 0.0000 | 427 | 466420 | 31 | 0 | [6 empty] | 0.0000
437 | 466430 | C 2603 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 436 | 466429 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
438 | 466431 | C 2603 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 436 | 466429 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
439 | 466432 | C 2603 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 436 | 466429 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
440 | 466433 | C Flat No. 2604 Internal Painting | NA | 0.0000 | 0.0000 | 427 | 466420 | 31 | 0 | [6 empty] | 0.0000
441 | 466434 | C 2604 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 440 | 466433 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
442 | 466435 | C 2604 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 440 | 466433 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
443 | 466436 | C 2604 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 440 | 466433 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
444 | 466437 | C 27th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
445 | 466438 | C Flat No. 2701 Internal Painting | NA | 0.0000 | 0.0000 | 444 | 466437 | 31 | 0 | [6 empty] | 0.0000
446 | 466439 | C 2701 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 445 | 466438 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
447 | 466440 | C 2701 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 445 | 466438 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
448 | 466441 | C 2701 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 445 | 466438 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
449 | 466442 | C Flat No. 2702 Internal Painting | NA | 0.0000 | 0.0000 | 444 | 466437 | 31 | 0 | [6 empty] | 0.0000
450 | 466443 | C 2702 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 449 | 466442 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
451 | 466444 | C 2702 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 449 | 466442 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
452 | 466445 | C 2702 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 449 | 466442 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
453 | 466446 | C Flat No. 2703 Internal Painting | NA | 0.0000 | 0.0000 | 444 | 466437 | 31 | 0 | [6 empty] | 0.0000
454 | 466447 | C 2703 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 453 | 466446 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
455 | 466448 | C 2703 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 453 | 466446 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
456 | 466449 | C 2703 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 453 | 466446 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
457 | 466450 | C Flat No. 2704 Internal Painting | NA | 0.0000 | 0.0000 | 444 | 466437 | 31 | 0 | [6 empty] | 0.0000
458 | 466451 | C 2704 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 457 | 466450 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
459 | 466452 | C 2704 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 457 | 466450 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
460 | 466453 | C 2704 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 457 | 466450 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
461 | 466454 | C 28th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
462 | 466455 | C Flat No. 2801 Internal Painting | NA | 0.0000 | 0.0000 | 461 | 466454 | 31 | 0 | [6 empty] | 0.0000
463 | 466456 | C 2801 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 462 | 466455 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
464 | 466457 | C 2801 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 462 | 466455 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
465 | 466458 | C 2801 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 462 | 466455 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
466 | 466459 | C Flat No. 2802 Internal Painting | NA | 0.0000 | 0.0000 | 461 | 466454 | 31 | 0 | [6 empty] | 0.0000
467 | 466460 | C 2802 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 466 | 466459 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
468 | 466461 | C 2802 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 466 | 466459 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
469 | 466462 | C 2802 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 466 | 466459 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
470 | 466463 | C Flat No. 2803 Internal Painting | NA | 0.0000 | 0.0000 | 461 | 466454 | 31 | 0 | [6 empty] | 0.0000
471 | 466464 | C 2803 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 470 | 466463 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
472 | 466465 | C 2803 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 470 | 466463 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
473 | 466466 | C 2803 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 470 | 466463 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
474 | 466467 | C Flat No. 2804 Internal Painting | NA | 0.0000 | 0.0000 | 461 | 466454 | 31 | 0 | [6 empty] | 0.0000
475 | 466468 | C 2804 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 474 | 466467 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
476 | 466469 | C 2804 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 474 | 466467 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
477 | 466470 | C 2804 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 474 | 466467 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
478 | 466471 | C 29th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
479 | 466472 | C Flat No. 2901 Internal Painting | NA | 0.0000 | 0.0000 | 478 | 466471 | 31 | 0 | [6 empty] | 0.0000
480 | 466473 | C 2901 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 479 | 466472 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
481 | 466474 | C 2901 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 479 | 466472 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
482 | 466475 | C 2901 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 479 | 466472 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
483 | 466476 | C Flat No. 2902 Internal Painting | NA | 0.0000 | 0.0000 | 478 | 466471 | 31 | 0 | [6 empty] | 0.0000
484 | 466477 | C 2902 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 483 | 466476 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
485 | 466478 | C 2902 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 483 | 466476 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
486 | 466479 | C 2902 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 483 | 466476 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
487 | 466480 | C Flat No. 2903 Internal Painting | NA | 0.0000 | 0.0000 | 478 | 466471 | 31 | 0 | [6 empty] | 0.0000
488 | 466481 | C 2903 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 487 | 466480 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
489 | 466482 | C 2903 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 487 | 466480 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
490 | 466483 | C 2903 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 487 | 466480 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
491 | 466484 | C Flat No. 2904 Internal Painting | NA | 0.0000 | 0.0000 | 478 | 466471 | 31 | 0 | [6 empty] | 0.0000
492 | 466485 | C 2904 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 491 | 466484 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
493 | 466486 | C 2904 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 491 | 466484 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
494 | 466487 | C 2904 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 491 | 466484 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
495 | 466488 | C 30th Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
496 | 466489 | C Flat No. 3001 Internal Painting | NA | 0.0000 | 0.0000 | 495 | 466488 | 31 | 0 | [6 empty] | 0.0000
497 | 466490 | C 3001 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 496 | 466489 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
498 | 466491 | C 3001 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 496 | 466489 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
499 | 466492 | C 3001 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 496 | 466489 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
500 | 466493 | C Flat No. 3002 Internal Painting | NA | 0.0000 | 0.0000 | 495 | 466488 | 31 | 0 | [6 empty] | 0.0000
501 | 466494 | C 3002 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 500 | 466493 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
502 | 466495 | C 3002 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 500 | 466493 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
503 | 466496 | C 3002 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 500 | 466493 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
504 | 466497 | C Flat No. 3003 Internal Painting | NA | 0.0000 | 0.0000 | 495 | 466488 | 31 | 0 | [6 empty] | 0.0000
505 | 466498 | C 3003 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 504 | 466497 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
506 | 466499 | C 3003 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 504 | 466497 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
507 | 466500 | C 3003 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 504 | 466497 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
508 | 466501 | C Flat No. 3004 Internal Painting | NA | 0.0000 | 0.0000 | 495 | 466488 | 31 | 0 | [6 empty] | 0.0000
509 | 466502 | C 3004 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 508 | 466501 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
510 | 466503 | C 3004 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 508 | 466501 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
511 | 466504 | C 3004 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 508 | 466501 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
512 | 466505 | C 31st Floor Internal Painting | NA | 0.0000 | 0.0000 | 1 | 465989 | 31 | 0 | [6 empty] | 0.0000
513 | 466506 | C Flat No. 3101 Internal Painting | NA | 0.0000 | 0.0000 | 512 | 466505 | 31 | 0 | [6 empty] | 0.0000
514 | 466507 | C 3101 Ceiling Premium Emulsion Painting | Sq.Ft | 2283.2100 | 2283.2100 | 513 | 466506 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
515 | 466508 | C 3101 Walls Satin Matt Painting | Sq.Ft | 4019.7600 | 4019.7600 | 513 | 466506 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
516 | 466509 | C 3101 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 3280.2000 | 3280.2000 | 513 | 466506 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
517 | 466510 | C Flat No. 3102 Internal Painting | NA | 0.0000 | 0.0000 | 512 | 466505 | 31 | 0 | [6 empty] | 0.0000
518 | 466511 | C 3102 Ceiling Premium Emulsion Painting | Sq.Ft | 1706.3100 | 1706.3100 | 517 | 466510 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
519 | 466512 | C 3102 Walls Satin Matt Painting | Sq.Ft | 2559.3900 | 2559.3900 | 517 | 466510 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
520 | 466513 | C 3102 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2433.1500 | 2433.1500 | 517 | 466510 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
521 | 466514 | C Flat No. 3103 Internal Painting | NA | 0.0000 | 0.0000 | 512 | 466505 | 31 | 0 | [6 empty] | 0.0000
522 | 466515 | C 3103 Ceiling Premium Emulsion Painting | Sq.Ft | 1370.0300 | 1370.0300 | 521 | 466514 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
523 | 466516 | C 3103 Walls Satin Matt Painting | Sq.Ft | 2530.6400 | 2530.6400 | 521 | 466514 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
524 | 466517 | C 3103 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2046.7000 | 2046.7000 | 521 | 466514 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000
525 | 466518 | C Flat No. 3104 Internal Painting | NA | 0.0000 | 0.0000 | 512 | 466505 | 31 | 0 | [6 empty] | 0.0000
526 | 466519 | C 3104 Ceiling Premium Emulsion Painting | Sq.Ft | 1680.3000 | 1680.3000 | 525 | 466518 | 4 | 6267 | Ceiling Premium Emulsion Painting | [5 empty] | 0.0000
527 | 466520 | C 3104 Walls Satin Matt Painting | Sq.Ft | 2409.0400 | 2409.0400 | 525 | 466518 | 4 | 6268 | Walls Satin Matt Painting | [5 empty] | 0.0000
528 | 466521 | C 3104 Ceiling & Walls Cement Painting (Above False ceiling) | Sq.Ft | 2395.0000 | 2395.0000 | 525 | 466518 | 4 | 6269 | Toilet Ceiling & Walls | [5 empty] | 0.0000