## Sheet1
Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS
Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor | Selected Group :- C 16th Floor
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 675007 | C 16th Floor | NA | 0.0000 | 0.0000 | 0 | 544695 | 31 | 0 | [6 empty] | 0.0000
2 | 675008 | C 16th Fl. Marble Flooring & Skirting Bedding & Adhesive | NA | 0.0000 | 0.0000 | 1 | 675007 | 31 | 0 | [6 empty] | 0.0000
3 | 675012 | C1601 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 675008 | 4 | 33150 | C101 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
4 | 675013 | C1602 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 675008 | 4 | 33151 | C102 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
5 | 675014 | C1603 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 675008 | 4 | 33152 | C103 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
6 | 675015 | C1604 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 675008 | 4 | 33153 | C104 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
7 | 675009 | C 16th Fl. Vitrified Flooring & Skirting Bedding & Adhesive | NA | 0.0000 | 0.0000 | 1 | 675007 | 31 | 0 | [6 empty] | 0.0000
8 | 675016 | C1601 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 717.9600 | 717.9600 | 7 | 675009 | 4 | 33155 | C101 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
9 | 675017 | C1602 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 625.3900 | 625.3900 | 7 | 675009 | 4 | 33156 | C102 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
10 | 675018 | C1603 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 560.7000 | 560.7000 | 7 | 675009 | 4 | 33157 | C103 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
11 | 675019 | C1604 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 639.3800 | 639.3800 | 7 | 675009 | 4 | 33158 | C104 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
12 | 675010 | C 16th Fl. All Toi. Kitchen, Dry Balcony dado Adhesive | NA | 0.0000 | 0.0000 | 1 | 675007 | 31 | 0 | [6 empty] | 0.0000
13 | 675020 | C1601 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 675010 | 4 | 33160 | C101 Dado Adhesive M | [5 empty] | 0.0000
14 | 675021 | C1602 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 675010 | 4 | 33161 | C102 Dado Adhesive M | [5 empty] | 0.0000
15 | 675022 | C1603 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 675010 | 4 | 33162 | C103 Dado Adhesive M | [5 empty] | 0.0000
16 | 675023 | C1604 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 675010 | 4 | 33163 | C104 Dado Adhesive M | [5 empty] | 0.0000
17 | 675011 | C 16th Fl. Wash Basin Counter Bedding | NA | 0.0000 | 0.0000 | 1 | 675007 | 31 | 0 | [6 empty] | 0.0000
18 | 675024 | C1601 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 675011 | 4 | 33165 | C101 Wash Basin Counter Bedding Material | [5 empty] | 0.0000
19 | 675025 | C1602 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 675011 | 4 | 33166 | C102 Wash Basin Counter Bedding Material | [5 empty] | 0.0000
20 | 675026 | C1603 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 675011 | 4 | 33167 | C103 Wash Basin Counter Bedding Material | [5 empty] | 0.0000
21 | 675027 | C1604 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 675011 | 4 | 33168 | C104 Wash Basin Counter Bedding Material | [5 empty] | 0.0000