## Sheet1
Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS
Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor | Selected Group :- C 11th Floor
Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters] | Task Identification with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 674902 | C 11th Floor | NA | 0.0000 | 0.0000 | 0 | 544695 | 31 | 0 | [6 empty] | 0.0000
2 | 674903 | C 11th Fl. Marble Flooring & Skirting Bedding & Adhesive | NA | 0.0000 | 0.0000 | 1 | 674902 | 31 | 0 | [6 empty] | 0.0000
3 | 674907 | C1101 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 674903 | 4 | 33150 | C101 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
4 | 674908 | C1102 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 674903 | 4 | 33151 | C102 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
5 | 674909 | C1103 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 674903 | 4 | 33152 | C103 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
6 | 674910 | C1104 Marble Flooring & Skirting Bedding & Adhesive | No. | 1.0000 | 1.0000 | 2 | 674903 | 4 | 33153 | C104 Marble Bedding & Adhesive Material | [5 empty] | 0.0000
7 | 674904 | C 11th Fl. Vitrified Flooring & Skirting Bedding & Adhesive | NA | 0.0000 | 0.0000 | 1 | 674902 | 31 | 0 | [6 empty] | 0.0000
8 | 674911 | C1101 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 811.2800 | 811.2800 | 7 | 674904 | 4 | 33155 | C101 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
9 | 674912 | C1102 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 645.0900 | 645.0900 | 7 | 674904 | 4 | 33156 | C102 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
10 | 674913 | C1103 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 557.5800 | 557.5800 | 7 | 674904 | 4 | 33157 | C103 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
11 | 674914 | C1104 Vitrified Flooring & Skirting Bedding & Adhesive | No. | 658.9700 | 658.9700 | 7 | 674904 | 4 | 33158 | C104 Vitrified Bedding & Adhesive M | [5 empty] | 0.0000
12 | 674905 | C 11th Fl. All Toi. Kitchen, Dry Balcony dado Adhesive | NA | 0.0000 | 0.0000 | 1 | 674902 | 31 | 0 | [6 empty] | 0.0000
13 | 674915 | C1101 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 674905 | 4 | 33160 | C101 Dado Adhesive M | [5 empty] | 0.0000
14 | 674916 | C1102 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 674905 | 4 | 33161 | C102 Dado Adhesive M | [5 empty] | 0.0000
15 | 674917 | C1103 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 674905 | 4 | 33162 | C103 Dado Adhesive M | [5 empty] | 0.0000
16 | 674918 | C1104 All Toi. Kitchen, Dry Balcony dado Adhesive | No. | 1.0000 | 1.0000 | 12 | 674905 | 4 | 33163 | C104 Dado Adhesive M | [5 empty] | 0.0000
17 | 674906 | C 11th Fl. Wash Basin Counter Bedding | NA | 0.0000 | 0.0000 | 1 | 674902 | 31 | 0 | [6 empty] | 0.0000
18 | 674919 | C1101 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 674906 | 4 | 33165 | C101 Wash Basin Counter Bedding Material | [5 empty] | 0.0000
19 | 674920 | C1102 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 674906 | 4 | 33166 | C102 Wash Basin Counter Bedding Material | [5 empty] | 0.0000
20 | 674921 | C1103 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 674906 | 4 | 33167 | C103 Wash Basin Counter Bedding Material | [5 empty] | 0.0000
21 | 674922 | C1104 Wash Basin Counter Bedding | No. | 1.0000 | 1.0000 | 17 | 674906 | 4 | 33168 | C104 Wash Basin Counter Bedding Material | [5 empty] | 0.0000