## Sheet1
Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS
Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting | Selected Group :- C Lobby Ceiling & Walls Painting
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 466950 | C Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 0 | 460116 | 31 | 0 | [6 empty] | 0.0000
2 | 466951 | C 1st Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
3 | 466953 | C 1st Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 2 | 466951 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
4 | 466954 | C 1st Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 2 | 466951 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
5 | 466955 | C 1st Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 2 | 466951 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
6 | 467053 | C 2nd Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
7 | 467054 | C 2nd Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 6 | 467053 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
8 | 467055 | C 2nd Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 6 | 467053 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
9 | 467056 | C 2nd Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 6 | 467053 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
10 | 467057 | C 3rd Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
11 | 467058 | C 3rd Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 10 | 467057 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
12 | 467059 | C 3rd Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 10 | 467057 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
13 | 467060 | C 3rd Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 10 | 467057 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
14 | 467061 | C 4thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
15 | 467062 | C 4thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 14 | 467061 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
16 | 467063 | C 4thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 14 | 467061 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
17 | 467064 | C 4thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 14 | 467061 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
18 | 467065 | C 5thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
19 | 467066 | C 5thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 18 | 467065 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
20 | 467067 | C 5thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 18 | 467065 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
21 | 467068 | C 5thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 18 | 467065 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
22 | 467069 | C 6thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
23 | 467070 | C 6thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 22 | 467069 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
24 | 467071 | C 6thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 22 | 467069 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
25 | 467072 | C 6thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 22 | 467069 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
26 | 467073 | C 7thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
27 | 467074 | C 7thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 26 | 467073 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
28 | 467075 | C 7thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 26 | 467073 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
29 | 467076 | C 7thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 26 | 467073 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
30 | 467077 | C 8thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
31 | 467078 | C 8thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 30 | 467077 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
32 | 467079 | C 8thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 30 | 467077 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
33 | 467080 | C 8thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 30 | 467077 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
34 | 467081 | C 9thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
35 | 467082 | C 9thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 34 | 467081 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
36 | 467083 | C 9thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 34 | 467081 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
37 | 467084 | C 9thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 34 | 467081 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
38 | 467085 | C 10thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
39 | 467086 | C 10thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 38 | 467085 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
40 | 467087 | C 10thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 38 | 467085 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
41 | 467088 | C 10thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 38 | 467085 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
42 | 467089 | C 11thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
43 | 467090 | C 11thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 42 | 467089 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
44 | 467091 | C 11thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 42 | 467089 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
45 | 467092 | C 11thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 42 | 467089 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
46 | 467093 | C 12thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
47 | 467094 | C 12thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 46 | 467093 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
48 | 467095 | C 12thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 46 | 467093 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
49 | 467096 | C 12thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 46 | 467093 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
50 | 467097 | C 13thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
51 | 467098 | C 13thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 50 | 467097 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
52 | 467099 | C 13thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 50 | 467097 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
53 | 467100 | C 13thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 50 | 467097 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
54 | 467101 | C 14thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
55 | 467102 | C 14thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 54 | 467101 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
56 | 467103 | C 14thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 54 | 467101 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
57 | 467104 | C 14thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 54 | 467101 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
58 | 467105 | C 15thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
59 | 467106 | C 15thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 58 | 467105 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
60 | 467107 | C 15thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 58 | 467105 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
61 | 467108 | C 15thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 58 | 467105 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
62 | 467109 | C 16thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
63 | 467110 | C 16thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 62 | 467109 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
64 | 467111 | C 16thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 62 | 467109 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
65 | 467112 | C 16thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 62 | 467109 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
66 | 467113 | C 17thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
67 | 467114 | C 17thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 66 | 467113 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
68 | 467115 | C 17thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 66 | 467113 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
69 | 467116 | C 17thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 66 | 467113 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
70 | 467117 | C 18thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
71 | 467118 | C 18thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 70 | 467117 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
72 | 467119 | C 18thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 70 | 467117 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
73 | 467120 | C 18thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 70 | 467117 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
74 | 467121 | C 19thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
75 | 467122 | C 19thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 74 | 467121 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
76 | 467123 | C 19thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 74 | 467121 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
77 | 467124 | C 19thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 74 | 467121 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
78 | 467125 | C 20thFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
79 | 467126 | C 20thFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 78 | 467125 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
80 | 467127 | C 20thFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 78 | 467125 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
81 | 467128 | C 20thFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 78 | 467125 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
82 | 467129 | C 21stFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
83 | 467130 | C 21stFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 82 | 467129 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
84 | 467131 | C 21stFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 82 | 467129 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
85 | 467132 | C 21stFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 82 | 467129 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
86 | 467133 | C 22ndFloor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
87 | 467134 | C 22ndFloor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 86 | 467133 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
88 | 467135 | C 22ndFloor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 86 | 467133 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
89 | 467136 | C 22ndFl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 86 | 467133 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
90 | 467137 | C 23rd Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
91 | 467138 | C 23rd Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 90 | 467137 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
92 | 467139 | C 23rd Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 90 | 467137 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
93 | 467140 | C 23rd Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 90 | 467137 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
94 | 467141 | C 24th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
95 | 467142 | C 24th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 94 | 467141 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
96 | 467143 | C 24th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 94 | 467141 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
97 | 467144 | C 24th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 94 | 467141 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
98 | 467145 | C 25th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
99 | 467146 | C 25th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 98 | 467145 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
100 | 467147 | C 25th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 98 | 467145 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
101 | 467148 | C 25th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 98 | 467145 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
102 | 467149 | C 26th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
103 | 467150 | C 26th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 102 | 467149 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
104 | 467151 | C 26th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 102 | 467149 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
105 | 467152 | C 26th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 102 | 467149 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
106 | 467153 | C 27th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
107 | 467154 | C 27th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 106 | 467153 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
108 | 467155 | C 27th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 106 | 467153 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
109 | 467156 | C 27th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 106 | 467153 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
110 | 467157 | C 28th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
111 | 467158 | C 28th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 110 | 467157 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
112 | 467159 | C 28th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 110 | 467157 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
113 | 467160 | C 28th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 110 | 467157 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
114 | 467161 | C 29th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
115 | 467162 | C 29th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 114 | 467161 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
116 | 467163 | C 29th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 114 | 467161 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
117 | 467164 | C 29th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 114 | 467161 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
118 | 467165 | C 30th Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
119 | 467166 | C 30th Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 118 | 467165 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
120 | 467167 | C 30th Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 118 | 467165 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
121 | 467168 | C 30th Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 118 | 467165 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000
122 | 467169 | C 31st Floor Lobby Ceiling & Walls Painting | NA | 0.0000 | 0.0000 | 1 | 466950 | 31 | 0 | [6 empty] | 0.0000
123 | 467170 | C 31st Floor Lobby Ceiling Premium Emulsion Painting | Sq.Ft | 457.9 | 457.9 | 122 | 467169 | 4 | 12876 | A Lobby Ceiling Painting | [5 empty] | 0.0000
124 | 467171 | C 31st Floor Lobby Walls Satin Matt Painting | Sq.Ft | 714.28 | 714.28 | 122 | 467169 | 4 | 12875 | A Lobby Wall Painting | [5 empty] | 0.0000
125 | 467172 | C 31st Fl. Lobby Ceiling, Walls Painting above False Ceiling | Sq.Ft | 780.04 | 780.04 | 122 | 467169 | 4 | 12866 | A Lift cement paint | [5 empty] | 0.0000