## Sheet1
Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS | Project :-GANGA DHAM TOWERS
Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork | Selected Group :- C Ledge Wall Brickwork
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 438533 | C Ledge Wall Brickwork | NA | 0.0000 | 0.0000 | 0 | 438531 | 31 | 0 | [6 empty] | 0.0000
2 | 438534 | C 1st floor Ledge wall BBM Work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
3 | 438535 | C 101 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 2 | 438534 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
4 | 438536 | C 102 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 2 | 438534 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
5 | 438537 | C 103 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 2 | 438534 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
6 | 438538 | C 104 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 2 | 438534 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
7 | 438539 | C 2nd Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
8 | 438540 | C 201 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 7 | 438539 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
9 | 438541 | C 202 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 7 | 438539 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
10 | 438542 | C 203 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 7 | 438539 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
11 | 438543 | C 204 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 7 | 438539 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
12 | 438544 | C 3rd Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
13 | 438545 | C 301 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 12 | 438544 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
14 | 438546 | C 302 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 12 | 438544 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
15 | 438547 | C 303 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 12 | 438544 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
16 | 438548 | C 304 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 12 | 438544 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
17 | 438549 | C 4th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
18 | 438550 | C 401 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 17 | 438549 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
19 | 438551 | C 402 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 17 | 438549 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
20 | 438552 | C 403 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 17 | 438549 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
21 | 438553 | C 404 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 17 | 438549 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
22 | 438554 | C 5th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
23 | 438555 | C 501 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 22 | 438554 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
24 | 438556 | C 502 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 22 | 438554 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
25 | 438557 | C 503 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 22 | 438554 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
26 | 438558 | C 504 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 22 | 438554 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
27 | 438559 | C 6th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
28 | 438560 | C 601 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 27 | 438559 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
29 | 438561 | C 602 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 27 | 438559 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
30 | 438562 | C 603 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 27 | 438559 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
31 | 438563 | C 604 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 27 | 438559 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
32 | 438564 | C 7th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
33 | 438565 | C 701 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 32 | 438564 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
34 | 438566 | C 702 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 32 | 438564 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
35 | 438567 | C 703 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 32 | 438564 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
36 | 438568 | C 704 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 32 | 438564 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
37 | 438569 | C 8th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
38 | 438570 | C 801 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 37 | 438569 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
39 | 438571 | C 802 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 37 | 438569 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
40 | 438572 | C 803 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 37 | 438569 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
41 | 438573 | C 804 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 37 | 438569 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
42 | 438574 | C 9th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
43 | 438575 | C 901 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 42 | 438574 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
44 | 438576 | C 902 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 42 | 438574 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
45 | 438577 | C 903 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 42 | 438574 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
46 | 438578 | C 904 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 42 | 438574 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
47 | 438579 | C 10th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
48 | 438580 | C 1001 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 47 | 438579 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
49 | 438581 | C 1002 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 47 | 438579 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
50 | 438582 | C 1003 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 47 | 438579 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
51 | 438583 | C 1004 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 47 | 438579 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
52 | 438584 | C 11th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
53 | 438585 | C 1101 Ledge wall 100mm thk. BBM work | Sq.Ft | 234.7200 | 82.19 | 52 | 438584 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
54 | 438586 | C 1102 Ledge wall 100mm thk. BBM work | Sq.Ft | 184.5300 | 47.72 | 52 | 438584 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
55 | 438587 | C 1103 Ledge wall 100mm thk. BBM work | Sq.Ft | 83.1200 | 48.99 | 52 | 438584 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
56 | 438588 | C 1104 Ledge wall 100mm thk. BBM work | Sq.Ft | 242.4400 | 47.06 | 52 | 438584 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
57 | 438589 | C 12th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
58 | 438590 | C 1201 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.19 | 57 | 438589 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
59 | 438591 | C 1202 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.72 | 57 | 438589 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
60 | 438592 | C 1203 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.99 | 57 | 438589 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
61 | 438593 | C 1204 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.06 | 57 | 438589 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
62 | 438594 | C 13th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
63 | 438595 | C 1301 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 62 | 438594 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
64 | 438596 | C 1302 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 62 | 438594 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
65 | 438597 | C 1303 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 62 | 438594 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
66 | 438598 | C 1304 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 62 | 438594 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
67 | 438599 | C 14th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
68 | 438600 | C 1401 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 67 | 438599 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
69 | 438601 | C 1402 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 67 | 438599 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
70 | 438602 | C 1403 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 67 | 438599 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
71 | 438603 | C 1404 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 67 | 438599 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
72 | 438604 | C 15th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
73 | 438605 | C 1501 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 72 | 438604 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
74 | 438606 | C 1502 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 72 | 438604 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
75 | 438607 | C 1503 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 72 | 438604 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
76 | 438608 | C 1504 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 72 | 438604 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
77 | 438609 | C 16th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
78 | 438610 | C 1601 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 77 | 438609 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
79 | 438611 | C 1602 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 77 | 438609 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
80 | 438612 | C 1603 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 77 | 438609 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
81 | 438613 | C 1604 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 77 | 438609 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
82 | 438614 | C 17th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
83 | 438615 | C 1701 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 82 | 438614 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
84 | 438616 | C 1702 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 82 | 438614 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
85 | 438617 | C 1703 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 82 | 438614 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
86 | 438618 | C 1704 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 82 | 438614 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
87 | 438619 | C 18th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
88 | 438620 | C 1801 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 87 | 438619 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
89 | 438621 | C 1802 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 87 | 438619 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
90 | 438622 | C 1803 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 87 | 438619 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
91 | 438623 | C 1804 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 87 | 438619 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
92 | 438624 | C 19th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
93 | 438625 | C 1901 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 92 | 438624 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
94 | 438626 | C 1902 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 92 | 438624 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
95 | 438627 | C 1903 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 92 | 438624 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
96 | 438628 | C 1904 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 92 | 438624 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
97 | 438629 | C 20th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
98 | 438630 | C 2001 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 97 | 438629 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
99 | 438631 | C 2002 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 97 | 438629 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
100 | 438632 | C 2003 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 97 | 438629 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
101 | 438633 | C 2004 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 97 | 438629 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
102 | 438634 | C 21st Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
103 | 438635 | C 2101 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 102 | 438634 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
104 | 438636 | C 2102 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 102 | 438634 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
105 | 438637 | C 2103 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 102 | 438634 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
106 | 438638 | C 2104 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 102 | 438634 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
107 | 438639 | C 22nd Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
108 | 438640 | C 2201 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 107 | 438639 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
109 | 438641 | C 2202 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 107 | 438639 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
110 | 438642 | C 2203 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 107 | 438639 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
111 | 438643 | C 2204 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 107 | 438639 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
112 | 438644 | C 23rd Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
113 | 438645 | C 2301 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 112 | 438644 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
114 | 438646 | C 2302 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 112 | 438644 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
115 | 438647 | C 2303 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 112 | 438644 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
116 | 438648 | C 2304 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 112 | 438644 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
117 | 438649 | C 24th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
118 | 438650 | C 2401 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 117 | 438649 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
119 | 438651 | C 2402 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 117 | 438649 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
120 | 438652 | C 2403 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 117 | 438649 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
121 | 438653 | C 2404 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 117 | 438649 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
122 | 438654 | C 25th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
123 | 438655 | C 2501 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 122 | 438654 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
124 | 438656 | C 2502 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 122 | 438654 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
125 | 438657 | C 2503 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 122 | 438654 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
126 | 438658 | C 2504 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 122 | 438654 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
127 | 438659 | C 26th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
128 | 438660 | C 2601 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 127 | 438659 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
129 | 438661 | C 2602 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 127 | 438659 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
130 | 438662 | C 2603 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 127 | 438659 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
131 | 438663 | C 2604 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 127 | 438659 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
132 | 438664 | C 27th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
133 | 438665 | C 2701 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 132 | 438664 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
134 | 438666 | C 2702 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 132 | 438664 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
135 | 438667 | C 2703 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 132 | 438664 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
136 | 438668 | C 2704 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 132 | 438664 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
137 | 438669 | C 28th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
138 | 438670 | C 2801 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 137 | 438669 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
139 | 438671 | C 2802 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 137 | 438669 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
140 | 438672 | C 2803 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 137 | 438669 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
141 | 438673 | C 2804 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 137 | 438669 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
142 | 438674 | C 29th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
143 | 438675 | C 2901 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 142 | 438674 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
144 | 438676 | C 2902 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 142 | 438674 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
145 | 438677 | C 2903 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 142 | 438674 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
146 | 438678 | C 2904 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 142 | 438674 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
147 | 438679 | C 30th Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
148 | 438680 | C 3001 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 147 | 438679 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
149 | 438681 | C 3002 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 147 | 438679 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
150 | 438682 | C 3003 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 147 | 438679 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
151 | 438683 | C 3004 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 147 | 438679 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
152 | 438684 | C 31st Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
153 | 438685 | C 3101 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 152 | 438684 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
154 | 438686 | C 3102 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 152 | 438684 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
155 | 438687 | C 3103 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 152 | 438684 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
156 | 438688 | C 3104 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 152 | 438684 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
157 | 667321 | C 32nd Floor Ledge wall 100mm thk. BBM work | NA | 0.0000 | 0.0000 | 1 | 438533 | 31 | 0 | [6 empty] | 0.0000
158 | 667322 | C 3201 Ledge wall 100mm thk. BBM work | Sq.Ft | 82.1900 | 82.1900 | 157 | 667321 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
159 | 667323 | C 3202 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.7200 | 47.7200 | 157 | 667321 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
160 | 667324 | C 3203 Ledge wall 100mm thk. BBM work | Sq.Ft | 48.9900 | 48.9900 | 157 | 667321 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000
161 | 667325 | C 3204 Ledge wall 100mm thk. BBM work | Sq.Ft | 47.0600 | 47.0600 | 157 | 667321 | 4 | 1410 | Flyash Brickwork-150mm | [5 empty] | 0.0000