## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L) | Selected Group :- F- RCC Labour Work on Built-up Area (L)
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 482476 | F- RCC Labour Work on Built-up Area (L) | NA | 0.0000 | 0.0000 | 0 | 482475 | 31 | 0 | [6 empty] | 0.0000
2 | 482477 | F - 3rd Floor (4th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
3 | 538432 | F - 4th Slab RCC Lobour Work on Built.up Area(L) | Sq.Ft | 6780.67 | 6780.67 | 2 | 482477 | 4 | 31489 | C-Aluform RCC On Built-up area Basis | [5 empty] | 0.0000
4 | 482485 | F - 4th Floor (5th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
5 | 482486 | F - 4th Floor (5th Slab) Aluform RCC on built-up area Basis | Sq.Ft | 6780.67 | 6780.67 | 4 | 482485 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
6 | 482487 | F - 5th Floor (6th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
7 | 482488 | F - 5th Floor (6th Slab) Aluform RCC on built-up area Basis | Sq.Ft | 6780.67 | 6780.67 | 6 | 482487 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
8 | 482489 | F - 6th Floor (7th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
9 | 482490 | F - 6th Floor (7th Slab) Aluform RCC on built-up area Basis | Sq.Ft | 6780.67 | 6780.67 | 8 | 482489 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
10 | 482491 | F - 7th Floor (8th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
11 | 482492 | F - 7th Floor (8th Slab) Aluform RCC on built-up area Basis | Sq.Ft | 6780.67 | 6780.67 | 10 | 482491 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
12 | 482493 | F - 8th Floor (9th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
13 | 482494 | F - 8th Floor (9th Slab) Aluform RCC on built-up area Basis | Sq.Ft | 6780.67 | 6780.67 | 12 | 482493 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
14 | 482495 | F - 9th Floor (10th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
15 | 482496 | F - 9th Floor (10th Slab) Aluform RCC on built-up area Basis | Sq.Ft | 6780.67 | 6780.67 | 14 | 482495 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
16 | 482497 | F - 10th Floor (11th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
17 | 482498 | F - 10th Floor (11th Slab) Aluform RCC on built-up area Basi | Sq.Ft | 6780.67 | 6780.67 | 16 | 482497 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
18 | 482499 | F - 11th Floor (12th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
19 | 482500 | F - 11th Floor (12th Slab) Aluform RCC on built-up area Basi | Sq.Ft | 6780.67 | 6780.67 | 18 | 482499 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
20 | 482501 | F - 12th Floor (13th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
21 | 482502 | F - 12th Floor (13th Slab) Aluform RCC on built-up area Basi | Sq.Ft | 6780.67 | 6780.67 | 20 | 482501 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
22 | 482503 | F - 13th Floor (14th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
23 | 482504 | F - 13th Floor (14th Slab) Aluform RCC on built-up area Basi | Sq.Ft | 6780.67 | 6780.67 | 22 | 482503 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
24 | 482505 | F - 14th Floor (15th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
25 | 482506 | F - 14th Floor (15th Slab) Aluform RCC on built-up area Basi | Sq.Ft | 6780.67 | 6780.67 | 24 | 482505 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
26 | 482542 | F - 15th Floor (16th Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
27 | 482543 | F - Terrace Floor (16th Slab) Aluform RCC on built-up area B | Sq.Ft | 6780.67 | 6780.67 | 26 | 482542 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
28 | 482544 | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
29 | 482545 | Top Terrace,LMR,OHWT,Parapet wall pergola (L) Aluform RCC on | Sq.Ft | 6780.67 | 6780.67 | 28 | 482544 | 4 | 30576 | Aluform RCC on built-up area Basis | [5 empty] | 0.0000
30 | 482547 | F-Sorting & Shifting mockup,checking & rework | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
31 | 482548 | Sorting & Shifting mockup,checking (1st Floor) | Sq.Ft | 6780.67 | 6780.67 | 30 | 482547 | 4 | 19664 | Sorting & Shifting Mockup checking |  |  |  |  | Started | 0.0000
32 | 482549 | Shifting of shuttering material from last floor to G.F.(L) | Sq.Ft | 6780.67 | 6780.67 | 30 | 482547 | 4 | 19664 | Sorting & Shifting Mockup checking |  |  |  |  | Started | 0.0000
33 | 482550 | After Completion of all RCC Work of building | No. | 1.0000 | 1.0000 | 30 | 482547 | 4 | 19668 | After Completion of all RCC work of building |  |  |  |  | Started | 0.0000
34 | 538426 | F - LG Top Slab Floor (1st Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
35 | 538429 | F - 1st Slab RCC Lobour Work on Built-up Area(L) | Sq.Ft | 2358.5 | 2358.5 | 34 | 538426 | 4 | 31487 | C- RCC on Built-up area Basis | [5 empty] | 0.0000
36 | 538427 | F - 1st Floor (2nd slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
37 | 538430 | F -2nd Slab RCC Lobour Work on Built.up Area(L) | Sq.Ft | 7416.18 | 7416.18 | 36 | 538427 | 4 | 31487 | C- RCC on Built-up area Basis | [5 empty] | 0.0000
38 | 538428 | F - 2nd Floor (3rd Slab) | NA | 0.0000 | 0.0000 | 1 | 482476 | 31 | 0 | [6 empty] | 0.0000
39 | 538431 | F - 3rd Slab RCC Lobour Work on Built-up Area(L) | Sq.Ft | 7416.18 | 7416.18 | 38 | 538428 | 4 | 31489 | C-Aluform RCC On Built-up area Basis | [5 empty] | 0.0000