## Sheet1
Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work | Selected Group :- Fire Staicase Tread Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
496390 | Fire Staicase Lower Ground Floor Tread Work | R.Ft | 44.2800 | 44.2800 | 4249 | Granite Tread | R.Ft | 44.2800 | 90.0000 | 168.001.001.005.005.001.003.002.001.001. | 0.0000 | Labour | 0 | 0.0000
496390 | Fire Staicase Lower Ground Floor Tread Work | R.Ft | 44.2800 | 44.2800 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.001.001. | 0.0000 | Labour | 0 | 0.0000
496392 | Fire Staicase Ground Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.002.001. | 0.0000 | Labour | 0 | 0.0000
496392 | Fire Staicase Ground Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.002.001. | 0.0000 | Labour | 0 | 0.0000
496394 | Fire Staicase 1st Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.003.001. | 0.0000 | Labour | 0 | 0.0000
496394 | Fire Staicase 1st Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.003.001. | 0.0000 | Labour | 0 | 0.0000
496396 | Fire Staicase 2nd Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.004.001. | 0.0000 | Labour | 0 | 0.0000
496396 | Fire Staicase 2nd Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.004.001. | 0.0000 | Labour | 0 | 0.0000
496398 | Fire Staicase 3rd Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.005.001. | 0.0000 | Labour | 0 | 0.0000
496398 | Fire Staicase 3rd Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.005.001. | 0.0000 | Labour | 0 | 0.0000
496400 | Fire Staicase 4th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.006.001. | 0.0000 | Labour | 0 | 0.0000
496400 | Fire Staicase 4th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.006.001. | 0.0000 | Labour | 0 | 0.0000
496402 | Fire Staicase 5th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.007.001. | 0.0000 | Labour | 0 | 0.0000
496402 | Fire Staicase 5th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.007.001. | 0.0000 | Labour | 0 | 0.0000
496404 | Fire Staicase 6th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.008.001. | 0.0000 | Labour | 0 | 0.0000
496404 | Fire Staicase 6th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.008.001. | 0.0000 | Labour | 0 | 0.0000
496406 | Fire Staicase 7th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.009.001. | 0.0000 | Labour | 0 | 0.0000
496406 | Fire Staicase 7th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.009.001. | 0.0000 | Labour | 0 | 0.0000
496408 | Fire Staicase 8th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.010.001. | 0.0000 | Labour | 0 | 0.0000
496408 | Fire Staicase 8th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.010.001. | 0.0000 | Labour | 0 | 0.0000
496410 | Fire Staicase 9th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.011.001. | 0.0000 | Labour | 0 | 0.0000
496410 | Fire Staicase 9th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.011.001. | 0.0000 | Labour | 0 | 0.0000
496412 | Fire Staicase 10th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.012.001. | 0.0000 | Labour | 0 | 0.0000
496412 | Fire Staicase 10th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.012.001. | 0.0000 | Labour | 0 | 0.0000
496414 | Fire Staicase 11th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.013.001. | 0.0000 | Labour | 0 | 0.0000
496414 | Fire Staicase 11th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.013.001. | 0.0000 | Labour | 0 | 0.0000
496416 | Fire Staicase 12th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.014.001. | 0.0000 | Labour | 0 | 0.0000
496416 | Fire Staicase 12th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.014.001. | 0.0000 | Labour | 0 | 0.0000
496418 | Fire Staicase 13th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.015.001. | 0.0000 | Labour | 0 | 0.0000
496418 | Fire Staicase 13th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.015.001. | 0.0000 | Labour | 0 | 0.0000
496420 | Fire Staicase 14th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.016.001. | 0.0000 | Labour | 0 | 0.0000
496420 | Fire Staicase 14th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.016.001. | 0.0000 | Labour | 0 | 0.0000
496422 | Fire Staicase 15th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.017.001. | 0.0000 | Labour | 0 | 0.0000
496422 | Fire Staicase 15th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.017.001. | 0.0000 | Labour | 0 | 0.0000
496424 | Fire Staicase 16th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.018.001. | 0.0000 | Labour | 0 | 0.0000
496424 | Fire Staicase 16th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.018.001. | 0.0000 | Labour | 0 | 0.0000
496426 | Fire Staicase 17th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.019.001. | 0.0000 | Labour | 0 | 0.0000
496426 | Fire Staicase 17th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.019.001. | 0.0000 | Labour | 0 | 0.0000
519220 | Fire Staicase 18th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 4249 | Granite Tread | R.Ft | 88.5600 | 90.0000 | 168.001.001.005.005.001.003.002.020.001. | 0.0000 | Labour | 0 | 0.0000
519220 | Fire Staicase 18th Floor Tread Work | R.Ft | 88.5600 | 88.5600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0 | 0.0000 | 168.001.001.005.005.001.003.002.020.001. | 0.0000 | Labour | 0 | 0.0000