## Sheet1
Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work | Selected Group :- Regular Staicase Tread Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
496343 | Regular Staicase Lower Ground Floor Tread Work | R.Ft | 39.3600 | 39.3600 | 4249 | Granite Tread | R.Ft | 39.3600 | 0.0000 | 168.001.001.005.005.001.003.001.001.001. | 0.0000 | Labour | 0 | 0.0000
496343 | Regular Staicase Lower Ground Floor Tread Work | R.Ft | 39.3600 | 39.3600 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.001.001. | 0.0000 | Labour | 0 | 0.0000
496353 | Regular Staicase Ground Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.002.001. | 0.0000 | Labour | 0 | 0.0000
496353 | Regular Staicase Ground Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.002.001. | 0.0000 | Labour | 0 | 0.0000
496355 | Regular Staicase 1st Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.003.001. | 0.0000 | Labour | 0 | 0.0000
496355 | Regular Staicase 1st Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.003.001. | 0.0000 | Labour | 0 | 0.0000
496357 | Regular Staicase 2nd Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.004.001. | 0.0000 | Labour | 0 | 0.0000
496357 | Regular Staicase 2nd Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.004.001. | 0.0000 | Labour | 0 | 0.0000
496359 | Regular Staicase 3rd Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.005.001. | 0.0000 | Labour | 0 | 0.0000
496359 | Regular Staicase 3rd Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.005.001. | 0.0000 | Labour | 0 | 0.0000
496361 | Regular Staicase 4th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.006.001. | 0.0000 | Labour | 0 | 0.0000
496361 | Regular Staicase 4th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.006.001. | 0.0000 | Labour | 0 | 0.0000
496363 | Regular Staicase 5th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.007.001. | 0.0000 | Labour | 0 | 0.0000
496363 | Regular Staicase 5th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.007.001. | 0.0000 | Labour | 0 | 0.0000
496365 | Regular Staicase 6th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.008.001. | 0.0000 | Labour | 0 | 0.0000
496365 | Regular Staicase 6th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.008.001. | 0.0000 | Labour | 0 | 0.0000
496367 | Regular Staicase 7th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.009.001. | 0.0000 | Labour | 0 | 0.0000
496367 | Regular Staicase 7th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.009.001. | 0.0000 | Labour | 0 | 0.0000
496369 | Regular Staicase 8th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.010.001. | 0.0000 | Labour | 0 | 0.0000
496369 | Regular Staicase 8th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.010.001. | 0.0000 | Labour | 0 | 0.0000
496371 | Regular Staicase 9th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.011.001. | 0.0000 | Labour | 0 | 0.0000
496371 | Regular Staicase 9th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.011.001. | 0.0000 | Labour | 0 | 0.0000
496373 | Regular Staicase 10th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.012.001. | 0.0000 | Labour | 0 | 0.0000
496373 | Regular Staicase 10th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.012.001. | 0.0000 | Labour | 0 | 0.0000
496375 | Regular Staicase 11th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.013.001. | 0.0000 | Labour | 0 | 0.0000
496375 | Regular Staicase 11th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.013.001. | 0.0000 | Labour | 0 | 0.0000
496377 | Regular Staicase 12th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.014.001. | 0.0000 | Labour | 0 | 0.0000
496377 | Regular Staicase 12th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.014.001. | 0.0000 | Labour | 0 | 0.0000
496379 | Regular Staicase 13th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.015.001. | 0.0000 | Labour | 0 | 0.0000
496379 | Regular Staicase 13th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.015.001. | 0.0000 | Labour | 0 | 0.0000
496381 | Regular Staicase 14th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.016.001. | 0.0000 | Labour | 0 | 0.0000
496381 | Regular Staicase 14th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.016.001. | 0.0000 | Labour | 0 | 0.0000
496383 | Regular Staicase 15th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.017.001. | 0.0000 | Labour | 0 | 0.0000
496383 | Regular Staicase 15th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.017.001. | 0.0000 | Labour | 0 | 0.0000
496385 | Regular Staicase 16th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.018.001. | 0.0000 | Labour | 0 | 0.0000
496385 | Regular Staicase 16th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.018.001. | 0.0000 | Labour | 0 | 0.0000
496387 | Regular Staicase 17th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.019.001. | 0.0000 | Labour | 0 | 0.0000
496387 | Regular Staicase 17th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.019.001. | 0.0000 | Labour | 0 | 0.0000
519218 | Regular Staicase 18th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 4249 | Granite Tread | R.Ft | 83.64 | 0.0000 | 168.001.001.005.005.001.003.001.020.001. | 0.0000 | Labour | 0 | 0.0000
519218 | Regular Staicase 18th Floor Tread Work | R.Ft | 83.6400 | 83.6400 | 3863 | Kota Tread (L) - DSP | R.Ft | 0.0000 | 0.0000 | 168.001.001.005.005.001.003.001.020.001. | 0.0000 | Labour | 0 | 0.0000