## Sheet1
Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work | Selected Group :- A - West Side External painting Work
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 4745.471 | 4745.471 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 16140 | 1st Coat Putty (L) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 16142 | 1st Coat Putty (M) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 2697 | Quality & Schedule - BC | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 8713 | Scaffolding work | Sq.Ft | 339.9380 | 0.0000 | 168.001.001.005.016.001.001.001. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 16140 | 1st Coat Putty (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 16142 | 1st Coat Putty (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 2697 | Quality & Schedule - BC | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 8713 | Scaffolding work | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.002. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 16140 | 1st Coat Putty (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 16142 | 1st Coat Putty (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 2697 | Quality & Schedule - BC | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 8713 | Scaffolding work | Sq.Ft | 467.1150 | 0.0000 | 168.001.001.005.016.001.001.003. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.004. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.005. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.006. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.007. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.008. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 2350.319 | 2350.319 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.009. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.010. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.011. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.012. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.013. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 2350.319 | 2350.319 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.014. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 2521.203 | 2521.203 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.015. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 2120.228 | 2120.228 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.017. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 1287.687 | 1287.687 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.018. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 1287.687 | 1287.687 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.019. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 1116.803 | 1116.803 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16140 | 1st Coat Putty (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 16142 | 1st Coat Putty (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2697 | Quality & Schedule - BC | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 8713 | Scaffolding work | Sq.Ft | 437.2620 | 0.0000 | 168.001.001.005.016.001.001.020. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1214.61 | 1214.61 | 12503 | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 12502 | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 16140 | 1st Coat Putty (L) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 16142 | 1st Coat Putty (M) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 12715 | 1st Coat Semi-Acrylic Paint (L) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 12714 | 1st Coat Semi-Acrylic Paint (M) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 12717 | 2nd Coat Semi-Acrylic Paint (L) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 12719 | 2nd Coat Semi-Acrylic Paint (M) | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 2697 | Quality & Schedule - BC | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000
627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 8713 | Scaffolding work | Sq.Ft | 1633.4050 | 0.0000 | 168.001.001.005.016.001.001.021. | 0.0000 | Labour | 0 | 0.0000